## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | AUGMENTATION OF EXISTING LAYING DISTRIBUTION SYSTEM TO EXTEND THE BENEFIT OF 100% HOUSEHOLDS IN ZONE-III AT MANDIRBAZAR BLOCK WITHIN ' MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA- MATHURAPUR, DISTRICT- SOUTH 24 PGNS' UNDER SOUTH-24 PGNS W/S DIV | SM/15484 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000045/2022-2023 | 3016-SWD-I | 20/02/2023 |  | Resource Division | 368.04 | 0 | 0 | 0
2 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | AUGMENTATION OF EXISTING LAYING DISTRIBUTION SYSTEM TO EXTEND THE BENEFIT OF 100% HOUSEHOLDS IN ZONE-III AT MANDIRBAZAR BLOCK WITHIN ' MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA- MATHURAPUR, DISTRICT- SOUTH 24 PGNS' UNDER SOUTH-24 PGNS W/S DIV | SM/15484 | Augmentation | Preparation and submission of Detailed Survey, Design and Drawing for laying distribution system of UTTAR AKRABERIA MOUZA in MANDIRBAZAR (ZONE-III) Block under Mega Surface Water Based Water Supply Scheme for Falta-Mathurapur, South 24-Pgns. district. | AE HQ-I |  | ORD/000391/2021-2022 | 1985/SWDI | 27/01/2022 | 26/02/2022 | MS R. DUTTA AND CO | 4.83 | 4.65 | 96.29 | 100
3 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | AUGMENTATION OF EXISTING LAYING DISTRIBUTION SYSTEM TO EXTEND THE BENEFIT OF 100% HOUSEHOLDS IN ZONE-III AT MANDIRBAZAR BLOCK WITHIN ' MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA- MATHURAPUR, DISTRICT- SOUTH 24 PGNS' UNDER SOUTH-24 PGNS W/S DIV | SM/15484 | Augmentation | Boundary wall for proposed OHR Site Uttar Akrabaria within Mandirbazar block, Mouza-Uttar Akrabaria under Mega Surface Water Based Water Supply Secheme for Falta-Mathurapur, Dist. South 24 Paraganas. (Length- 397 mtr.) | AE HQ-I |  | ORD/000111/2021-2022 | 1115/SWD-I | 26/10/2021 | 24/01/2022 | UNITED BUILDERS | 60.18 | 18 | 29.91 | 0
4 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | AUGMENTATION OF EXISTING LAYING DISTRIBUTION SYSTEM TO EXTEND THE BENEFIT OF 100% HOUSEHOLDS IN ZONE-III AT MANDIRBAZAR BLOCK WITHIN ' MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA- MATHURAPUR, DISTRICT- SOUTH 24 PGNS' UNDER SOUTH-24 PGNS W/S DIV | SM/15484 | Augmentation | Hiring of additional 01 (one) no. diesel driven Non-Air conditioner Motor Cab having BS-III & above category (Luxury Ambassador / Indica / Swift Dezire Car) with driver for official use of the Assistant Engineers under South 24-Pgns. W/S Division-I, PHE Dte. [w.e.f. 01/04/2023 to 30/09/2023] | AE HQ-II |  | ORD/000875/2022-2023 | 3728/SWD-I | 31/03/2023 | 30/09/2023 | SUBRAT KUMAR SETHY | 0.87 | 1.55 | 177.97 | 50
5 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | AUGMENTATION OF EXISTING LAYING DISTRIBUTION SYSTEM TO EXTEND THE BENEFIT OF 100% HOUSEHOLDS IN ZONE-III AT MANDIRBAZAR BLOCK WITHIN ' MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA- MATHURAPUR, DISTRICT- SOUTH 24 PGNS' UNDER SOUTH-24 PGNS W/S DIV | SM/15484 | Augmentation | Continuation order for the work of Hiring of additional 01 (one) no. diesel driven Non-Air conditioner Motor Cab having BS-III & above category (Luxury Ambassador / Indica / Swift Dezire Car) with driver for official use of the Assistant Engineers under South 24-Pgns. W/S Division-I, PHE Dte. [w.e.f. 01/10/2023 to 31/03/2024] | AE HQ-II | JE-2 | ORD/000582/2023-2024 | 2389/SWD-I | 27/09/2023 | 28/03/2024 | SUBRAT KUMAR SETHY | 0.87 | 1.1 | 126.17 | 25
6 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | AUGMENTATION OF EXISTING LAYING DISTRIBUTION SYSTEM TO EXTEND THE BENEFIT OF 100% HOUSEHOLDS IN ZONE-III AT MANDIRBAZAR BLOCK WITHIN ' MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA- MATHURAPUR, DISTRICT- SOUTH 24 PGNS' UNDER SOUTH-24 PGNS W/S DIV | SM/15484 | Augmentation | Construction of 1000 cum OHR , Laying distrbution main pipe line with FHTC for 'Augmentation of existing Laying Distribution System to extend the benefit of 100% households and providing FHTC from existing distribution system in Zone-III at Mandirbazar Block within " Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District- South 24 Pgns" under South-24 Pgns W/S Divn-I of South 24-Pgns. W/S Circle, PHE Dte'. (No of FHTC.7715) | AE HQ-I,AE HQ-II | JE-3 | ORD/000542/2023-2024 | 2461/SWD-I | 04/10/2023 | 30/07/2024 | SUPRITI ENTERPRISE | 1557.57 | 114.6 | 7.36 | 10
7 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | AUGMENTATION OF EXISTING LAYING DISTRIBUTION SYSTEM TO EXTEND THE BENEFIT OF 100% HOUSEHOLDS IN ZONE-III AT MANDIRBAZAR BLOCK WITHIN ' MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA- MATHURAPUR, DISTRICT- SOUTH 24 PGNS' UNDER SOUTH-24 PGNS W/S DIV | SM/15484 | Augmentation | Continuation order for the work of Hiring of additional 01 (one) no. diesel driven Non-Air conditioner Motor Cabhaving BS-III & above category (Luxury Ambassador / Indica / Swift Dezire Car) with driver for official use of the Assistant Engineers under South 24-Pgns. W/S Division-I, PHE Dte. [w.e.f. 01/04/2024 to 30/09/2024] | AE HQ-II | JE-2 | ORD/000904/2023-2024 | 1493/SWD-I | 30/03/2024 | 29/09/2024 | SUBRAT KUMAR SETHY | 0.87 | 1.18 | 135.6 | 0
Total | [13 empty] | 1993.23 | 141.08 | 7.08