## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | AUGMENTATION OF EXISTING LAYING DISTRIBUTION SYSTEM TO EXTEND THE BENEFIT OF 100% HOUSEHOLDS IN ZONE-II AT MANDIRBAZAR BLOCK WITHIN ' MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA- MATHURAPUR, DISTRICT- SOUTH 24 PGNS' UNDER SOUTH-24 PGNS W/S DIVN | SM/15485 | Augmentation | Preparation and submission of Detailed Survey, Design and Drawing for laying distribution system of PUKURIA MOUZA in MANDIRBAZAR (ZONE-II) Block under Mega Surface Water Based Water Supply Scheme for Falta-Mathurapur, South 24-Pgns. district. |  |  | ORD/000514/2021-2022 | 1984/SWD-I | 27/01/2022 | 26/02/2022 | RADIANT | 4.83 | 0 | 0 | 100
2 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | AUGMENTATION OF EXISTING LAYING DISTRIBUTION SYSTEM TO EXTEND THE BENEFIT OF 100% HOUSEHOLDS IN ZONE-II AT MANDIRBAZAR BLOCK WITHIN ' MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA- MATHURAPUR, DISTRICT- SOUTH 24 PGNS' UNDER SOUTH-24 PGNS W/S DIVN | SM/15485 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000044/2022-2023 | 3016/SWD-I | 20/02/2023 | 20/02/2023 | Resource Division | 395.19 | 0 | 0 | 0
3 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | AUGMENTATION OF EXISTING LAYING DISTRIBUTION SYSTEM TO EXTEND THE BENEFIT OF 100% HOUSEHOLDS IN ZONE-II AT MANDIRBAZAR BLOCK WITHIN ' MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA- MATHURAPUR, DISTRICT- SOUTH 24 PGNS' UNDER SOUTH-24 PGNS W/S DIVN | SM/15485 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000212/2023-2024 | 670 | 24/05/2023 | 24/05/2023 | Resource Division | 500.47 | 0 | 0 | 0
4 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | AUGMENTATION OF EXISTING LAYING DISTRIBUTION SYSTEM TO EXTEND THE BENEFIT OF 100% HOUSEHOLDS IN ZONE-II AT MANDIRBAZAR BLOCK WITHIN ' MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA- MATHURAPUR, DISTRICT- SOUTH 24 PGNS' UNDER SOUTH-24 PGNS W/S DIVN | SM/15485 | Augmentation | Construction of Boundary wall for proposed 1250 Cum OHR Site of Zone-II within Mandirbazar block, Mouza-PurbaBishnupur (JL No-23), under Mega Surface Water Based Water Supply Secheme for Falta-Mathurapur, Dist. South 24 Paraganas. (Length- 145 mtr.) | AE HQ-I | JE-3 | ORD/000023/2022-2023 | 878/SWD-I | 14/07/2022 | 12/09/2022 | A P POWER AND CONCRETE | 27.53 | 0 | 0 | 50
5 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | AUGMENTATION OF EXISTING LAYING DISTRIBUTION SYSTEM TO EXTEND THE BENEFIT OF 100% HOUSEHOLDS IN ZONE-II AT MANDIRBAZAR BLOCK WITHIN ' MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA- MATHURAPUR, DISTRICT- SOUTH 24 PGNS' UNDER SOUTH-24 PGNS W/S DIVN | SM/15485 | Augmentation | Supplying, fitting & fixing Doors, Windows & allied works in Mandirbazar GLR cum Pump house, Sub-Station Building, Chlorination Building, Office Building, Dormitory Building & Guard Room etc. for Augmentation of existing Laying Distribution System to extend the benefit of 100% households in Zone-II at Mandirbazar Block within " Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District- South 24 Pgns" under South-24 Pgns W/S Divn-I (TSM/014522) | AE HQ-I | JE-3 | ORD/000547/2023-2024 | 2495/SWD-I | 06/10/2023 | 05/12/2023 | AVIK ENTERPRISE | 33.18 | 0 | 0 | 100
6 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | AUGMENTATION OF EXISTING LAYING DISTRIBUTION SYSTEM TO EXTEND THE BENEFIT OF 100% HOUSEHOLDS IN ZONE-II AT MANDIRBAZAR BLOCK WITHIN ' MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA- MATHURAPUR, DISTRICT- SOUTH 24 PGNS' UNDER SOUTH-24 PGNS W/S DIVN | SM/15485 | Augmentation | Construction of Approach Road with allied for Head Work Site Augmentation of existing laying distribution system to extend the benefit of 100% households in Zone-II at Mandirbazar Block within Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District- South 24 pgns under South-24 pgns W/S Divn-I of South 24-pgns. W/S Circle, Phe Dte. (TSM/14522) | AE HQ-II | JE-3 | ORD/000618/2023-2024 | 2802/SWD-I | 09/11/2023 | 24/12/2023 | A.P POWER AND CONCRETE | 8.99 | 0 | 0 | 100
7 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | AUGMENTATION OF EXISTING LAYING DISTRIBUTION SYSTEM TO EXTEND THE BENEFIT OF 100% HOUSEHOLDS IN ZONE-II AT MANDIRBAZAR BLOCK WITHIN ' MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA- MATHURAPUR, DISTRICT- SOUTH 24 PGNS' UNDER SOUTH-24 PGNS W/S DIVN | SM/15485 | Augmentation | Piling work for protection of Mandirbazar Hatuganj road near Mandirbazar P.S. damaged due to construction of 1200 mm dia valve chamber for in connection with Augmentation of existing laying distribution system to extend the benefit of 100% households in Zone-II at Mandirbazar block within Mega Surface Water Based Water Supply Scheme for Falta-Mathurapur, Dist. South 24-Pgs. under South 24-Pgns. W/S Division-I, PHE Dte. (SM/ 15485) [2nd call] | AE HQ-II | JE-3 | ORD/000716/2023-2024 | 359/SWD-I | 16/01/2024 | 31/01/2024 | M/S SUBHODEEP ENTERPRISE | 1.19 | 0 | 0 | 100
8 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | AUGMENTATION OF EXISTING LAYING DISTRIBUTION SYSTEM TO EXTEND THE BENEFIT OF 100% HOUSEHOLDS IN ZONE-II AT MANDIRBAZAR BLOCK WITHIN ' MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA- MATHURAPUR, DISTRICT- SOUTH 24 PGNS' UNDER SOUTH-24 PGNS W/S DIVN | SM/15485 | Augmentation | Development of Land and Construction of Temporary pathway at OHR Site of Mandirbazar Block for Augmentation of existing Laying Distribution System to extend the benefit of 100% households from existing distribution system in Zone-II at Mandirbazar Block within Mega Surface Water Based W/S Scheme for Falta-Mathurapur, Dist- South 24-Pgns. under South 24-Parganas W/S Divn.-I, PHE Dte. (TSM/014522) | AE HQ-II | JE-3 | ORD/000744/2023-2024 | 549/SWD-I | 31/01/2024 | 01/03/2024 | RIVER BENZ CONSTRUCTION | 3.01 | 0 | 0 | 100
9 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | AUGMENTATION OF EXISTING LAYING DISTRIBUTION SYSTEM TO EXTEND THE BENEFIT OF 100% HOUSEHOLDS IN ZONE-II AT MANDIRBAZAR BLOCK WITHIN ' MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA- MATHURAPUR, DISTRICT- SOUTH 24 PGNS' UNDER SOUTH-24 PGNS W/S DIVN | SM/15485 | Augmentation | Construction of 1250 cum OHR, Laying distrbution main pipe line with FHTC for Augmentation of existing Laying Distribution System to extend the benefit of 100% households and providing FHTC from existing distribution system in Zone-II at Mandirbazar Block within Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District- South 24 Pgns under South-24 Pgns W/S Divn-I of South 24-Pgns. W/S Circle, PHE Dte. (No of FHTC = 9619) | AE HQ-I | JE-3 | ORD/000054/2023-2024 | 273/SWD-I | 24/04/2023 | 01/04/2025 | ALOK ENTERPRISE (A UNIT OF SAKET TREXIM PVT. LTD.) | 1667.83 | 0 | 0 | 20
Total | [13 empty] | 2642.23 | 0 | 0