## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based RAMNAGAR (ZONE-II) piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas dis | SM/15634 | Augmentation | Preparation and submission of Detailed Project Report of RAMNAGAR(II) Ground Water Based Piped Water Supply Scheme in BARUIPUR PURBA Assembly Constituency of BARUIPUR Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE BSD |  | ORD/000404/2021-2022 | 1946/SWD-I | 27/01/2022 | 26/02/2022 | ENVIROTECH SOLUTIONS | 2.76 | 2.72 | 98.5 | 0
2 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based RAMNAGAR (ZONE-II) piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas dis | SM/15634 | Augmentation | Sinking of 02 (Two) nos. Rig bored 250mm x 150mm dia. & 300 mtr. deep Tubewell having 66 mtr. housing pipe by Rotary method for RAMNAGAR (ZONE-II) PWSS to accommodate FHTC in BARUIPUR block for Augmentaion of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division-I, P.H.E. Dte. [TSM/018217] | AE BSD |  | ORD/000602/2022-2023 | 3125/SWD-I | 24/02/2023 | 26/03/2023 | SARWAR JAMAN | 31.77 | 15.54 | 48.93 | 50
3 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based RAMNAGAR (ZONE-II) piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas dis | SM/15634 | Augmentation | Construction of Boundary Wall, Chlorine Room along with Laying of Distribution System, Rising Main, Providing Functional Household Tap Connection (FHTC) for Augmentation of RAMNAGAR (PART-II) MOUZA Piped Water Supply Scheme of BARUIPUR Block for implementation of JJM under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. [No. of FHTC = 1885] [TSM/018217] | AE BSD | JE RWS,JE-2 | ORD/000028/2023-2024 | 112/SWD-I | 11/04/2023 | 31/03/2025 | JYOTY SOLAR POWER (EMAIL ID-INFO.JYOTYSOLARPOWER@GMAIL.COM) | 288.53 | 249.37 | 86.43 | 100
4 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Ground water based RAMNAGAR (ZONE-II) piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas dis | SM/15634 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1 &2 for Augmentation of Ramnagar (Zone-II) water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Baruipur] | Assistant Engineer | Junior Engineer | ORD/000063/2023-2024 | 1057/SMD | 18/04/2023 | 17/07/2023 | ELECTRICAL & MECHANICAL ENGINEERING CORPORATION | 25.66 | 25.13 | 97.92 | 100
5 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Ground water based RAMNAGAR (ZONE-II) piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas dis | SM/15634 | Augmentation | Improvement of outdoor Illumination arrangement with allied works at Pump House no-2 of Ramnagar (Zone-II) W/S Scheme under SMD, P.H.E. Dte. (Block-Baruipur) | Assistant Engineer | Junior Engineer | ORD/002343/2023-2024 | 1527/SMSD | 14/12/2023 | 29/12/2023 | ELECTRICAL & MECHANICAL ENGINEERING CORPORATION | 0.92 | 0.92 | 99.62 | 100
6 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Ground water based RAMNAGAR (ZONE-II) piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas dis | SM/15634 | Augmentation | Improvement of outdoor Illumination arrangement with allied works at Pump House no-1 of Ramnagar (Zone-II) W/S Scheme under SMD, P.H.E. Dte. (Block-Baruipur) | Assistant Engineer | Junior Engineer | ORD/002346/2023-2024 | 1455/SMSD | 30/11/2023 | 15/12/2023 | ELECTRICAL & MECHANICAL ENGINEERING CORPORATION | 0.92 | 0.92 | 99.62 | 100
7 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Ground water based RAMNAGAR (ZONE-II) piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas dis | SM/15634 | Augmentation | Supply & Fixing main switch & Bus bar at Pump House no-1 & 2 of Ramnagar (Zone-II) W/S Scheme under SMD, P.H.E. Dte.(Block-Baruipur) | Assistant Engineer | Junior Engineer | ORD/002382/2023-2024 | 1453/SMSD | 30/11/2023 | 15/12/2023 | ELECTRICAL & MECHANICAL ENGINEERING CORPORATION | 0.58 | 0.58 | 100 | 100
8 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based RAMNAGAR (ZONE-II) piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas dis | SM/15634 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000109/2023-2024 | 294/SWD-I | 25/04/2023 | 25/04/2023 | Resource Division | 18.89 | 0 | 0 | 0
9 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Ground water based RAMNAGAR (ZONE-II) piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas dis | SM/15634 | Augmentation | Payment of electricity bill for new service connection under SMD, PHE Dte. |  |  | BILL/01504/2023-2024 | BP-2023-24-175 | 02/08/2023 | 02/08/2023 | WBSEDCL | 7.34 | 0 | 0 | 0
10 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based RAMNAGAR (ZONE-II) piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas dis | SM/15634 | Augmentation | Construction of Boundary wall, Platform for providung FHTC, Protection works for Pipeline and other allied Works for ''Proposed Ground Water based RAMNAGAR [ZONE-II] piped water supply schee to accoodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Areas of South 24 Parganas District.'' (SM/15634) |  |  | ORD/000425/2024-2025 | 3752/SWD-I | 28/08/2024 | 12/10/2024 | SUPER CONSTRUCTION | 72.09 | 0 | 0 | 0
11 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Ground water based RAMNAGAR (ZONE-II) piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas dis | SM/15634 | Augmentation | Supply & installation of LED board at P.H. No- 1 & 2 of RAMNAGAR (Zone-II) water supply scheme under South 24 Pgs Mechanical Division PHE Dte.[ Block- Baruipur ] | Assistant Engineer | Junior Engineer | ORD/002197/2023-2024 | 355/SMSD | 20/03/2024 | 04/04/2024 | NITESH MANAGEMENT | 0.78 | 0.78 | 100 | 100
12 | SOUTH 24 PARGANAS |  | Alipore Division | Ground water based RAMNAGAR (ZONE-II) piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas dis | SM/15634 | Augmentation | Road restoration 1) Chandakhali to Dhapdhapi More 2) Ramnagar Bazar to Matiar Dhali House 3) Doctor More to Madanpur Ashok Sangha CIub 4) Construction of road from T03 SurJapur Hat to Ramnagar to petrol pump on Pultala Champahali Road of PMGSY-III under Baruipur Block.(WB 02 573) |  |  | BILL/01667/2024-2025 | BP-2024-25-774 | 23/10/2024 | 23/10/2024 | W.B.S.R.D.A., SOUTH TWENTY FOUR PARGANAS DIVISION | 7.11 | 0 | 0 | 0
Total | [13 empty] | 457.34 | 295.95 | 64.71