## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Proposed ground water based ASUTI I/II & CHATTA GP piped water supply scheme to accommodate FHTC in THAKURPUKUR MAHESHTALA block under South 24 parganas W/S division-I, South 24 parganas district | SM/15660 | Augmentation | Supply, installation, commissioning and trial run of auto cum manual control panel including pumping machinery and related accessories at Tube Well no.1 of Chata Gram Panchayet area under South 24-Pgs Mechanical Division PHE Dte. | Assistant Engineer -II | Junior Engineer | ORD/003266/2021-2022 | 914/SMD | 09/08/2021 | 07/11/2021 | J.K. ENGINEERING CO. | 5.81 | 0 | 0 | 0
2 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Proposed ground water based ASUTI I/II & CHATTA GP piped water supply scheme to accommodate FHTC in THAKURPUKUR MAHESHTALA block under South 24 parganas W/S division-I, South 24 parganas district | SM/15660 | Augmentation | Supply, installation & Commissioning of 30 KVA voltage stabilizer at Asuti-I&II Gram Panchayet area Block-Thakurpukur Maheshtala under South 24-Pgs Mechanical Division PHE Dte. |  |  | ORD/003608/2021-2022 | 868/SMD | 28/07/2021 | 27/08/2021 | S.P. CONSTRUCTION | 3.93 | 0 | 0 | 0
3 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Proposed ground water based ASUTI I/II & CHATTA GP piped water supply scheme to accommodate FHTC in THAKURPUKUR MAHESHTALA block under South 24 parganas W/S division-I, South 24 parganas district | SM/15660 | Augmentation | Investigation of Soil for the proposed Over Head Reservoir (Capacity - 1300 m3) site inside Zone no.- I (Mouza- Kalikapur, JL No.- 22, Plot No.- 4323) of Asuti-I/Asuti-II and Chata GP W/S Scheme within Thakurpukur Maheshtala Block under South 24 Parganas Water Supply Division-I, PHE Dte. | AE SWSD-I |  | ORD/000460/2021-2022 | 1221/SWD-I | 12/11/2021 | 12/12/2021 | G TECH INDIA | 0.54 | 0.54 | 100 | 100
4 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Proposed ground water based ASUTI I/II & CHATTA GP piped water supply scheme to accommodate FHTC in THAKURPUKUR MAHESHTALA block under South 24 parganas W/S division-I, South 24 parganas district | SM/15660 | Augmentation | Construction of Pump House at Chatta Kalikapur Mouza in connection to Water Supply arrangement for Asuti I / II and Chatta under Thakurpukur Maheshtala Block under South 24-Pgns. W/S Division-I, PHE Dte. | AE SWSD-I |  | ORD/000385/2020-2021 | 2065/SWD-I | 19/02/2021 | 20/05/2021 | SAMPSON INFRA DESIGN LLP | 8.63 | 8.49 | 98.41 | 100
5 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Proposed ground water based ASUTI I/II & CHATTA GP piped water supply scheme to accommodate FHTC in THAKURPUKUR MAHESHTALA block under South 24 parganas W/S division-I, South 24 parganas district | SM/15660 | Augmentation | Construction of Pump House at Ganney Gangadharpur Mouza in connection to Water Supply arrangement for Asuti I / II and Chatta under Thakurpukur Maheshtala Block under South 24-Pgns. W/S Division-I, PHE Dte. | AE SWSD-I |  | ORD/000767/2020-2021 | 2063/SWD-I | 19/02/2021 | 20/05/2021 | J. ENTERPRISE | 9.43 | 9.3 | 98.62 | 100
6 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Proposed ground water based ASUTI I/II & CHATTA GP piped water supply scheme to accommodate FHTC in THAKURPUKUR MAHESHTALA block under South 24 parganas W/S division-I, South 24 parganas district | SM/15660 | Augmentation | Providing FHTC for Zone I (Part) and adjoining areas under Thakurpukur Maheshtala Block, PHE Dte. under South 24-Pgns. W/S Division-I, PHE Dte., District-South 24 Parganas. | AE SWSD-I | JE-2 | ORD/000007/2022-2023 | 821/SWD-I | 08/07/2022 | 02/07/2025 | M/S. S.S. ENTERPRISE | 316.71 | 0 | 0 | 80
7 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Proposed ground water based ASUTI I/II & CHATTA GP piped water supply scheme to accommodate FHTC in THAKURPUKUR MAHESHTALA block under South 24 parganas W/S division-I, South 24 parganas district | SM/15660 | Augmentation | Laying of UPVC pipeline for Zone-I of Chata GP under Thakurpukur-Maheshtala Water Supply Scheme under SWD-I, PHE Dte., District-South 24-Parganas. | AE SWSD-I | JE-2 | ORD/000205/2022-2023 | 733/SWD-I | 27/06/2022 | 02/01/2026 | M/S. S.S. ENTERPRISE | 526.13 | 383.61 | 72.91 | 65
8 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Proposed ground water based ASUTI I/II & CHATTA GP piped water supply scheme to accommodate FHTC in THAKURPUKUR MAHESHTALA block under South 24 parganas W/S division-I, South 24 parganas district | SM/15660 | Augmentation | Laying Rising Main from proposed Tubewell to existing OHR for zone I with interconnection and bypass arrangement of Asuti Chatta W/S Scheme under Thakurpukur Maheshtala Block under South 24-Parganas W/S Division-I, PHE Dte | AE SWSD-I | JE-2 | ORD/000175/2021-2022 | 2389/SWD-I | 25/02/2022 | 01/04/2025 | M/S. S.S. ENTERPRISE | 67.25 | 45.42 | 67.55 | 25
9 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Proposed ground water based ASUTI I/II & CHATTA GP piped water supply scheme to accommodate FHTC in THAKURPUKUR MAHESHTALA block under South 24 parganas W/S division-I, South 24 parganas district | SM/15660 | Augmentation | Construction of Pump House (Size 4.80mX3.66m) at tubewell site Sonamukhi Krishnanagar (JL-38, Plot-22) for water supply arrangement of Ashuti-Chata Water supply scheme under South 24-Pgns W/S-I, PHE Dte. Dist. South 24 Paraganas. | AE SWSD-I |  | ORD/000416/2021-2022 | 2385/SWD-I | 25/02/2022 | 26/04/2022 | M/S. TORSA ENTERPRISE | 7.56 | 7.1 | 93.96 | 0
10 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Proposed ground water based ASUTI I/II & CHATTA GP piped water supply scheme to accommodate FHTC in THAKURPUKUR MAHESHTALA block under South 24 parganas W/S division-I, South 24 parganas district | SM/15660 | Augmentation | Construction of Pump House (Size 4.80mX3.66m) at tubewell site Chata Kalikapur (JL-22, Plot-4350) for water supply arrangement of Ashuti-Chata Water supply scheme under South 24-Pgns W/S-I, PHE Dte. Dist. South 24 Paraganas. | AE S24D1 | JE-2 | ORD/000606/2021-2022 | 2383/SWD-I | 25/02/2022 | 26/04/2022 | M/S. SREEJIT ENTERPRISE | 6.08 | 0 | 0 | 0
11 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Proposed ground water based ASUTI I/II & CHATTA GP piped water supply scheme to accommodate FHTC in THAKURPUKUR MAHESHTALA block under South 24 parganas W/S division-I, South 24 parganas district | SM/15660 | Augmentation | Construction of Boundary wall for proposed Pump House Site at Ganney Gangadharpur Mouza near Asuti II GP under Asuti Chatta W/S Scheme , Dist. South 24 Paraganas under South 24-Pgns. W/S Divn.-I, PHE Dte. [2nd call] | AE SWSD-I |  | ORD/000068/2022-2023 | 1113/SWD-I | 23/08/2022 | 22/10/2022 | JYOTI ENTERPRISE | 6.01 | 5.97 | 99.35 | 0
12 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Proposed ground water based ASUTI I/II & CHATTA GP piped water supply scheme to accommodate FHTC in THAKURPUKUR MAHESHTALA block under South 24 parganas W/S division-I, South 24 parganas district | SM/15660 | Augmentation | Sinking of 2 nos. Rig Ground bored 300mm x 200mm dia. & 300 mtr. deep Tubewell by Rotary method for Zone-II under Ashuti Chata water supply scheme in Thakurpukur-Maheshtala Block, South 24 Paraganas District. | AE SWSD-I |  | ORD/000331/2021-2022 | 2388/SWD-I JJM | 25/02/2022 | 26/04/2022 | M/S. S.S. ENTERPRISE | 34.05 | 32.55 | 95.6 | 0
13 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Proposed ground water based ASUTI I/II & CHATTA GP piped water supply scheme to accommodate FHTC in THAKURPUKUR MAHESHTALA block under South 24 parganas W/S division-I, South 24 parganas district | SM/15660 | Augmentation | Construction of Over Head Reservoir of capacity 1500 cum at ZONE - I of Asuti-I/II & Chata water supply scheme under South 24 Pgs Water Supply Divn.-I . PHE Dte. | AE SWSD-I | JE-2 | ORD/000206/2022-2023 | 158/SWD-I | 25/04/2022 | 01/01/2026 | M/S. S.S. ENTERPRISE | 344.98 | 314.94 | 91.29 | 100
14 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Proposed ground water based ASUTI I/II & CHATTA GP piped water supply scheme to accommodate FHTC in THAKURPUKUR MAHESHTALA block under South 24 parganas W/S division-I, South 24 parganas district | SM/15660 | Augmentation | Sinking of 3 nos. Rig Ground bored 300mm x 200mm dia. & 300 mtr. deep Tubewell by Rotary method for Zone-I under Ashuti Chata water supply scheme in Thakurpukur-Maheshtala Block, South 24 Paraganas District. [2nd Call] | AE SWSD-I |  | ORD/000009/2022-2023 | 853/SWD-I | 12/07/2022 | 10/09/2022 | M/S. S.S. ENTERPRISE | 50.84 | 47.64 | 93.7 | 100
15 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Proposed ground water based ASUTI I/II & CHATTA GP piped water supply scheme to accommodate FHTC in THAKURPUKUR MAHESHTALA block under South 24 parganas W/S division-I, South 24 parganas district | SM/15660 | Augmentation | Construction of Pump House (Size 4.80mX3.66m) at tubewell site Shankharipota (JL-36, Plot-69) for water supply arrangement of Ashuti-Chata Water supply scheme under South 24-Pgns W/S-I, PHE Dte. Dist. South 24 Paraganas. | AE SWSD-I |  | ORD/000389/2021-2022 | 2386/SWD-I | 25/02/2022 | 26/04/2022 | M/S. DAS ENTERPRISE | 7.57 | 7.19 | 94.91 | 100
16 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Proposed ground water based ASUTI I/II & CHATTA GP piped water supply scheme to accommodate FHTC in THAKURPUKUR MAHESHTALA block under South 24 parganas W/S division-I, South 24 parganas district | SM/15660 | Augmentation | Construction of Pump House (Size 4.80mX3.66m) at tubewell site Ganney Gangadharpur (JL-28, Plot-510) for water supply arrangement of Ashuti-Chata Water supply scheme under South 24-Pgns W/S-I, PHE Dte. Dist. South 24 Paraganas. | AE SWSD-I |  | ORD/000358/2021-2022 | 2384/SWD-I | 25/02/2022 | 26/04/2022 | JYOTI ENTERPRISE | 7.57 | 7.49 | 98.98 | 0
17 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Proposed ground water based ASUTI I/II & CHATTA GP piped water supply scheme to accommodate FHTC in THAKURPUKUR MAHESHTALA block under South 24 parganas W/S division-I, South 24 parganas district | SM/15660 | Augmentation | Construction of Pump House (Size 4.80mX3.66m) at tubewell site Chata Kalikapur (JL-22, Kh-1) for water supply arrangement of Ashuti-Chata Water supply scheme under South 24-Pgns W/S-I, PHE Dte. Dist. South 24 Paraganas. | AE SWSD-I |  | ORD/000459/2021-2022 | 2382/SWD-I | 25/02/2022 | 26/04/2022 | SNEHA CONSTRUCTION | 5.02 | 4.85 | 96.57 | 100
18 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Proposed ground water based ASUTI I/II & CHATTA GP piped water supply scheme to accommodate FHTC in THAKURPUKUR MAHESHTALA block under South 24 parganas W/S division-I, South 24 parganas district | SM/15660 | Augmentation | Construction of Boundary wall for proposed Pump House Site at Sonamukhi Krishnanagar under Asuti Chatta W/S Scheme , Dist. South 24 Paraganas under South 24-Pgns. W/S Divn.-I, PHE Dte. | AE SWSD-I | JE-1 | ORD/000008/2022-2023 | 850/SWD-I | 12/07/2022 | 10/09/2022 | M/S. TORSA ENTERPRISE | 7.04 | 6.33 | 89.88 | 100
19 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Proposed ground water based ASUTI I/II & CHATTA GP piped water supply scheme to accommodate FHTC in THAKURPUKUR MAHESHTALA block under South 24 parganas W/S division-I, South 24 parganas district | SM/15660 | Augmentation | Construction of 05 (Five) nos. Boundary Wall (Length 51 m X 5 nos.) at tubewell site for ASUTI I & II and CHATTA GP PWSS to accommodate FHTC in Thakurpukur-Maheshtala Block under South 24 Parganas Water Supply Division-I, PHE Dte. [TSM/019643] | AE SWSD-I | JE-2 | ORD/000663/2022-2023 | 3379/SWD-I | 10/03/2023 | 24/04/2023 | SIMRAN ENTERPRISE | 42.26 | 13.33 | 31.54 | 60
20 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Proposed ground water based ASUTI I/II & CHATTA GP piped water supply scheme to accommodate FHTC in THAKURPUKUR MAHESHTALA block under South 24 parganas W/S division-I, South 24 parganas district | SM/15660 | Augmentation | Providing Balance FHTC for ThakurpukurMaheshtala Block (Part) in connection to "Piped Water Supply Scheme for ASUTI I & ASUTI II GP under South 24 Parganas W/S Division-I, PHE, Dte. Dist. South 24 Pgns. [TSM/010373] | AE SWSD-I | JE-1 | ORD/000701/2022-2023 | 3510/SWD-I | 17/03/2023 | 28/02/2025 | J D J ENTERPRISE (A UNIT OF J D J TRADERS PVT. LTD.) | 72.39 | 0 | 0 | 10
21 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Proposed ground water based ASUTI I/II & CHATTA GP piped water supply scheme to accommodate FHTC in THAKURPUKUR MAHESHTALA block under South 24 parganas W/S division-I, South 24 parganas district | SM/15660 | Augmentation | Construction of 05 (Five) nos. Pump Houses (Size 4.80 m X 3.66 m) at tubewell site for ASUTI I & II and CHATTA GP PWSS to accommodate FHTC in Thakurpukur-Maheshtala Block under South 24 Parganas Water Supply Division-I, PHE Dte. [TSM/019643] | AE SWSD-I | JE-1 | ORD/000711/2022-2023 | 3536/SWD-I | 20/03/2023 | 19/05/2023 | M/S J. ENTERPRISE | 34.14 | 14.76 | 43.24 | 55
22 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Proposed ground water based ASUTI I/II & CHATTA GP piped water supply scheme to accommodate FHTC in THAKURPUKUR MAHESHTALA block under South 24 parganas W/S division-I, South 24 parganas district | SM/15660 | Augmentation | Hiring of 01 (one) no. diesel driven Non-Air conditioned Motor Cab having BS-III & above category (Luxury Ambassador/ Indica/ Swift Dezire Car) with driver for official use of the Assistant Engineers, South 24-Pgns. W/S Sub-Division-I, under South 24-Pgns, W/S Divn-I, P.H.E. Dte. (w.e.f. 01/06/2023 to 30/11/2023) | AE SWSD-I |  | ORD/000179/2023-2024 | 780/SWD-I | 31/05/2023 | 30/11/2023 | AMARI BHADRA | 0.87 | 1.52 | 174.84 | 40
23 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Proposed ground water based ASUTI I/II & CHATTA GP piped water supply scheme to accommodate FHTC in THAKURPUKUR MAHESHTALA block under South 24 parganas W/S division-I, South 24 parganas district | SM/15660 | Augmentation | Hiring of 01 (one) no. diesel driven Non-Air conditioner Motor Cab having BS-III & above category (Luxury Ambassador / Indica / Swift Dezire Car) with driver for official use of the Assistant Engineer, Sub-Division-I under South 24-Pgns. W/S Division-I, PHE Dte.[w.e.f. 16/12/2023 to 12/06/2024] [Vehicle No- WB-23D-8048] | AE SWSD-I |  | ORD/000761/2023-2024 | 3246/SWD-I | 15/12/2023 | 12/06/2024 | SAROJ KUMAR SINGH | 0.86 | 2.25 | 263.73 | 50
24 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Proposed ground water based ASUTI I/II & CHATTA GP piped water supply scheme to accommodate FHTC in THAKURPUKUR MAHESHTALA block under South 24 parganas W/S division-I, South 24 parganas district | SM/15660 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1,2 & 3 for Augmentation of Asuti I/II & Chatta GP water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Thakurpukur Maheshtala] | Assistant Engineer -II | Junior Engineer | ORD/000612/2022-2023 | 771/SMD | 16/03/2023 | 14/06/2023 | CINZANO | 39.14 | 37.47 | 95.73 | 100
25 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Proposed ground water based ASUTI I/II & CHATTA GP piped water supply scheme to accommodate FHTC in THAKURPUKUR MAHESHTALA block under South 24 parganas W/S division-I, South 24 parganas district | SM/15660 | Augmentation | Sinking of 02 (Three) nos. Rig bored 300mm x 200mm dia. & 300 mtr. deep Tube-well having 66 mtr. housing pipe by Rotary method for ASUTI- I & II and CHATTA PWSS to accommodate FHTC in THAKURPUKUR - MAHESHTALA block under South 24-Parganas W/S Division-I, P.H.E. Dte. within South 24 Parganas district. (PART-II) [TSM/019643] | AE SWSD-I |  | ORD/000635/2022-2023 | 3259/SWD-I | 02/03/2023 | 01/04/2023 | PADMA ENGINEERING CO. | 43.15 | 38.31 | 88.78 | 100
26 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Proposed ground water based ASUTI I/II & CHATTA GP piped water supply scheme to accommodate FHTC in THAKURPUKUR MAHESHTALA block under South 24 parganas W/S division-I, South 24 parganas district | SM/15660 | Augmentation | Additional work for sinking of Rig bored 300 mm x 200 mm dia. & 300 mtr. deep Tube well to achieve 66 mtr. housing pipe by Rotary Method for ASUTI-I/II & CHATTA PWSS of ThakurpukurMaheshtala Block for Sonamukhi- Hrishnanagar (Khatian No.- 2922, Plot No.- 4350) under South 24-Parganas W/S Division- I, P.H.E. Dte. [TSM/019643] | AE SWSD-I |  | ORD/000694/2022-2023 | 3497/SWD-I | 16/03/2023 | 31/03/2023 | M/S. S.S. ENTERPRISE | 2.2 | 2.14 | 96.98 | 100
27 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Proposed ground water based ASUTI I/II & CHATTA GP piped water supply scheme to accommodate FHTC in THAKURPUKUR MAHESHTALA block under South 24 parganas W/S division-I, South 24 parganas district | SM/15660 | Augmentation | Balance Concrete for Over Head Reservoir of capacity 1500 cum at Zone-I of Asuti-I/II & Chata Water Supply Scheme under South 24-Pgns. Water Supply Division-I, PHE Dte. (SM/15660) | AE SWSD-I | JE-2 | ORD/000441/2023-2024 | 2097/SWD-I | 30/08/2023 | 29/09/2023 | M/S. S.S. ENTERPRISE | 4.02 | 4.02 | 99.99 | 100
28 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Proposed ground water based ASUTI I/II & CHATTA GP piped water supply scheme to accommodate FHTC in THAKURPUKUR MAHESHTALA block under South 24 parganas W/S division-I, South 24 parganas district | SM/15660 | Augmentation | Sinking of 03 (Three) nos. Rig bored 300mm x 200mm dia. & 300 mtr. deep Tubewell having 66 mtr. housing pipe by Rotary method for ASUTI- I & II and CHATTA PWSS to accomodate FHTC in THAKURPUKUR - MAHESHTALA block under South 24-Parganas W/S Division-I, P.H.E. Dte. within South 24 Parganas district. (PART-I) [TSM/019643] [2nd call] | AE SWSD-I |  | ORD/000120/2023-2024 | 532/SWD-I | 11/05/2023 | 10/06/2023 | PADMA ENGINEERING CO. | 64.72 | 61.67 | 95.28 | 100
29 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Proposed ground water based ASUTI I/II & CHATTA GP piped water supply scheme to accommodate FHTC in THAKURPUKUR MAHESHTALA block under South 24 parganas W/S division-I, South 24 parganas district | SM/15660 | Augmentation | Providing FHTC for ground water based ASUTI I & II and CHATTA GP PWSS in Thakurpukur Maheshtala Block under South 24 Parganas W/S Division-I, PHE, Dte. [TSM/019643] | AE SWSD-I | JE-2 | ORD/000660/2022-2023 | 3376/SWD-I | 10/03/2023 | 09/05/2023 | STAR ENTERPRISE | 17.94 | 7.98 | 44.47 | 40
30 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Proposed ground water based ASUTI I/II & CHATTA GP piped water supply scheme to accommodate FHTC in THAKURPUKUR MAHESHTALA block under South 24 parganas W/S division-I, South 24 parganas district | SM/15660 | Augmentation | Additional work for sinking of Rig bored 300 mm x 200 mm dia. & 300 mtr. deep Tube well to achieve 66 mtr. housing pipe by Rotary Method for ASUTI-I/II & CHATTA PWSS of ThakurpukurMaheshtala Block for Sonamukhi- Hrishnanagar (Khatian No.- 1, Plot No.- 22) under South 24-Parganas W/S Division- I, P.H.E. Dte. [TSM/019643] | AE SWSD-I |  | ORD/000692/2022-2023 | 3495/SWD-I | 16/03/2023 | 31/03/2023 | M/S. S.S. ENTERPRISE | 2.2 | 2.11 | 95.97 | 100
31 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Proposed ground water based ASUTI I/II & CHATTA GP piped water supply scheme to accommodate FHTC in THAKURPUKUR MAHESHTALA block under South 24 parganas W/S division-I, South 24 parganas district | SM/15660 | Augmentation | Additional work for sinking of Rig bored 300 mm x 200 mm dia. & 300 mtr. deep Tube well to achieve 66 mtr. housing pipe by Rotary Method for ASUTI-I/II & CHATTA PWSS of ThakurpukurMaheshtala Block for Sonamukhi- Hrishnanagar (Khatian No.- 1, Plot No.- 510) under South 24-Parganas W/S Division- I, P.H.E. Dte. [TSM/019643] | AE SWSD-I |  | ORD/000693/2022-2023 | 3496/SWD-I | 16/03/2023 | 31/03/2023 | M/S. S.S. ENTERPRISE | 2.2 | 2.14 | 96.98 | 100
32 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Proposed ground water based ASUTI I/II & CHATTA GP piped water supply scheme to accommodate FHTC in THAKURPUKUR MAHESHTALA block under South 24 parganas W/S division-I, South 24 parganas district | SM/15660 | Augmentation | Repair & Retrofitting of Civil Structures at Chatta Head Work Site with allied Works at ZONE - I of Asuti-I/II & Chatta under Proposed Ground Water Based Asuti-I/II & Chatta GP Piped Water Supply Scheme to accomodates FHTC in Thakurpukur-Maheshtala Block under South 24 Pgs Water Supply Divn.-I . PHE Dte. (SM/15660) | AE SWSD-I | JE-2 | ORD/000677/2023-2024 | 3094/SWD-I | 06/12/2023 | 01/01/2026 | M/S. S.S. ENTERPRISE (NODAKHALI) | 19.5 | 5.89 | 30.2 | 60
33 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Proposed ground water based ASUTI I/II & CHATTA GP piped water supply scheme to accommodate FHTC in THAKURPUKUR MAHESHTALA block under South 24 parganas W/S division-I, South 24 parganas district | SM/15660 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000284/2023-2024 | 2007/SWD-I | 28/08/2023 | 28/08/2023 | Resource Division | 3.73 | 0 | 0 | 0
34 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Proposed ground water based ASUTI I/II & CHATTA GP piped water supply scheme to accommodate FHTC in THAKURPUKUR MAHESHTALA block under South 24 parganas W/S division-I, South 24 parganas district | SM/15660 | Augmentation | Bill for Security Deposit for New Service Connection |  |  | BILL/01263/2022-2023 | BP-2022-23-438 | 10/03/2023 | 10/03/2023 | CESC LTD | 4.35 | 0 | 0 | 0
35 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Proposed ground water based ASUTI I/II & CHATTA GP piped water supply scheme to accommodate FHTC in THAKURPUKUR MAHESHTALA block under South 24 parganas W/S division-I, South 24 parganas district | SM/15660 | Augmentation | Payment of electricity bill for new service connection under SMD, PHE Dte. |  |  | BILL/04224/2023-2024 | BP-2023-24-433 | 27/12/2023 | 27/12/2023 | CESC LTD | 4.54 | 0 | 0 | 0
36 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Proposed ground water based ASUTI I/II & CHATTA GP piped water supply scheme to accommodate FHTC in THAKURPUKUR MAHESHTALA block under South 24 parganas W/S division-I, South 24 parganas district | SM/15660 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 12 & 13 for Augmentation of Asuti I/II & Chatta GP water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Thakurpukur Maheshtala] | Assistant Engineer -II |  | ORD/001546/2023-2024 | 674/SMD | 01/02/2024 | 01/05/2024 | DEBJYOTI BASU | 25.41 | 0 | 0 | 0
37 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Proposed ground water based ASUTI I/II & CHATTA GP piped water supply scheme to accommodate FHTC in THAKURPUKUR MAHESHTALA block under South 24 parganas W/S division-I, South 24 parganas district | SM/15660 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 10 & 11 for Augmentation of Asuti I/II & Chatta GP water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Thakurpukur Maheshtala] | Assistant Engineer -II | Junior Engineer | ORD/001544/2023-2024 | 675/SMD | 01/02/2024 | 01/05/2024 | P.K. ENGINEERING | 25.4 | 11.87 | 46.72 | 40
38 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Proposed ground water based ASUTI I/II & CHATTA GP piped water supply scheme to accommodate FHTC in THAKURPUKUR MAHESHTALA block under South 24 parganas W/S division-I, South 24 parganas district | SM/15660 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 14 for Augmentation of Asuti I/II & Chatta GP water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Thakurpukur Maheshtala] | Assistant Engineer -II |  | ORD/001482/2023-2024 | 687/SMD | 01/02/2024 | 01/05/2024 | SHIVAM ENTERPRISE | 12.58 | 0 | 0 | 0
39 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Proposed ground water based ASUTI I/II & CHATTA GP piped water supply scheme to accommodate FHTC in THAKURPUKUR MAHESHTALA block under South 24 parganas W/S division-I, South 24 parganas district | SM/15660 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 6 & 7 for Augmentation of Asuti I/II & Chatta GP water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Thakurpukur Maheshtala] | Assistant Engineer -II | Junior Engineer | ORD/001542/2023-2024 | 676/SMD | 01/02/2024 | 01/01/2026 | P.K. ENTERPRISE | 25.45 | 0 | 0 | 40
40 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Proposed ground water based ASUTI I/II & CHATTA GP piped water supply scheme to accommodate FHTC in THAKURPUKUR MAHESHTALA block under South 24 parganas W/S division-I, South 24 parganas district | SM/15660 | Augmentation | Interconnections of 04 (Four) nos. pumps for Asuti-I/II & Chatta GP PWSS to accommodate FHTC in Thakurpukur Maheshtala Block under South 24-Pgns. Water Supply Division-I, PHE Dte. (SM/15660) |  |  | ORD/000393/2024-2025 | 3641/SWD-I | 20/08/2024 | 19/09/2024 | M/S. S.S. ENTERPRISE (NODAKHALI) | 22.07 | 0 | 0 | 0
41 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Proposed ground water based ASUTI I/II & CHATTA GP piped water supply scheme to accommodate FHTC in THAKURPUKUR MAHESHTALA block under South 24 parganas W/S division-I, South 24 parganas district | SM/15660 | Augmentation | Development and yield testing of (4 Nos) rig ground bored 300 mm x 200 mm dia & 300 mtr. deep tube-well for Asuti-I, II and Chatta GP PWSS at Rameswarpur, Chatta Head work site, Ganney Gangadharpur and Sarsuna in the Arsenic afeected areas of South 24-Parganas district under South 24-Parganas W/S Division-I, PHE Dte. (SM/15660) |  |  | ORD/000759/2024-2025 | 4680/SWD-I | 18/11/2024 | 18/12/2024 | PADMA ENGINEERING CO. | 2.71 | 0 | 0 | 0
42 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Proposed ground water based ASUTI I/II & CHATTA GP piped water supply scheme to accommodate FHTC in THAKURPUKUR MAHESHTALA block under South 24 parganas W/S division-I, South 24 parganas district | SM/15660 | Augmentation | Construction of 04 (four) nos. Switching cum control room at Kalikapur, Kalagachia, Khalpar and near Ashuti-I Panchayat office for ASUTI I/II & CHATTA GP Piped Water Supply Scheme to accommondate FHTC in THAKURPUKUR MAHESHTALA Block under South 24 Pngs Divn-I, PHE Dte, South 24 Parganas District. (SM/15660) | AE SWSD-I | JE-1 | ORD/000879/2024-2025 | 4977/SWD-I | 05/12/2024 | 03/06/2025 | MOTIONMASS TECHNO OPC PVT LTD | 17.66 | 0 | 0 | 50
43 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Proposed ground water based ASUTI I/II & CHATTA GP piped water supply scheme to accommodate FHTC in THAKURPUKUR MAHESHTALA block under South 24 parganas W/S division-I, South 24 parganas district | SM/15660 | Augmentation | Continuation order for the work of Hiring of 01 (one) no. diesel driven Non-Air conditioner Motor Cab having BS-III & above category (Luxury Ambassador / Indica / Swift Dezire Car) with driver for official use of the Assistant Engineer, Sub-Division-I under South 24-Pgns. W/S Division-I, PHE Dte.[w.e.f. 13/06/2024 to 30/11/2024] [Vehicle No- WB-23D-8048] | AE SWSD-I,Assistant Engineer | JE-2,JE1 | ORD/000276/2024-2025 | 2683/SWD-I | 07/06/2024 | 25/11/2024 | SAROJ KUMAR SINGH | 0.81 | 2.06 | 253.77 | 0
44 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Proposed ground water based ASUTI I/II & CHATTA GP piped water supply scheme to accommodate FHTC in THAKURPUKUR MAHESHTALA block under South 24 parganas W/S division-I, South 24 parganas district | SM/15660 | Augmentation | Supply and installation of LED Glow sign board with allied works at PH No-3 under Augmentation of Asuti-I/II & Chatta GP Water Supply Scheme, under South 24-Pgs Mechanical Division,PHE Dte (Block: Thakurpukur Maheshtala) (SM/15660) | Assistant Engineer -II | Junior Engineer | ORD/002368/2023-2024 | 148-AE-II-SMD | 07/02/2024 | 22/02/2024 | MAA TARA ENTERPRISE | 0.75 | 0 | 0 | 0
45 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Proposed ground water based ASUTI I/II & CHATTA GP piped water supply scheme to accommodate FHTC in THAKURPUKUR MAHESHTALA block under South 24 parganas W/S division-I, South 24 parganas district | SM/15660 | Augmentation | Laying of Balance UPVC pielines within Asuti-I/II GP and extended areas under Asuti-I/II & Chatta GP PWSS to accommodate FHTC in Thakur pukur Mahestala Block under South 24 Pgns W/S Div I PHED (SM/15660) | AE SWSD-I | JE-2 | ORD/000698/2024-2025 | 4500/SWD-I | 30/10/2024 | 31/03/2025 | SUPRITI ENTERPRISE | 94.83 | 0 | 0 | 40
46 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Proposed ground water based ASUTI I/II & CHATTA GP piped water supply scheme to accommodate FHTC in THAKURPUKUR MAHESHTALA block under South 24 parganas W/S division-I, South 24 parganas district | SM/15660 | Augmentation | Renovation of external illumination arrangement with other allied works at P.H. No. - 5 of Augmentation of Asuti-I/II & Chatta GP Water Supply Scheme (Mahisgot), under South 24 Pgs Mechanical Division, PHE Dte. (Block : Bishnupur-I)(SM/15660) | Assistant Engineer -II | Junior Engineer | ORD/000726/2024-2025 | 1033/AE-II/SMD | 13/08/2024 | 28/08/2024 | SUDIP PRADHAN | 0.78 | 0 | 0 | 100
47 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Proposed ground water based ASUTI I/II & CHATTA GP piped water supply scheme to accommodate FHTC in THAKURPUKUR MAHESHTALA block under South 24 parganas W/S division-I, South 24 parganas district | SM/15660 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 8 & 9 for Augmentation of Asuti I/II & Chatta GP water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Thakurpukur Maheshtala] | Assistant Engineer -II | Junior Engineer | ORD/001491/2023-2024 | 685/SMD | 01/02/2024 | 30/05/2025 | DIPA CHHETRI | 25.44 | 3.15 | 12.37 | 50
48 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Proposed ground water based ASUTI I/II & CHATTA GP piped water supply scheme to accommodate FHTC in THAKURPUKUR MAHESHTALA block under South 24 parganas W/S division-I, South 24 parganas district | SM/15660 | Augmentation | Continuation order for the work of Hiring of 01 (one) no. diesel driven Non-Air conditioner Motor Cab having BS-III & above category (Luxury Ambassador / Indica / Swift Dezire Car) with driver for official use of the Assistant Engineer, Sub-Division-I under South 24-Pgns. W/S Division-I, PHE Dte.[w.e.f. 01/12/2024 to 31/05/2025] [Vehicle NoWB-23D-8048] | Assistant Engineer | JE1 | ORD/001062/2024-2025 | 4879/SWD-I | 29/11/2024 | 30/05/2025 | SAROJ KUMAR SINGH | 0.86 | 1.84 | 213.17 | 50
49 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Proposed ground water based ASUTI I/II & CHATTA GP piped water supply scheme to accommodate FHTC in THAKURPUKUR MAHESHTALA block under South 24 parganas W/S division-I, South 24 parganas district | SM/15660 | Augmentation | Road Restoration of Different pathways excavates for laying of pipeline underground water based ASUTI I/II & Chatta GP PWSS to accommodate FHTC in Thakur Pukur Maheshtala Block under South 24 Parganas W/S Division -I P.H.E. Dte. (SM/ 15660) | AE SWSD-I | JE-1 | ORD/000729/2024-2025 | 4616/SWD-I | 13/11/2024 | 01/05/2025 | J.D.J ENTERPRISE (A UNIT OF J D J TRADERS PVT. LTD.) | 135.92 | 0 | 0 | 45
50 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Proposed ground water based ASUTI I/II & CHATTA GP piped water supply scheme to accommodate FHTC in THAKURPUKUR MAHESHTALA block under South 24 parganas W/S division-I, South 24 parganas district | SM/15660 | Augmentation | Laying of Balance UPVC pielines within Chatta GP and extended areas under Asuti-I/II & Chatta GP PWSS to accommodate FHTC in Thakurpukur-Mahestala Block under South 24-Pgns. W/S Division-I, PHE Dte. (SM/15660) | AE SWSD-I | JE-1 | ORD/000728/2024-2025 | 4615/SWD-I | 13/11/2024 | 13/03/2025 | J.D.J ENTERPRISE (A UNIT OF J D J TRADERS PVT. LTD.) | 174.51 | 0 | 0 | 45
51 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Proposed ground water based ASUTI I/II & CHATTA GP piped water supply scheme to accommodate FHTC in THAKURPUKUR MAHESHTALA block under South 24 parganas W/S division-I, South 24 parganas district | SM/15660 | Augmentation | Upgradation of external illumination arrangement with other allied works at P.H. No. - 8 under Augmentation of Asuti-I/II & Chatta GP Water Supply Scheme (Chalkipara), under South 24 Pgs Mechanical Division, PHE Dte. (Block : Thakurpukur Maheshtala) (SM/15660) | Assistant Engineer -II | Junior Engineer | ORD/001822/2024-2025 | 1377-AE-II-SMD | 26/11/2024 | 11/12/2024 | STANDARD ENGINEERING | 0.76 | 0 | 0 | 0
52 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Proposed ground water based ASUTI I/II & CHATTA GP piped water supply scheme to accommodate FHTC in THAKURPUKUR MAHESHTALA block under South 24 parganas W/S division-I, South 24 parganas district | SM/15660 | Augmentation | Supply, delivery & installation of additional electrical accessories at PH No.- 10 of Augmentation of Asuti - I/II & Chatta GP Water supply scheme (Dilkhusmath) under JJM under South 24 Pgs. Mechanical Division, PHE Dte. (Block : Thakurpukur Maheshtala) [SM/15660] | Assistant Engineer -II | Junior Engineer | ORD/002560/2024-2025 | 997-AE-II-SMD | 06/08/2024 | 21/08/2024 | P.K. ENGINEERING | 0.6 | 0 | 0 | 0
53 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Proposed ground water based ASUTI I/II & CHATTA GP piped water supply scheme to accommodate FHTC in THAKURPUKUR MAHESHTALA block under South 24 parganas W/S division-I, South 24 parganas district | SM/15660 | Augmentation | Supply, delivery & installation of additional electrical accessories at PH No.- 7 of Augmentation of Asuti - I/II & Chatta GP Water supply scheme (Rameswarpur) under JJM under South 24 Pgs. Mechanical Division, PHE Dte. (Block : Thakurpukur Maheshtala) [SM/15660] | Assistant Engineer -II | Junior Engineer | ORD/002568/2024-2025 | 1526-AE-II-SMD | 19/12/2024 | 03/01/2025 | P.K. ENTERPRISE | 0.7 | 0 | 0 | 0
54 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Proposed ground water based ASUTI I/II & CHATTA GP piped water supply scheme to accommodate FHTC in THAKURPUKUR MAHESHTALA block under South 24 parganas W/S division-I, South 24 parganas district | SM/15660 | Augmentation | Land Development of Chatta Kalikapur Pump House Site to facilitate the boring of Tubewell under Asuti-I / Asuti-II & Chatta W/S Scheme under South 24 Pgns W/S Division-I , PHE Dte. (SM/15660) |  |  | ORD/000718/2023-2024 | 361/SWD-I | 16/01/2024 | 15/02/2024 | MS POUSALI ENTERPRISE | 4.83 | 4.8 | 99.42 | 100
55 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Proposed ground water based ASUTI I/II & CHATTA GP piped water supply scheme to accommodate FHTC in THAKURPUKUR MAHESHTALA block under South 24 parganas W/S division-I, South 24 parganas district | SM/15660 | Augmentation | Modification of foundation of awarded of Over Head Reservoir of capacity 1250 cum at ZONE - II of Asuti-I/II & Chata Piped Water Supply Scheme to accommodate FHTC in Thakurpukur-Maheshtala block under South 24 Pgs Water Supply Divn.-I . PHE Dte. (SM/15660) | AE SWSD-I | JE-1 | ORD/000750/2023-2024 | 552/SWD-I | 31/01/2024 | 20/02/2024 | J.D.J ENTERPRISE (A UNIT OF J D J TRADERS PVT. LTD.) | 11.88 | 11.8 | 99.33 | 100
56 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Proposed ground water based ASUTI I/II & CHATTA GP piped water supply scheme to accommodate FHTC in THAKURPUKUR MAHESHTALA block under South 24 parganas W/S division-I, South 24 parganas district | SM/15660 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 4 & 5 for Augmentation of Asuti I/II & Chatta GP water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Thakurpukur Maheshtala] | Assistant Engineer -II | Junior Engineer | ORD/001476/2023-2024 | 683/SMD | 01/02/2024 | 01/05/2024 | KARUNAMOY ENGINEERING | 25.15 | 24.64 | 97.98 | 100
57 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Proposed ground water based ASUTI I/II & CHATTA GP piped water supply scheme to accommodate FHTC in THAKURPUKUR MAHESHTALA block under South 24 parganas W/S division-I, South 24 parganas district | SM/15660 | Augmentation | Upgradation of external illumination arrangement with other allied works at PH No-1 under Augmentation of Asuti-I/II & Chatta GP Water Supply Scheme, under South 24-Pgs Mechanical Division,PHE Dte (Block: Thakurpukur Maheshtala) (SM/15660) | Assistant Engineer -II | Junior Engineer | ORD/002102/2023-2024 | 146-AE-II-SMD | 07/02/2024 | 22/02/2024 | M/S POUSALI ENTERPRISE | 0.75 | 0.75 | 100 | 100
58 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Proposed ground water based ASUTI I/II & CHATTA GP piped water supply scheme to accommodate FHTC in THAKURPUKUR MAHESHTALA block under South 24 parganas W/S division-I, South 24 parganas district | SM/15660 | Augmentation | Miscellaneous works in connection with the improvement of external illumination arrangement with other allied works at PH No-2 under Augmentation of Asuti-I/II & Chatta GP Water Supply Scheme, under South 24-Pgs Mechanical Division,PHE Dte (Block: Thakurpukur Maheshtala) (SM/15660) | Assistant Engineer -II | Junior Engineer | ORD/002146/2023-2024 | 147-AE-II-SMD | 07/02/2024 | 22/02/2024 | ROY & BISWAS ENGG. CO. | 0.75 | 0 | 0 | 100
59 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Proposed ground water based ASUTI I/II & CHATTA GP piped water supply scheme to accommodate FHTC in THAKURPUKUR MAHESHTALA block under South 24 parganas W/S division-I, South 24 parganas district | SM/15660 | Augmentation | Road restoration from Malangermath to Neemtala damaged due to pipeline under Asuti and Asuti-II Water Supply Scheme under South 24-Pgns. Water Supply Division-I, PHE Dte. (SM/15660) | AE SWSD-I | JE-1 | ORD/000293/2024-2025 | 3132/SWD-I | 10/07/2024 | 24/08/2024 | SADHURHAT CO OP LABOUR CONTRACT AND CONSTRUCTION SOCIETY LTD. | 21.38 | 21.38 | 99.98 | 100
60 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Proposed ground water based ASUTI I/II & CHATTA GP piped water supply scheme to accommodate FHTC in THAKURPUKUR MAHESHTALA block under South 24 parganas W/S division-I, South 24 parganas district | SM/15660 | Augmentation | Laying of Pipeline in uncovered areas of Chatta Kalikapur Mouza under Asuti I/ Asuti II and Chata GP Piped Water Supply Scheme to accommodate FHTC in Thakurpukur Mahestala Block under South 24 Pgns. W/S Division-I, PHE Dte., South 24 Parganas Districts (SM/15660) | AE SWSD-I | JE-2 | ORD/000511/2024-2025 | 3979/SWD-I | 11/09/2024 | 11/10/2024 | M/S. S.S. ENTERPRISE (NODAKHALI) | 23.86 | 0 | 0 | 80
61 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Proposed ground water based ASUTI I/II & CHATTA GP piped water supply scheme to accommodate FHTC in THAKURPUKUR MAHESHTALA block under South 24 parganas W/S division-I, South 24 parganas district | SM/15660 | Augmentation | Land development of tube-well sites at Kalagachia Chalkipara & Sarsuna under Asuti-I/II & Chatta GP PWSS to accommodate FHTC in Thakurpukur-Maheshtala Block under South 24-Pgns. W/S Division-I, PHE Dte. (SM/15660) | AE SWSD-I | JE-1 | ORD/000767/2024-2025 | 4688/SWD-I | 18/11/2024 | 18/12/2024 | K.P CONSTRUCTION | 8.29 | 8.21 | 99 | 100
62 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Proposed ground water based ASUTI I/II & CHATTA GP piped water supply scheme to accommodate FHTC in THAKURPUKUR MAHESHTALA block under South 24 parganas W/S division-I, South 24 parganas district | SM/15660 | Augmentation | Temporary road repairing at Chata Bazar Moshgot Road under Asuti I / Asuti II and Chatta W/S Scheme under South 24-Pgns, W/S Division-I, P.H.E. Dte. [SM/15660] | AE SWSD-I | JE-2 | ORD/000865/2024-2025 | 4923/SWD-I | 03/12/2024 | 31/12/2025 | M/S. S.S. ENTERPRISE (NODAKHALI) | 60.96 | 44.56 | 73.1 | 60
63 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Proposed ground water based ASUTI I/II & CHATTA GP piped water supply scheme to accommodate FHTC in THAKURPUKUR MAHESHTALA block under South 24 parganas W/S division-I, South 24 parganas district | SM/15660 | Augmentation | Miscellaneous upgradation works regarding incorporation of LED Board, improvement of external illumination arrangement etc. at P.H. No. - 4 of Augmentation of Asuti-I/II & Chatta GP Water Supply Scheme (Sonamukhi Krishnanagar), under South 24 Pgs Mechanical Division, PHE Dte. (Block : Thakurpukur Maheshtala)(SM/15660) | Assistant Engineer -II | Junior Engineer | ORD/000798/2024-2025 | 1032-AE-II-SMD | 13/08/2024 | 28/08/2024 | DYNATECH SOLUTION | 0.78 | 0.64 | 82.11 | 100
64 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Proposed ground water based ASUTI I/II & CHATTA GP piped water supply scheme to accommodate FHTC in THAKURPUKUR MAHESHTALA block under South 24 parganas W/S division-I, South 24 parganas district | SM/15660 | Augmentation | Supply, delivery & installation of additional electrical accessories at PH No.- 8 of Augmentation of Asuti - I/II & Chatta GP Water supply scheme (Chalkipara) under JJM under South 24 Pgs. Mechanical Division, PHE Dte. (Block : Thakurpukur Maheshtala) [SM/15660] | Assistant Engineer -II | Junior Engineer | ORD/001545/2024-2025 | 1319-AE-II-SMD | 30/10/2024 | 14/11/2024 | DIPA CHHETRI | 0.9 | 0 | 0 | 100
65 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Proposed ground water based ASUTI I/II & CHATTA GP piped water supply scheme to accommodate FHTC in THAKURPUKUR MAHESHTALA block under South 24 parganas W/S division-I, South 24 parganas district | SM/15660 | Augmentation | Supply & delivery of additional materials for PH No-4 & 5 of Augmentation of Ashuti-I/II & Chatta GP water supply scheme under JJM under South 24-Pgs Mechanical Division,PHE Dte.(Block-Thakurpukur Maheshtala) [SM/15660] | Assistant Engineer -II | Junior Engineer | ORD/002865/2023-2024 | 287-AE-II-SMD | 15/03/2024 | 30/03/2024 | KARUNAMOY ENGINEERING | 0.57 | 0 | 0 | 100
66 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Proposed ground water based ASUTI I/II & CHATTA GP piped water supply scheme to accommodate FHTC in THAKURPUKUR MAHESHTALA block under South 24 parganas W/S division-I, South 24 parganas district | SM/15660 | Augmentation | Procurement of additional column pipes and its allied materials for PH No.- 8 of Augmentation of Asuti - I/II & Chatta GP Water supply scheme (Chalkipara) under JJM under South 24 Pgs. Mechanical Division, PHE Dte. (Block : Thakurpukur Maheshtala) [SM/15660] | Assistant Engineer -II | Junior Engineer | ORD/001546/2024-2025 | 1320-AE-II-SMD | 30/10/2024 | 14/11/2024 | DIPA CHHETRI | 0.29 | 0 | 0 | 100
67 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Proposed ground water based ASUTI I/II & CHATTA GP piped water supply scheme to accommodate FHTC in THAKURPUKUR MAHESHTALA block under South 24 parganas W/S division-I, South 24 parganas district | SM/15660 | Augmentation | Payment of quotation for effecting new service connection at Khanberia under Asuti-I&II and Chatta GP JL No. 32, Khatian No. 1268 Application No. 1007832957 Reference ID - 106623121 |  |  | BILL/00532/2024-2025 | BP-2024-25-130 | 24/06/2024 | 24/06/2024 | WBSEDCL | 14.33 | 0 | 0 | 0
68 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Proposed ground water based ASUTI I/II & CHATTA GP piped water supply scheme to accommodate FHTC in THAKURPUKUR MAHESHTALA block under South 24 parganas W/S division-I, South 24 parganas district | SM/15660 | Augmentation | Payment of electricity bill for new service connection under SMD, PHE Dte. |  |  | BILL/04933/2023-2024 | BP-2023-24-541 | 27/02/2024 | 27/02/2024 | CESC LTD | 2.44 | 0 | 0 | 0
69 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Proposed ground water based ASUTI I/II & CHATTA GP piped water supply scheme to accommodate FHTC in THAKURPUKUR MAHESHTALA block under South 24 parganas W/S division-I, South 24 parganas district | SM/15660 | Augmentation | Payment of electricity bill for new service connection under SMD, PHE Dte. |  |  | BILL/04687/2023-2024 | BP-2023-24-506 | 12/02/2024 | 12/02/2024 | WBSEDCL | 10.06 | 0 | 0 | 0
70 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Proposed ground water based ASUTI I/II & CHATTA GP piped water supply scheme to accommodate FHTC in THAKURPUKUR MAHESHTALA block under South 24 parganas W/S division-I, South 24 parganas district | SM/15660 | Augmentation | Payment of electricity bill for new service connection under SMD, PHE Dte. |  |  | BILL/04926/2023-2024 | BP-2023-24-531 | 26/02/2024 | 26/02/2024 | CESC LTD | 2.34 | 0 | 0 | 0
71 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Proposed ground water based ASUTI I/II & CHATTA GP piped water supply scheme to accommodate FHTC in THAKURPUKUR MAHESHTALA block under South 24 parganas W/S division-I, South 24 parganas district | SM/15660 | Augmentation | Supply and Installation of DI specials with allied works under Asuti-I/II & Chatta GP PWSS to accommodate FHTC in Thakurpukur Maheshtala Block under South 24 Pgns W/S Division-I, PHE Dte, South 24 Pgns Dist. (SM/15660) | AE SWSD-I | JE-1 | ORD/000021/2025-2026 | 973/SWD-I | 09/04/2025 | 09/05/2025 | J.D.J ENTERPRISE (A UNIT OF J D J TRADERS PVT. LTD.) | 18.93 | 0 | 0 | 75
72 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Proposed ground water based ASUTI I/II & CHATTA GP piped water supply scheme to accommodate FHTC in THAKURPUKUR MAHESHTALA block under South 24 parganas W/S division-I, South 24 parganas district | SM/15660 | Augmentation | Restoration of Road (Sonamukhi Chowmatha More, Das Para road, Nandalal Chatterjee road Shibrampur Main road) damaged due to laying of 150 & 200mm dia DI Pipe of KMC Bagpota Road under Asuti I, Asuti - II and Chatta Water Supply scheme of South 24 Pargana W/S Division-I, P.H.E Dte. (SM/15660) | AE SWSD-I | JE-1 | ORD/000091/2025-2026 | 1766/SWD-I | 02/07/2025 | 10/08/2026 | GAYATRI CONSTRUCTION | 33.77 | 0 | 0 | 100
73 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Proposed ground water based ASUTI I/II & CHATTA GP piped water supply scheme to accommodate FHTC in THAKURPUKUR MAHESHTALA block under South 24 parganas W/S division-I, South 24 parganas district | SM/15660 | Augmentation | Balance pipeline laying, road repair with allied works under proposed ground water based Asuti I Asuti II & Chatta GP PWSS to accommodate FHTC in Thakurpukur-Maheshtala Block under SWD - I, P.H.E. Dte District South 24 Parganas. (SM/15660) | AE SWSD-I | JE-2 | ORD/000131/2025-2026 | 2096/SWD-I | 14/08/2025 | 30/05/2026 | M/S. S.S. ENTERPRISE (NODAKHALI) | 139.27 | 0 | 0 | 20
74 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Proposed ground water based ASUTI I/II & CHATTA GP piped water supply scheme to accommodate FHTC in THAKURPUKUR MAHESHTALA block under South 24 parganas W/S division-I, South 24 parganas district | SM/15660 | Augmentation | Interconnection pipeline for 04 nos. tube-well with rising main under Asuti-I/II & Chatta GP PWSS to accommodate FHTC in Thakurpukur Maheshtala Block under South 24-Pgns. W/S Division-I, PHE Dte. (SM/15660) (2nd call) | AE SWSD-I | JE-1 | ORD/001144/2024-2025 | 314/SWD-I | 28/01/2025 | 27/02/2025 | SRIJON ENTERPRISE | 11.69 | 0 | 0 | 100
75 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Proposed ground water based ASUTI I/II & CHATTA GP piped water supply scheme to accommodate FHTC in THAKURPUKUR MAHESHTALA block under South 24 parganas W/S division-I, South 24 parganas district | SM/15660 | Augmentation | Negotiation of gaps in MS pipeline of different dia of rising main and distribution on the Mosh Got Chatta Bazar road with allied works for proposed ground water based Asuti-I/II & Chatta GP Piped Water Supply Scheme to accommodate FHTC in Thakurpukur Maheshtala Block under South 24-Parganas W/S Division-I, PHE Dte. (SM/15660) | AE SWSD-I | JE-2 | ORD/001126/2024-2025 | 189/SWD-I | 17/01/2025 | 16/02/2025 | SRIJON ENTERPRISE | 69.28 | 0 | 0 | 100
76 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Proposed ground water based ASUTI I/II & CHATTA GP piped water supply scheme to accommodate FHTC in THAKURPUKUR MAHESHTALA block under South 24 parganas W/S division-I, South 24 parganas district | SM/15660 | Augmentation | Supply, installation, trail run, commissioning of Full Bore Electromagnetic Flow Meter in connection to PWS Scheme of proposed ground water based ASUTI- I /II & CHATTA GP piped water supply scheme to accommodate FHTC in THAKURPUKUR MAHESHTALA block under South 24 Parganas W/S Division-I, PHE Dte., South 24-Parganas District. [SM/15660] | AE SWSD-I | JE-1 | ORD/001129/2024-2025 | 192/SWD-I | 17/01/2025 | 01/02/2025 | B.S. RUBBER INDUSTRIES | 4.77 | 0 | 0 | 100
77 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Proposed ground water based ASUTI I/II & CHATTA GP piped water supply scheme to accommodate FHTC in THAKURPUKUR MAHESHTALA block under South 24 parganas W/S division-I, South 24 parganas district | SM/15660 | Augmentation | Payment of Additional Quotation for new service connection at Augmentation of Asuti-I/II and Chatta GP PWSS, PH No- 9 (Khanberia) under Thakurpukur Maheshtala Block. Application No-1007832957 Reference ID-860341276 Memo No-BKT/PHE/QUOT Date-08-07-2025 |  |  | BILL/01778/2025-2026 |  | 20/08/2025 | 20/08/2025 | WBSEDCL | 9.62 | 0 | 0 | 0
Total | [13 empty] | 2817.51 | 1210.7 | 42.97