## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | JAGULGACHHI piped water supply scheme to accommodate FHTC in BHANGAR-I block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Under JJM | SM/15754 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000216/2023-2024 | 1007/SWD- I | 09/06/2023 | 09/06/2023 | Resource Division | 12.87 | 0 | 0 | 0
2 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | JAGULGACHHI piped water supply scheme to accommodate FHTC in BHANGAR-I block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Under JJM | SM/15754 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000046/2023-2024 | 287/SWD-I | 24/04/2023 | 24/04/2023 | Resource Division | 24.11 | 0 | 0 | 0
3 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | JAGULGACHHI piped water supply scheme to accommodate FHTC in BHANGAR-I block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Under JJM | SM/15754 | Augmentation | Construction of Boundary Wall and others allied works at HW & 2nd Tubewell site of JAGULGACHI Piped Water Supply Scheme to accommodate FHTC in Bhangar-I Block under South 24-Parganas, W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission. [SM/15754] |  |  | ORD/000750/2024-2025 | 4672/SWD-I | 18/11/2024 | 17/01/2025 | A.P POWER AND CONCRETE | 75.42 | 0 | 0 | 0
4 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | JAGULGACHHI piped water supply scheme to accommodate FHTC in BHANGAR-I block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Under JJM | SM/15754 | Augmentation | Quotation for new service(power) connection at Jagulgachi PH-1 water supply scheme under bhangar-I block Reference ID- 106492239, Application No-1007561863 |  |  | BILL/00566/2024-2025 | BP-2024-25-139 | 03/07/2024 | 03/07/2024 | WBSEDCL | 0.71 | 0 | 0 | 0
5 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | JAGULGACHHI piped water supply scheme to accommodate FHTC in BHANGAR-I block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Under JJM | SM/15754 | Augmentation | Bhangor Bodra Road from 0.00 kmp to 204kmp, Permanent restoration work, damaged due tp " Pipeline Laying of 250mm to 90mm dia HDPE Pipe Line along flank by PHE DEpartment " within Alipore Highway sub-Division under South 24 Parganas Highway Division in the district of South 24 Parganas. (SM/15754) |  |  | BILL/00641/2024-2025 | BP-2024-25-364 | 02/10/2024 | 02/10/2024 | EXECUTIVE ENGINEER, SOUTH 24 PGS HIGHWAY DIVISION PW (ROADS) DTE | 11.37 | 0 | 0 | 0
6 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | JAGULGACHHI piped water supply scheme to accommodate FHTC in BHANGAR-I block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Under JJM | SM/15754 | Augmentation | Laying Distribution System, Rising Main, Functional Household Tap Connection (FHTC) and construction of Pump House cum Chlorine Room (2 Nos.) for JAGULGACHI Piped Water Supply Scheme to accommodate FHTC in Bhangar-I Block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission. (No of FHTC = 2089) (TSM/018474) | AE HQ-I,AE HQ-II | JE RWS, Bhangar-II Block,JE-4 | ORD/000035/2023-2024 | 125/SWD-I | 12/04/2023 | 25/04/2025 | A P POWER AND CONCRETE | 279.5 | 0 | 0 | 10
7 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | JAGULGACHHI piped water supply scheme to accommodate FHTC in BHANGAR-I block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Under JJM | SM/15754 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1 & 2 of Jagulgachhi water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Bhangar-I] | Assistant Engineer | Junior Engineer | ORD/001516/2022-2023 | 896/SMD | 27/03/2023 | 25/06/2023 | GLACIER ENGINEERING CO. | 23.44 | 0 | 0 | 40
8 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | JAGULGACHHI piped water supply scheme to accommodate FHTC in BHANGAR-I block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Under JJM | SM/15754 | Augmentation | Sinking of 02 (Two) nos. Rig bored 250mm x 150mm dia. & 300 mtr. deepTubewell having 66 mtr. housing pipe by Rotary method for JAGULGACHI PWSS of BHANGAR-I block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division-I, P.H.E. Dte. [TSM/018474] | AE HQ-I | JE RWS, Bhangar-II Block,JE-4 | ORD/000639/2022-2023 | 3287/SWD-I | 03/03/2023 | 05/01/2024 | M/S MONDAL ENTERPRISE | 31.76 | 0 | 0 | 50
Total | [13 empty] | 459.18 | 0 | 0