## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based RAMNAGAR (ZONE-I) piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas dist | SM/15755 | Augmentation | Preparation and submission of Detailed Project Report of RAMNAGAR(I) Ground Water Based Piped Water Supply Scheme in BARUIPUR PURBA Assembly Constituency of BARUIPUR Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE BSD |  | ORD/000407/2021-2022 | 1945/SWD-I | 27/01/2022 | 26/02/2022 | ENVIROTECH SOLUTIONS | 2.76 | 2.69 | 97.48 | 0
2 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based RAMNAGAR (ZONE-I) piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas dist | SM/15755 | Augmentation | Construction of Boundary Wall, Chlorine Room along with Laying of Distribution System, Rising Main, Providing Functional Household Tap Connection (FHTC) for Augmentation of RAMNAGAR (PART-I) MOUZA Piped Water Supply Scheme of BARUIPUR Block for implementation of JJM under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. [No. of FHTC = 1885] [TSM/018210] | AE BSD | JE RWS | ORD/000160/2023-2024 | 843/SWD-I | 05/06/2023 | 08/11/2025 | SRIKRISHNA CO OP LABOUR CONT AND CONS SOCIETY LTD | 276.76 | 197.24 | 71.27 | 88
3 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Ground water based RAMNAGAR (ZONE-I) piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas dist | SM/15755 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1 &2 for Augmentation of Ramnagar (Zone-I) water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Baruipur] | Assistant Engineer | Junior Engineer | ORD/000062/2023-2024 | 1056/SMD | 18/04/2023 | 17/07/2023 | ELECTRICAL & MECHANICAL ENGINEERING CORPORATION | 25.66 | 25.1 | 97.82 | 100
4 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based RAMNAGAR (ZONE-I) piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas dist | SM/15755 | Augmentation | Sinking of 02 (Two) nos. Rig bored 250mm x 150mm dia. & 300 mtr. deepTubewell having 66 mtr. housing pipe by Rotary method for RAMNAGAR (ZONE-I) PWSS to accommodate FHTC in BARUIPUR block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division-I, P.H.E. Dte. [TSM/018210] | AE BSD |  | ORD/000631/2022-2023 | 3258/SWD-I | 02/03/2023 | 01/04/2023 | MUNNA AGROTECH ENTERPRISE | 31.76 | 31.1 | 97.93 | 100
5 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Ground water based RAMNAGAR (ZONE-I) piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas dist | SM/15755 | Augmentation | Supply & Fixing main switch & Bus bar at Pump House no-1 & 2 of Ramnagar (Zone-I) W/S Scheme under SMD, P.H.E. Dte.(Block-Baruipur) | Assistant Engineer | Junior Engineer | ORD/002381/2023-2024 | 1452/SMSD | 30/11/2023 | 15/12/2023 | ELECTRICAL & MECHANICAL ENGINEERING CORPORATION | 0.58 | 0.58 | 100 | 100
6 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Ground water based RAMNAGAR (ZONE-I) piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas dist | SM/15755 | Augmentation | Improvement of outdoor Illumination arrangement with allied works at Pump House no-1 of Ramnagar (Zone-I) W/S Scheme under SMD, P.H.E. Dte. (Block-Baruipur) | Assistant Engineer | Junior Engineer | ORD/002345/2023-2024 | 1454/SMSD | 30/11/2023 | 15/12/2023 | ELECTRICAL & MECHANICAL ENGINEERING CORPORATION | 0.92 | 0.91 | 99.43 | 100
7 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based RAMNAGAR (ZONE-I) piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas dist | SM/15755 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000108/2023-2024 | 294/SWD-I | 25/04/2023 | 25/04/2023 | Resource Division | 19.94 | 0 | 0 | 0
8 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Ground water based RAMNAGAR (ZONE-I) piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas dist | SM/15755 | Augmentation | Payment of electricity bill for new service connection under SMD, PHE Dte. |  |  | BILL/01503/2023-2024 | BP-2023-24-174 | 02/08/2023 | 02/08/2023 | WBSEDCL | 2.88 | 0 | 0 | 0
9 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based RAMNAGAR (ZONE-I) piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas dist | SM/15755 | Augmentation | Construction of platform for FHTC, restoration of road after laying of pipeline, development of land and other allied works for "Ground Water Based RAMNAGAR (Zone-I) Piped Water Supply Scheme to Accommodate FHTC in BARUIPUR Block Under South 24 Parganas W/S Division-I, South 24 Parganas District For Augmentation of Surface Water Based Water Supply Scheme In Arsenic Affected Areas of South 24 Parganas District." (SM/15755) |  |  | ORD/000523/2024-2025 | 4016/SWD-I | 13/09/2024 | 12/11/2024 | SRIKRISHNA CO OP LABOUR CONT AND CONS SOCIETY LTD | 95.5 | 0 | 0 | 0
10 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Ground water based RAMNAGAR (ZONE-I) piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas dist | SM/15755 | Augmentation | Supply & installation of LED board at P.H. No- 1 & 2 of RAMNAGAR (Zone-I) water supply scheme under South 24 Pgs Mechanical Division PHE Dte.[ Block- Baruipur ] | Assistant Engineer | Junior Engineer | ORD/002198/2023-2024 | 354/SMSD | 20/03/2024 | 04/04/2024 | DITHI ENTERPRISE | 0.78 | 0.78 | 100 | 100
11 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Ground water based RAMNAGAR (ZONE-I) piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas dist | SM/15755 | Augmentation | Improvement of outdoor Illumination arrangement with allied works at Pump House no-2 of Ramnagar (Zone-I) W/S Scheme under SMD, P.H.E. Dte. (Block-Sonarpur) | Assistant Engineer | Junior Engineer | ORD/002347/2023-2024 | 134/SMSD | 02/02/2024 | 17/02/2024 | ELECTRICAL & MECHANICAL ENGINEERING CORPORATION | 0.92 | 0.91 | 99.23 | 100
12 | SOUTH 24 PARGANAS |  | Alipore Division | Ground water based RAMNAGAR (ZONE-I) piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas dist | SM/15755 | Augmentation | Road restoration for 1) Ramnagar Bazar to Sakhartpur Battafa, Bangal para under ramnagar-2 gp 2) Construction of road from T03 SurJapur Hat to Ramnagar to petrol pump on Pultala Champahali Road of PMGSY-III under Baruipur Block.(WB 02 573) |  |  | BILL/01697/2024-2025 | BP-2024-25-786 | 25/10/2024 | 25/10/2024 | W.B.S.R.D.A., SOUTH TWENTY FOUR PARGANAS DIVISION | 3.64 | 0 | 0 | 0
13 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based RAMNAGAR (ZONE-I) piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas dist | SM/15755 | Augmentation | Distressed / Affected stretches of different road under P&RD Deptt. in West Bengal due to pipeline laying work by PHED [Sl. No.25] |  |  | BILL/00485/2024-2025 | BP-2024-25-293 | 11/09/2024 | 11/09/2024 | WBSRDA SOUTH 24 PGS ALIPORE | 5.42 | 0 | 0 | 0
14 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based RAMNAGAR (ZONE-I) piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas dist | SM/15755 | Augmentation | Baruipur Ramnagar Uttarbhag Port Canning Road Permanent restoration work , cause due to pipe laying work of PHED under South 24 Pgns.Divn, PWD in the District of South 24 Pgns during the year 2024-2025. |  |  | BILL/00760/2024-2025 | BP-2024-25-451 | 06/10/2024 | 06/10/2024 | EXECUTIVE ENGINEER, SOUTH 24 PGS. DIVISION, PWD | 48.96 | 0 | 0 | 0
Total | [13 empty] | 516.47 | 259.32 | 50.21