## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based RAMNAGAR (ZONE-III) piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas di | SM/15756 | Augmentation | Preparation and submission of Detailed Project Report of RAMNAGAR(III) Ground Water Based Piped Water Supply Scheme in BARUIPUR PURBA Assembly Constituency of BARUIPUR Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE BSD |  | ORD/000406/2021-2022 | 1947/SWD-I | 27/01/2022 | 26/02/2022 | ENVIROTECH SOLUTIONS | 2.76 | 2.53 | 91.89 | 0
2 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based RAMNAGAR (ZONE-III) piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas di | SM/15756 | Augmentation | Sinking of 02 (Two) nos. Rig bored 250mm x 150mm dia. & 300 mtr. deepTubewell having 66 mtr. housing pipe by Rotary method for RAMNAGAR (ZONE-III) PWSS to accommodate FHTC in BARUIPUR block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division-I, P.H.E. Dte. [TSM/018222] | AE BSD |  | ORD/000630/2022-2023 | 3257/SWD-I | 02/03/2023 | 01/04/2023 | BENGAL ENTERPRISE | 31.76 | 30.44 | 95.87 | 0
3 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based RAMNAGAR (ZONE-III) piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas di | SM/15756 | Augmentation | Construction of Boundary Wall, Chlorine Room along with Laying of Distribution System, Rising Main, Providing Functional Household Tap Connection (FHTC) for Augmentation of RAMNAGAR (PART-III) MOUZA Piped Water Supply Scheme of BARUIPUR Block for implementation of JJM under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. [No. of FHTC = 943] [TSM/018222] | AE BSD | JE RWS,JE-2 | ORD/000055/2023-2024 | 274/SWD-I | 24/04/2023 | 28/10/2025 | MS SARADA UDYOG | 151.16 | 124.14 | 82.12 | 90
4 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Ground water based RAMNAGAR (ZONE-III) piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas di | SM/15756 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1 for Augmentation of Ramnagar (Zone-3) water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Baruipur] | Assistant Engineer | Junior Engineer | ORD/000004/2023-2024 | 939/SMD | 04/04/2023 | 03/07/2023 | K.S.P ENTERPRISE | 12.96 | 0 | 0 | 0
5 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Ground water based RAMNAGAR (ZONE-III) piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas di | SM/15756 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1 &2 for Augmentation of Ramnagar (Zone-III) water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Baruipur] | Assistant Engineer | Junior Engineer | ORD/000064/2023-2024 | 1058/SMD | 18/04/2023 | 17/07/2023 | M/S. G.P ENTERPRISE | 21.76 | 10.09 | 46.38 | 50
6 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based RAMNAGAR (ZONE-III) piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas di | SM/15756 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000110/2023-2024 | 294/SWD-I | 25/04/2023 | 25/04/2023 | Resource Division | 8.72 | 0 | 0 | 0
7 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Ground water based RAMNAGAR (ZONE-III) piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas di | SM/15756 | Augmentation | Payment of electricity bill for new service connection under SMD, PHE Dte. |  |  | BILL/04228/2023-2024 | BP-2023-24-434 | 27/12/2023 | 27/12/2023 | WBSEDCL | 3.87 | 0 | 0 | 0
8 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Ground water based RAMNAGAR (ZONE-III) piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas di | SM/15756 | Augmentation | Payment of electricity bill for new service connection under SMD, PHE Dte. |  |  | BILL/01717/2023-2024 | BP-2023-24-191 | 09/08/2023 | 09/08/2023 | WBSEDCL | 2.43 | 0 | 0 | 0
9 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Ground water based RAMNAGAR (ZONE-III) piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas di | SM/15756 | Augmentation | Payment of electricity bill for new service connection under SMD, PHE Dte. |  |  | BILL/01505/2023-2024 | BP-2023-24-173 | 02/08/2023 | 02/08/2023 | WBSEDCL | 2.91 | 0 | 0 | 0
10 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Ground water based RAMNAGAR (ZONE-III) piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas di | SM/15756 | Augmentation | Improvement of outdoor Illumination arrangement with allied works at Pump House no. 2 of Ramnagar (Zone-III) W/S Scheme under SMD, P.H.E. Dte. (Block-Baruipur)(SM/15756) | Assistant Engineer | Junior Engineer | ORD/002695/2023-2024 | 349/SMSD | 19/03/2024 | 03/04/2024 | M/S. G.P ENTERPRISE | 0.89 | 0 | 0 | 0
11 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Ground water based RAMNAGAR (ZONE-III) piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas di | SM/15756 | Augmentation | Supply & Fixing main switch & Bus bar at Pump House no-1 & 2 of Ramnagar (Zone-III) W/S Scheme under SMD, P.H.E. Dte.(Block-Baruipur)(SM/15756) | Assistant Engineer | Junior Engineer | ORD/002697/2023-2024 | 347/SMSD | 19/03/2024 | 03/04/2024 | M/S. G.P ENTERPRISE | 0.58 | 0 | 0 | 0
12 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based RAMNAGAR (ZONE-III) piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas di | SM/15756 | Augmentation | Construction of Platform for providing FHTC, protection work for pipeline and other allied works for "Proposed Ground water based RAMNAGAR ZONE-III piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas district". (SM/15756) [2nd call] |  |  | ORD/000547/2024-2025 | 4135/SWD-I | 23/09/2024 | 07/11/2024 | MS SARADA UDYOG | 25.01 | 0 | 0 | 0
13 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Ground water based RAMNAGAR (ZONE-III) piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas di | SM/15756 | Augmentation | Improvement of outdoor Illumination arrangement with allied works at Pump House no. 1 of Ramnagar (Zone-III) W/S Scheme under SMD, P.H.E. Dte. (Block-Baruipur)(SM/15756) | Assistant Engineer | Junior Engineer | ORD/002696/2023-2024 | 348/SMSD | 19/03/2024 | 03/04/2024 | M/S. G.P ENTERPRISE | 0.89 | 0.81 | 91.43 | 100
14 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based RAMNAGAR (ZONE-III) piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas di | SM/15756 | Augmentation | Baruipur Ramnagar Uttarbhag Port Canning Road Permanent restoration work for 5800.0 mtr of trench(0.00 Km-1.20 Km, 1.70 Km-2.50 Km, and 3.50 Km-4.40 Km) Total trench length=5800 mtr, cause due to pipe laying work of PHED under South 24 Pgns.Divn, PWD in the District of South 24 Pgns during the year 2024-2025. |  |  | BILL/00545/2024-2025 | BP-2024-25-332 | 24/09/2024 | 24/09/2024 | EXECUTIVE ENGINEER, SOUTH 24 PGS. DIVISION, PWD | 62.5 | 0 | 0 | 0
15 | SOUTH 24 PARGANAS |  | Alipore Division | Ground water based RAMNAGAR (ZONE-III) piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas di | SM/15756 | Augmentation | Road restoration for Canning mam to Padma Stopaj Via Kailasbabur Abad Khal Par |  |  | BILL/01675/2024-2025 | BP-2024-25-780 | 25/10/2024 | 25/10/2024 | W.B.S.R.D.A., SOUTH TWENTY FOUR PARGANAS DIVISION | 1.72 | 0 | 0 | 0
Total | [13 empty] | 329.91 | 168.02 | 50.93