## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Detailed project report for BODRA piped water supply scheme to accommodate FHTC in BHANGAR-I block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Under | SM/15757 | Augmentation | Sinking of 02 (Two) nos. Rig bored 250mm x 150mm dia. & 300 mtr. deepTubewell having 66 mtr. housing pipe by Rotary method for BODRA PWSS of BHANGAR-I block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division-I, P.H.E. Dte. [TSM/017117] | AE HQ-I |  | ORD/000638/2022-2023 | 3284/SWD-I | 03/03/2023 | 02/04/2023 | M/S MONDAL ENTERPRISE | 31.76 | 0 | 0 | 0
2 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Detailed project report for BODRA piped water supply scheme to accommodate FHTC in BHANGAR-I block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Under | SM/15757 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000036/2023-2024 | 287/SWD-I | 24/04/2023 | 24/04/2023 | Resource Division | 35.63 | 0 | 0 | 0
3 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Detailed project report for BODRA piped water supply scheme to accommodate FHTC in BHANGAR-I block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Under | SM/15757 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000213/2023-2024 | 1007/SWD- I | 09/06/2023 | 09/06/2023 | Resource Division | 12.71 | 0 | 0 | 0
4 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Detailed project report for BODRA piped water supply scheme to accommodate FHTC in BHANGAR-I block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Under | SM/15757 | Augmentation | Quotation for new service (power) connection at Bodra PH-1 , Water supply scheme under Bhangar-I Block. Reference ID-106663975, Application No- 1007921742 |  |  | BILL/01468/2024-2025 | BP-2024-25-348 | 06/09/2024 | 06/09/2024 | WBSEDCL | 5.93 | 0 | 0 | 0
5 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Detailed project report for BODRA piped water supply scheme to accommodate FHTC in BHANGAR-I block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Under | SM/15757 | Augmentation | Construction of 300 cum capacity OHR (20 mtr. Staging Height), Pump House cum Chlorine Room (2 Nos.) along with Laying Distribution System, Rising Main, Functional Household Tap Connection (FHTC) including design drawing of Pile Foundation & pile cap after soil investigation for BODRA Piped Water Supply Scheme to accommodate FHTC in Bhangar-I Block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission. (No of FHTC = 2064) (TSM/017117) | AE HQ-I | JE-4 | ORD/000047/2023-2024 | 254/SWD-I | 20/04/2023 | 02/12/2025 | SARDAR ENTERPRISE | 455.71 | 195.71 | 42.95 | 20
6 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Detailed project report for BODRA piped water supply scheme to accommodate FHTC in BHANGAR-I block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Under | SM/15757 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1 & 2 of Bodra water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Bhangar-I] | Assistant Engineer | Junior Engineer | ORD/000595/2023-2024 | 2367/SMD | 30/06/2023 | 01/07/2025 | GOENKA ENTERPRISE | 22.69 | 0 | 0 | 25
7 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Detailed project report for BODRA piped water supply scheme to accommodate FHTC in BHANGAR-I block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Under | SM/15757 | Augmentation | Sinking of 02 (Two) nos. Rig Ground bored 250mm x 150mm dia & 300 mtr. deep Tubewell having 66 mtr. housing pipe by Rotary method for BODRA Piped Water Supply Scheme to accommodate FHTC in BHANGAR-I Block for augmentation of surface water based water supply scheme in the Arsenic affected areas of South 24-Pgns. Dist. under South 24 Paraganas W/S Division-I, PHE Dte. (SM/15757) | AE HQ-I | JE-4 | ORD/000666/2024-2025 | 4396/SWD-I | 23/10/2024 | 27/11/2025 | M/S. SHYAM CONSTRUCTION | 31.05 | 0 | 0 | 50
8 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Detailed project report for BODRA piped water supply scheme to accommodate FHTC in BHANGAR-I block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Under | SM/15757 | Augmentation | Construction of Boundary Wall and others allied works at HW & 2nd Tubewell site of BODRA PWSS within Bhangar-I Block to accommodate FHTC in Bhangar-I Block under South 24-Parganas, W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission. (SM/15757) |  |  | ORD/000039/2025-2026 | 1118/SWD-I | 24/04/2025 | 08/07/2025 | SARDAR ENTERPRISE | 121 | 0 | 0 | 0
9 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Detailed project report for BODRA piped water supply scheme to accommodate FHTC in BHANGAR-I block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Under | SM/15757 | Augmentation | Improvement of outdoor illumination arrangement with allied works at Bodra PH-1 under Bhangar-I Block water supply scheme under SMD, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000801/2025-2026 | 980/SMSD | 15/07/2025 | 30/07/2025 | GOENKA ENTERPRISE | 0.92 | 0 | 0 | 100
Total | [13 empty] | 717.41 | 195.71 | 27.28