## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | HASANPUR piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Under JJM | SM/15759 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000017/2023-2024 | 286/SWD-I | 24/04/2023 | 24/04/2023 | Resource Division | 6.03 | 0 | 0 | 0
2 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | HASANPUR piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Under JJM | SM/15759 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000231/2023-2024 | 1006/SWD-I | 09/06/2023 | 09/06/2023 | Resource Division | 8.84 | 0 | 0 | 0
3 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | HASANPUR piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Under JJM | SM/15759 | Augmentation | Payment of electricity bill for new service connection under SMD, PHE Dte. |  |  | BILL/00008/2023-2024 | BP-2023-24-31 | 18/05/2023 | 18/05/2023 | WBSEDCL | 5.89 | 0 | 0 | 0
4 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | HASANPUR piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Under JJM | SM/15759 | Augmentation | Sinking of 02 (Two) nos. Rig bored 250mm X 150mm dia & 300 mtr. deep Tubewell having 66 mtr. housing pipe by Rotary method for HASANPUR PWSS of Sonarpur Block for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic Affected Areas of South 24 Parganas district under South 24 Parganas Water Supply Division-I, PHE Dte. [TSM/018119] | AE HQ-I | JE-3 | ORD/000667/2022-2023 | 3407/SWD-I | 10/03/2023 | 09/04/2023 | TAPAS KUMAR GIRI | 31.8 | 30.78 | 96.8 | 50
5 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | HASANPUR piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Under JJM | SM/15759 | Augmentation | Improvement of outdoor Illumination arrangement with allied works at Pump House no-2 of Hasanpur scheme under SMD, P.H.E. Dte.(Block-Sonarpur) (SM/15679) | Assistant Engineer | Junior Engineer | ORD/000691/2024-2025 | 1014/SMSD | 11/07/2024 | 26/07/2024 | A.K. INDUSTRIES | 0.92 | 0 | 0 | 100
6 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | HASANPUR piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Under JJM | SM/15759 | Augmentation | Improvement of outdoor Illumination arrangement with allied works at Pump House no-1 of Hasanpur W/S Scheme under SMD, P.H.E. Dte. (Block-Sonarpur) | Assistant Engineer | Junior Engineer | ORD/002997/2023-2024 | 261/SMSD | 23/02/2024 | 09/03/2024 | A.K. INDUSTRIES | 0.92 | 0 | 0 | 100
7 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | HASANPUR piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Under JJM | SM/15759 | Augmentation | Supplying, fabrication & laying of 610 mm dia (OD) MS Pipe conduits 50 mtr. in length to be prepared from 12.5 mm thick MS Plate by pipe jacking technique, including supplying and laying of 219 mm dia (OD) MS water main within the conduit 60 mtr. in length to be prepared from 10 mm thick MS Plate, across and underneath the Railway Track at Bidyadharpur Railway Station in between Station Champahati (CHT) - Bidyadharpur (BDYP), OHE Mast No. 20/4C as per permission of Railway Authority for "Hasanpur Piped Water Supply Scheme to accommodate FHTC in Sonarpur Block under South 24-Parganas, W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission"(SM/15759) |  |  | ORD/000022/2025-2026 | 974/SWD-I | 09/04/2025 | 08/06/2025 | SRIJON ENTERPRISE | 64.28 | 0 | 0 | 0
8 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | HASANPUR piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Under JJM | SM/15759 | Augmentation | Construction of Pump House cum Chlorine Room along with Laying Distribution System for HASANPUR Piped W/S Scheme to accommodate FHTC in Sonarpur Block for Augmentation of Surface Water based W/S Scheme in the Arsenic affected areas of South 24-Parganas District under South 24-Pgns. W/S Division-I, PHE Dte. [TSM/018119] | AE HQ-I,Assistant engineer (contractual) | JE-3 | ORD/000074/2023-2024 | 388/SWD-I | 28/04/2023 | 01/04/2025 | J.D. CONSTRUCTION | 165.4 | 137.46 | 83.11 | 30
9 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | HASANPUR piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Under JJM | SM/15759 | Augmentation | Construction of 200 Cum. capacity RCC Overhead Reservoir of 20 Mtr. Staging Height as per departmental design, drawing & specification with RCC Bored Pile & Pile Cap including Soil Investigation and foundation design including Laying Rising Main along with providing FHTC for HASANPUR Piped W/S Scheme in Sonarpur Block for Augmentation of Surface Water based W/S Scheme in the Arsenic affected areas of South 24-Parganas District under South 24-Pgns. W/S Division-I, PHE Dte. [No. of FHTC = 1435] [TSM/018119] | AE HQ-I,Assistant engineer (contractual) | JE-3 | ORD/000071/2023-2024 | 372/SWD-I | 27/04/2023 | 01/02/2025 | M/S. JAYDEEP DASGUPTA | 156.02 | 100.03 | 64.11 | 100
10 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | HASANPUR piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Under JJM | SM/15759 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1 & 2 for Augmentation of Hasanpur water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Sonarpur] | Assistant Engineer | Junior Engineer | ORD/000119/2023-2024 | 1036/SMD | 13/04/2023 | 01/04/2025 | A.K. INDUSTRIES | 25.4 | 11.86 | 46.67 | 100
11 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | HASANPUR piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Under JJM | SM/15759 | Augmentation | Construction of Boundary wall and Temporary approach road for Head work of HASANPUR Piped Water Supply Scheme to accommodate FHTC in Sonarpur Block under South 24-Parganas, W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission"under South 24-Pgns W/S Divn-I, PHE Dte. Dist. South 24 Parganas. (Length-166 mtr.) [SM/15759] | AE HQ-II,Assistant engineer (contractual) | JE-3 | ORD/000753/2023-2024 | 555/SWD-I | 31/01/2024 | 28/11/2024 | M/S. JAYDEEP DASGUPTA | 27.69 | 20.01 | 72.24 | 5
12 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | HASANPUR piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Under JJM | SM/15759 | Augmentation | Construction of Boundary Wall and others allied works at 2nd Tubewell site of HASANPUR Piped Water Supply Scheme to accommodate FHTC in Sonarpur Block under South 24-Parganas W/S Division-I PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission. (SM/15759) | Assistant engineer (contractual) | JE-3 | ORD/000245/2024-2025 | 2665/SWD-I | 07/06/2024 | 08/12/2024 | J.D. CONSTRUCTION | 10.57 | 0 | 0 | 80
13 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | HASANPUR piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Under JJM | SM/15759 | Augmentation | Laying of additional 90mm,75mm dia pipeline work along with Bullah Piling work of "HASANPUR Piped Water Supply Scheme to accommodate FHTC in Sonarpur Block under South 24-Parganas W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission". [SM/15759] | Assistant engineer (contractual) | JE-3 | ORD/000545/2024-2025 | 4102/SWD-I | 20/09/2024 | 20/01/2025 | J.D. CONSTRUCTION | 25.92 | 0 | 0 | 100
14 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | HASANPUR piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Under JJM | SM/15759 | Augmentation | Construction of 02 (Two) nos. pipe carrying structure over canal beside Bidyadharpur-Champahati Rail line at Hasanpur & Rampur Mouza for Laying of 90mm dia HDPE Dristribution Main under "Hasanpur Piped Water Supply Scheme to accommodate FHTC in Sonarpur Block under South 24-Parganas, W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission". (SM/15759) | Assistant engineer (contractual) | JE-3 | ORD/000023/2025-2026 | 975/SWD-I | 09/04/2025 | 24/05/2025 | GANAPATI ENTERPRISE | 12.01 | 0 | 0 | 100
Total | [13 empty] | 541.69 | 300.13 | 55.41