## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | HOGALKURIA piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Under JJM | SM/15771 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000018/2023-2024 | 286/SWD-I | 24/04/2023 | 24/04/2023 | Resource Division | 17.47 | 0 | 0 | 0
2 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | HOGALKURIA piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Under JJM | SM/15771 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000232/2023-2024 | 1006/SWD-I | 09/06/2023 | 09/06/2023 | Resource Division | 8.48 | 0 | 0 | 0
3 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | HOGALKURIA piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Under JJM | SM/15771 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1 & 2 for Augmentation of Hogalkuria water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Sonarpur |  |  | ORD/001222/2023-2024 | 2130/SMD | 31/05/2023 | 29/08/2023 | DEBJYOTI BASU | 22.79 | 0 | 0 | 0
4 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | HOGALKURIA piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Under JJM | SM/15771 | Augmentation | Up-gradation of pump house, chlorine room, office room, boundary wall and construction of pathway, drain & others allied works of HOGALKURIA Piped Water Supply Scheme to accommodate FHTC in Sonarpur Block under South 24-Parganas, W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission". (SM/15771) |  |  | ORD/000746/2024-2025 | 4668/SWD-I | 18/11/2024 | 17/01/2025 | R.K ENTERPRISE | 20.9 | 0 | 0 | 0
5 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | HOGALKURIA piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Under JJM | SM/15771 | Augmentation | Construction of Boundary Wall and others allied works at HW & 2nd Tube-well site "HOGALKURIA Piped Water Supply Scheme to accommodate FHTC in Sonarpur Block under South 24-Parganas, W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission." ( SM/15771). | Assistant engineer (contractual) | JE-3 | ORD/000818/2023-2024 | 1311/SWD-I | 15/03/2024 | 29/04/2024 | MS KRISHNA MONDAL | 55.36 | 0 | 0 | 0
6 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | HOGALKURIA piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Under JJM | SM/15771 | Augmentation | Sinking of 02 (Two) nos. Rig bored 250mm X 150mm dia & 300 mtr. deep Tubewell having 66 mtr. housing pipe by Rotary method for HOGALKURIA PWSS of Sonarpur Block for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic Affected Areas of South 24 Parganas district under South 24 Parganas Water Supply Division-I, PHE Dte. [TSM/017730] | AE HQ-II | JE-3 | ORD/000668/2022-2023 | 3408/SWD-I | 10/03/2023 | 09/04/2023 | TAPAS KUMAR GIRI | 31.8 | 0 | 0 | 100
7 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | HOGALKURIA piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Under JJM | SM/15771 | Augmentation | Construction of 200 cum OHR with soil investigation, pump house cum chlorine room, Laying rising and distrbution main pipe line with FHTC for HOGALKURIA Piped Water Supply Scheme to accommodate FHTC in Sonarpur Block under South 24-Partganas, W/S Division-I for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission". (No of FHTC = 1377) (TSM/017730) | AE HQ-I,Assistant engineer (contractual) | JE RWS, Sonarpur Block | ORD/000077/2023-2024 | 391/SWD-I | 28/04/2023 | 02/10/2025 | M/S MITRA CONSTRUCTION | 357.88 | 0 | 0 | 32
8 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | HOGALKURIA piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Under JJM | SM/15771 | Augmentation | Improvement of outdoor Illumination arrangement with allied works at Pump House no-1 of Hogolkuria W/S Scheme under SMD, P.H.E. Dte.(Block-Sonarpur)(SM/15771) | Assistant Engineer | Junior Engineer | ORD/000258/2025-2026 | 502/SMSD | 04/04/2025 | 19/04/2025 | DEBJYOTI BASU | 0.88 | 0 | 0 | 0
9 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | HOGALKURIA piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Under JJM | SM/15771 | Augmentation | Improvement of outdoor Illumination arrangement with allied works at Pump House no-2 of Hogalkuria W/S Scheme under SMD, P.H.E. Dte.(Block-Sonarpur)(SM/15771) | Assistant Engineer | Junior Engineer | ORD/000262/2025-2026 | 708/SMSD | 08/05/2025 | 23/05/2025 | DEBJYOTI BASU | 0.88 | 0 | 0 | 0
10 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | HOGALKURIA piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Under JJM | SM/15771 | Augmentation | Supply & Fixing main switch & Bus bar at Pump House no-1 & 2 of Hogolkuria W/S Scheme under SMD, P.H.E. Dte.(Block-Sonarpur)(SM/15771) | Assistant Engineer | Junior Engineer | ORD/000260/2025-2026 | 501/SMSD | 04/04/2025 | 19/04/2025 | DEBJYOTI BASU | 0.58 | 0 | 0 | 0
11 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | HOGALKURIA piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Under JJM | SM/15771 | Augmentation | Sinking of Rig Ground bored 250mm x 150mm dia. & 300 mtr. deep Tubewell having 66 mtr. housing pipe by Rotary method for 2nd Tubewell site of HOGOLKURIA Piped Water Supply Scheme of SONARPUR Block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs District under South 24-Parganas W/S Division-I, PHE Dte. [SM/15771] | Assistant engineer (contractual) | JE-3 | ORD/001098/2024-2025 | 74/SWD-I | 07/01/2025 | 09/03/2025 | AQUATECH ENGINEERS | 15.5 | 0 | 0 | 100
Total | [13 empty] | 532.52 | 0 | 0