## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | PADMAPUKURIA piped water supply scheme to accommodate FHTC in BHANGAR-I block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Under JJM | SM/15772 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1 & 2 of Padmapukuria water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Bhangar-I] | Assistant Engineer | Junior Engineer | ORD/001523/2022-2023 | 930/SMD | 30/03/2023 | 01/07/2025 | SINHA ELECTRICALS | 22.91 | 0 | 0 | 90
2 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | PADMAPUKURIA piped water supply scheme to accommodate FHTC in BHANGAR-I block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Under JJM | SM/15772 | Augmentation | Construction of 300 cum capacity OHR (20 mtr. Staging Height) including design drawing of Pile Foundation & pile cap after soil investigation, construction of Pump House cum Chlorine Room, Laying Distribution System, Rising Main, Functional Household Tap Connection (FHTC) for PADMAPUKURIA Piped Water Supply Scheme to accommodate FHTC in BHANGAR-I Block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission. (No of FHTC = 1985) (TSM/018416) | AE HQ-I | JE RWS, Bhangar-II Block,JE-4 | ORD/000307/2023-2024 | 1696/SWD-I | 07/08/2023 | 27/08/2025 | M.R.U. CONSTRUCTION | 472.58 | 258.43 | 54.69 | 25
3 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | PADMAPUKURIA piped water supply scheme to accommodate FHTC in BHANGAR-I block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Under JJM | SM/15772 | Augmentation | Sinking of 02 (Two) nos. Tube Well (250mm X 150mm) dia & 300 mtr. deep Tubewell having 66 mtr. housing pipe by Rotary method for PADMAPUKURIA PWSS at Head Work site and 2nd Tube Well site of Bhangar-I Block for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic Affected Areas of South 24 Parganas district under South 24 Parganas Water Supply Division-I, PHE Dte. [TSM/018416] | AE HQ-I | JE-4 | ORD/000669/2022-2023 | 3411/SWD-I | 10/03/2023 | 09/04/2023 | REALIENCE CONSTRUCTION | 31.79 | 7.53 | 23.69 | 100
4 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | PADMAPUKURIA piped water supply scheme to accommodate FHTC in BHANGAR-I block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Under JJM | SM/15772 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000044/2023-2024 | 287/SWD-I | 24/04/2023 | 24/04/2023 | Resource Division | 21.61 | 0 | 0 | 0
5 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | PADMAPUKURIA piped water supply scheme to accommodate FHTC in BHANGAR-I block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Under JJM | SM/15772 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000244/2023-2024 | 1007/SWD- I | 09/06/2023 | 09/06/2023 | Resource Division | 12.23 | 0 | 0 | 0
6 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | PADMAPUKURIA piped water supply scheme to accommodate FHTC in BHANGAR-I block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Under JJM | SM/15772 | Augmentation | Construction of 02 (two) nos. Boundary Walls, one at Headwork site & other at 2nd tube-well site, of PADMAPUKURIA Piped Water Supply Scheme to accommodate FHTC in Bhangar-I Block under South 24-Parganas, W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission. [SM/15772] | AE HQ-I | JE-4 | ORD/000827/2023-2024 | 1108/SWD-I | 05/03/2024 | 03/10/2025 | M.R.U. CONSTRUCTION | 27.66 | 0 | 0 | 70
7 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | PADMAPUKURIA piped water supply scheme to accommodate FHTC in BHANGAR-I block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Under JJM | SM/15772 | Augmentation | Development of Land, Construction of internal service road, pipeline protection, drum sheet walling and others allied works at HW site & 2nd Tubewell site of "PADMAPUKURIA Piped Water Supply Scheme to accommodate FHTC in Bhangar-I Block under South 24 Parganas W/S Division-I, PHE Dte. for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic Affected Areas of South 24 Parganas District under Jal Jeevan Mission." (SM/15772) | AE HQ-I | JE-4 | ORD/000519/2024-2025 | 3982/SWD-I | 11/09/2024 | 12/01/2026 | D-4 CONSTRUCTION | 77.7 | 0 | 0 | 50
8 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | PADMAPUKURIA piped water supply scheme to accommodate FHTC in BHANGAR-I block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Under JJM | SM/15772 | Augmentation | Improvement of outdoor Illumination arrangement with allied works at Padmapukuria PH-2 under Bhangar-I Block W/S Scheme under SMD, P.H.E. Dte.(SM/15772) | Assistant Engineer | Junior Engineer | ORD/002017/2024-2025 | 1542/SMSD | 21/11/2024 | 06/12/2024 | SINHA ELECTRICALS | 0.9 | 0 | 0 | 100
9 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | PADMAPUKURIA piped water supply scheme to accommodate FHTC in BHANGAR-I block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Under JJM | SM/15772 | Augmentation | Supply & installation of LED board at P.H. No-1 & 2 of Padmapukuria water supply scheme under South 24-Pgs Mechanical Division PHE Dte.[Bhangar-I][SM/15772] | Assistant Engineer | Junior Engineer | ORD/002051/2024-2025 | 1679/SMSD | 23/12/2024 | 07/01/2025 | SOHINI ENTERPRISE | 0.79 | 0 | 0 | 100
10 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | PADMAPUKURIA piped water supply scheme to accommodate FHTC in BHANGAR-I block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Under JJM | SM/15772 | Augmentation | Quotation for new service(power) connection at Padmapukuria PH -2 water supply scheme under bhangar-I block Reference ID- 106550930, Application No- 1007657634 |  |  | BILL/00982/2024-2025 | BP-2024-25-215 | 30/07/2024 | 30/07/2024 | WBSEDCL | 14.05 | 0 | 0 | 0
11 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | PADMAPUKURIA piped water supply scheme to accommodate FHTC in BHANGAR-I block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Under JJM | SM/15772 | Augmentation | Quotation for new service(power) connection at Padmapukuria PH-1 water supply scheme under bhangar-I block Reference ID-106626291, Application No- 1007839611 |  |  | BILL/00647/2024-2025 | BP-2024-25-155 | 10/07/2024 | 10/07/2024 | WBSEDCL | 12.7 | 0 | 0 | 0
12 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | PADMAPUKURIA piped water supply scheme to accommodate FHTC in BHANGAR-I block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Under JJM | SM/15772 | Augmentation | Improvement of outdoor Illumination arrangement with allied works at Padmapukuria PH-1 under Bhangar-I Block W/S Scheme under SMD, P.H.E. Dte.(SM/15772) | Assistant Engineer | Junior Engineer | ORD/002019/2024-2025 | 22/SMSD | 06/01/2025 | 21/01/2025 | SINHA ELECTRICALS | 0.9 | 0 | 0 | 100
Total | [13 empty] | 695.8 | 265.96 | 38.22