## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | GANGAJOARA piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Under JJM | SM/15773 | Augmentation | Sinking of 02 (Two) nos. Rig bored 250mm X 150mm dia & 300 mtr. deep Tubewell having 66 mtr. housing pipe by Rotary method for GANGAJOARA PWSS of Sonarpur Block for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic Affected Areas of South 24 Parganas district under South 24 Parganas Water Supply Division-I, PHE Dte. [TSM/017714] | AE HQ-I |  | ORD/000666/2022-2023 | 3406/SWD-I | 10/03/2023 | 09/04/2023 | TAPAS KUMAR GIRI | 31.8 | 0 | 0 | 50
2 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | GANGAJOARA piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Under JJM | SM/15773 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000016/2023-2024 | 286/SWD-I | 24/04/2023 | 24/04/2023 | Resource Division | 58.79 | 0 | 0 | 0
3 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | GANGAJOARA piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Under JJM | SM/15773 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000252/2023-2024 | 1006/SWD-I | 09/06/2023 | 09/06/2023 | Resource Division | 10.37 | 0 | 0 | 0
4 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | GANGAJOARA piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Under JJM | SM/15773 | Augmentation | Payment of electricity bill for new service connection under SMD, PHE Dte. |  |  | BILL/01099/2023-2024 | BP-2023-24-144 | 24/07/2023 | 24/07/2023 | WBSEDCL | 9.57 | 0 | 0 | 0
5 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | GANGAJOARA piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Under JJM | SM/15773 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1 & 2 for Augmentation of Gangajoara water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Sonarpur] | Assistant Engineer | Junior Engineer | ORD/000122/2023-2024 | 1111/SMD | 20/04/2023 | 19/07/2023 | JAGANNATH ENTERPRISE | 21.77 | 0 | 0 | 40
6 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | GANGAJOARA piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Under JJM | SM/15773 | Augmentation | Construction of Boundary Wall,Land Development,Pathway,Drain & others allied works of Gangajoara Piped Water Supply Scheme to accommodate FHTC in Sonarpur Block under South 24-Parganas, W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission. [SM/15773] |  | JE-1,JE-3 | ORD/000843/2023-2024 | 1209/SWD-I | 11/03/2024 | 25/04/2024 | SAMSUL ENTERPRISE | 41.07 | 0 | 0 | 0
7 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | GANGAJOARA piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Under JJM | SM/15773 | Augmentation | Construction of Protection Wall and Land Development at 2nd Tubewell site GANGAJOARA Piped Water Supply Scheme to accommodate FHTC in Sonarpur Block under South 24-Parganas W/S Division-I, PHE Dte. for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission. (SM/15773) | AE HQ-II | JE-3 | ORD/000804/2023-2024 | 1250/SWD-I | 13/03/2024 | 12/04/2024 | KALAM ENTERPRISE | 3.85 | 0 | 0 | 100
8 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | GANGAJOARA piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Under JJM | SM/15773 | Augmentation | Construction of Boundary Wall and others allied works at 2nd Tubewell site of "GANGAJOARA Piped Water Supply Scheme to accommodate FHTC in Sonarpur Block under South 24-Parganas, W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission". (SM/15773) | AE HQ-I,Assistant engineer (contractual) | JE-4 | ORD/000243/2024-2025 | 2663/SWD-I | 07/06/2024 | 22/07/2024 | NILKANTHA ENTERPRISE | 10.43 | 0 | 0 | 100
9 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | GANGAJOARA piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Under JJM | SM/15773 | Augmentation | Distressed / Affected stretches of different road under P&RD Deptt. in West Bengal due to pipeline laying work by PHED [Sl. No.24] |  |  | BILL/00483/2024-2025 | BP-2024-25-293 | 11/09/2024 | 11/09/2024 | WBSRDA SOUTH 24 PGS ALIPORE | 8.08 | 0 | 0 | 0
10 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | GANGAJOARA piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Under JJM | SM/15773 | Augmentation | Construction of 250 cum OHR with soil investigation, pump house cum chlorine room, Laying rising and distrbution main pipe line with FHTC for GANGAJOARA Piped Water Supply Scheme to accommodate FHTC in Sonarpur Block under South 24-Partganas, W/S Division-I for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission". (No of FHTC = 1683) (TSM/017714) | AE HQ-I,Assistant engineer (contractual) | JE-3 | ORD/000233/2023-2024 | 1417/SWD-I | 17/07/2023 | 01/01/2026 | SAMSUL ENTERPRISE | 487.01 | 0 | 0 | 70
11 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | GANGAJOARA piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Under JJM | SM/15773 | Augmentation | Additional LDS and Road Restoration of GANGAJOARA Piped Water Supply Scheme to accommodate FHTC in Sonarpur Block under South 24-Parganas, W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission. (SM/15773) |  |  | ORD/000792/2024-2025 | 4843/SWD-I | 27/11/2024 | 26/01/2025 | SAMSUL ENTERPRISE | 36.02 | 0 | 0 | 0
Total | [13 empty] | 718.76 | 0 | 0