## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based GOALBERIA piped water supply scheme to accommodate FHTC in JAYNAGAR-I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Areas of | SM/15774 | Augmentation | Sinking of 02 (Two) nos. Rig bored 250mm x 150mm dia. & 300 mtr. deep Tube-well having 66 mtr. housing pipe by Rotary method for GOALBERIA PWSS of JOYNAGAR-I Block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division-I, P.H.E. Dte. [TSM/018461] | AE BSD |  | ORD/000645/2022-2023 | 3317/SWD-I | 06/03/2023 | 05/04/2023 | MOUSUMI DAS SARKAR | 31.72 | 0 | 0 | 0
2 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Ground water based GOALBERIA piped water supply scheme to accommodate FHTC in JAYNAGAR-I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Areas of | SM/15774 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1 & 2 for Augmentation of Goalberia water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Jaynagar-I] | Assistant Engineer | Junior Engineer | ORD/000281/2023-2024 | 1141/SMD | 24/04/2023 | 23/07/2023 | BISALAXMI ENTERPRISE | 17.98 | 0 | 0 | 0
3 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based GOALBERIA piped water supply scheme to accommodate FHTC in JAYNAGAR-I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Areas of | SM/15774 | Augmentation | Preparation and submission of Detailed Project Report of "GOYALBERIA Ground Water Based Piped Water Supply Scheme" in JOYNAGAR-I block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. [2nd call] | AE BSD |  | ORD/000753/2022-2023 | 709/SWD-I | 23/06/2022 | 08/07/2022 | ECO CARE | 2.77 | 2.52 | 90.98 | 100
4 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based GOALBERIA piped water supply scheme to accommodate FHTC in JAYNAGAR-I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Areas of | SM/15774 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000305/2023-2024 | 2442/SWD-I | 30/09/2023 | 30/09/2023 | Resource Division | 21.51 | 0 | 0 | 0
5 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based GOALBERIA piped water supply scheme to accommodate FHTC in JAYNAGAR-I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Areas of | SM/15774 | Augmentation | Balance miscellaneous work for Ground water based GOALBERIA piped water supply scheme to accommodate FHTC in JAYNAGAR-I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Areas of South 24 Parganas District. (SM/15774) |  |  | ORD/000865/2023-2024 | 1201/SWD-I | 11/03/2024 | 25/04/2024 | MONDAL CONSTRUCTION (BARUIPUR) | 44.48 | 0 | 0 | 0
6 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based GOALBERIA piped water supply scheme to accommodate FHTC in JAYNAGAR-I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Areas of | SM/15774 | Augmentation | Construction of 200 Cum. capacity OHR (20 mtr. staging height), Boundary Wall, Chlorine Room along with Laying of Distribution System, Rising Main, Providing Functional Household Tap Connection (FHTC) including design and drawing of pile foundation and pile cap after soil investigation for Augmentation of GOALBERIA Piped Water Supply Scheme of JOYNAGAR-I Block for implementation of JJM under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. [No. of FHTC = 878] [TSM/018461] | AE BSD | JE-1 | ORD/000258/2023-2024 | 1507/SWD-I | 20/07/2023 | 11/03/2025 | KALPANA TRADERS | 280.17 | 107.72 | 38.45 | 35
Total | [13 empty] | 398.63 | 110.23 | 27.65