## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based GOPALPUR piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 parganas w/s Division-I, South 24 Parganas district for AUGMENTATION of Surface water based water supply scheme in the Arsenic Affected areas of Sou | SM/15775 | Augmentation | Preparation and submission of Detailed Project Report of Ground Water Based Gopalpur Piped Water Supply Scheme to accommodate FHTC in Sonarpur Block under South 24-Pgs W/S Division-I, PHE Dte for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district.. |  |  | ORD/000991/2022-2023 | 1503/SWD-I | 28/09/2022 | 28/10/2022 | GEO SOLUTION | 2.76 | 2.74 | 99.52 | 100
2 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based GOPALPUR piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 parganas w/s Division-I, South 24 Parganas district for AUGMENTATION of Surface water based water supply scheme in the Arsenic Affected areas of Sou | SM/15775 | Augmentation | Sinking of 02 (Two) nos. Rig bored 250mm X 150mm dia & 300 mtr. deep Tubewell having 66 mtr. housing pipe by Rotary method for GOPALPUR PWSS of Sonarpur Block for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic Affected Areas of South 24 Parganas district under South 24 Paraganas Water Supply Division-I, PHE Dte. [TSM/019594] | AE HQ-I | JE-3 | ORD/000092/2023-2024 | 402/SWD-I | 28/04/2023 | 28/05/2023 | TAPAS KUMAR GIRI | 31.8 | 15.21 | 47.83 | 50
3 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based GOPALPUR piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 parganas w/s Division-I, South 24 Parganas district for AUGMENTATION of Surface water based water supply scheme in the Arsenic Affected areas of Sou | SM/15775 | Augmentation | Construction of pump house cum chlorine room, Laying rising and distrbution main pipe line with FHTC for GOPALPUR Piped Water Supply Scheme to accommodate FHTC in Sonarpur Block under South 24-Partganas, W/S Division-I for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission". (No of FHTC = 1097) (TSM/019594) | AE HQ-I,Assistant engineer (contractual) | JE-3 | ORD/000104/2023-2024 | 481/SWD-I | 08/05/2023 | 25/03/2025 | GUHA CONSTRUCTION | 274.08 | 207.74 | 75.8 | 27
4 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Ground water based GOPALPUR piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 parganas w/s Division-I, South 24 Parganas district for AUGMENTATION of Surface water based water supply scheme in the Arsenic Affected areas of Sou | SM/15775 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1 & 2 for Augmentation of Gopalpur water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Sonarpur] | Assistant Engineer | Junior Engineer | ORD/000123/2023-2024 | 1112/SMD | 20/04/2023 | 01/01/2026 | KARUNAMOY ENGINEERING | 22.79 | 10.67 | 46.83 | 40
5 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based GOPALPUR piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 parganas w/s Division-I, South 24 Parganas district for AUGMENTATION of Surface water based water supply scheme in the Arsenic Affected areas of Sou | SM/15775 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000003/2023-2024 | 286/SWD-I | 24/04/2023 | 24/04/2023 | Resource Division | 17.6 | 0 | 0 | 0
6 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based GOPALPUR piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 parganas w/s Division-I, South 24 Parganas district for AUGMENTATION of Surface water based water supply scheme in the Arsenic Affected areas of Sou | SM/15775 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000249/2023-2024 | 1006/SWD-I | 09/06/2023 | 09/06/2023 | Resource Division | 6.76 | 0 | 0 | 0
7 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Ground water based GOPALPUR piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 parganas w/s Division-I, South 24 Parganas district for AUGMENTATION of Surface water based water supply scheme in the Arsenic Affected areas of Sou | SM/15775 | Augmentation | Improvement of outdoor Illumination arrangement with allied works at Pump House no-1 of Gopalpur W/S Scheme under SMD, P.H.E. Dte. (Block-Sonarpur) |  | Junior Engineer | ORD/002031/2023-2024 | 327-SMSD | 14/03/2024 | 29/03/2024 | KARUNAMOY ENGINEERING | 0 | 0 | NAN | 0
8 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based GOPALPUR piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 parganas w/s Division-I, South 24 Parganas district for AUGMENTATION of Surface water based water supply scheme in the Arsenic Affected areas of Sou | SM/15775 | Augmentation | Development of Land, Construction of Pathway, Drain & others allied works of GOPALPUR Piped Water Supply Scheme to accommodate FHTC in Sonarpur Block under South 24-Parganas, W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission. (SM/15775) | Assistant engineer (contractual) | JE-3 | ORD/000824/2023-2024 | 1298/SWD-I | 15/03/2024 | 01/02/2025 | GUHA CONSTRUCTION | 39.38 | 0 | 0 | 50
9 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Ground water based GOPALPUR piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 parganas w/s Division-I, South 24 Parganas district for AUGMENTATION of Surface water based water supply scheme in the Arsenic Affected areas of Sou | SM/15775 | Augmentation | Improvement of outdoor Illumination arrangement with allied works at Pump House no-2 of Gopalpur W/S Scheme under SMD, P.H.E. Dte. (Block-Sonarpur) | Assistant Engineer | Junior Engineer | ORD/002200/2023-2024 | 328/SMSD | 14/03/2024 | 29/03/2024 | KARUNAMOY ENGINEERING | 0.89 | 0 | 0 | 0
10 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Ground water based GOPALPUR piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 parganas w/s Division-I, South 24 Parganas district for AUGMENTATION of Surface water based water supply scheme in the Arsenic Affected areas of Sou | SM/15775 | Augmentation | Supply & Fixing main switch & Bus bar including allied work at Pump House no-1 of Gopalpur W/S Scheme under SMD, P.H.E. Dte.(Block-Sonarpur )(SM/15775) | Assistant Engineer | Junior Engineer | ORD/000304/2024-2025 | 943-SMSD | 28/06/2024 | 13/07/2024 | KARUNAMOY ENGINEERING | 0.95 | 0 | 0 | 0
11 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Ground water based GOPALPUR piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 parganas w/s Division-I, South 24 Parganas district for AUGMENTATION of Surface water based water supply scheme in the Arsenic Affected areas of Sou | SM/15775 | Augmentation | Supply & Fixing main switch & Bus bar including allied work at Pump House no-1 of Gopalpur W/S Scheme under SMD, P.H.E. Dte.(Block-Sonarpur )(SM/15775) | Assistant Engineer | Junior Engineer | ORD/000301/2024-2025 | 943/SMSD | 28/06/2024 | 13/07/2024 | KARUNAMOY ENGINEERING | 0.95 | 0 | 0 | 100
12 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Ground water based GOPALPUR piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 parganas w/s Division-I, South 24 Parganas district for AUGMENTATION of Surface water based water supply scheme in the Arsenic Affected areas of Sou | SM/15775 | Augmentation | Supply & Laying cable at Pump House no. 1 of Gopalpur W/S Scheme under SMD, P.H.E. Dte. (Block-Sonarpur )(SM/15775) | Assistant Engineer | Junior Engineer | ORD/000305/2024-2025 | 942/SMSD | 28/06/2024 | 13/07/2024 | KARUNAMOY ENGINEERING | 0.89 | 0 | 0 | 100
13 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based GOPALPUR piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 parganas w/s Division-I, South 24 Parganas district for AUGMENTATION of Surface water based water supply scheme in the Arsenic Affected areas of Sou | SM/15775 | Augmentation | Sinking of Rig Ground bored 250mm x 150mm dia. & 300 mtr. deep Tubewell having 66 mtr. housing pipe by Rotary method for 2nd Tubewell site of GOPALPUR Piped Water Supply Scheme of SONARPUR Block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs District under South 24-Parganas W/S Division-I, PHE Dte. [SM/15775] | Assistant engineer (contractual) | JE-3 | ORD/001101/2024-2025 | 77/SWD-I | 07/01/2025 | 01/06/2025 | B.K.ENTERPRISE | 15.68 | 0 | 0 | 100
14 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based GOPALPUR piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 parganas w/s Division-I, South 24 Parganas district for AUGMENTATION of Surface water based water supply scheme in the Arsenic Affected areas of Sou | SM/15775 | Augmentation | Construction of Boundary Wall and others allied works at 2nd Tubewell site of GOPALPUR Piped Water Supply Scheme to accommodate FHTC in SONARPUR Block under South 24-Parganas, W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission. (SM/15775) (2nd call) | Assistant engineer (contractual) | JE-3 | ORD/001143/2024-2025 | 313/SWD-I | 28/01/2025 | 25/09/2025 | SUJOY SADHUKHAN | 9.94 | 0 | 0 | 50
15 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Ground water based GOPALPUR piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 parganas w/s Division-I, South 24 Parganas district for AUGMENTATION of Surface water based water supply scheme in the Arsenic Affected areas of Sou | SM/15775 | Augmentation | Charges for new service connection at pump house no- II of Gopalpur water supply scheme (Sonarpur Block) |  |  | BILL/00737/2025-2026 |  | 18/06/2025 | 18/06/2025 | WBSEDCL | 11.99 | 0 | 0 | 0
Total | [13 empty] | 436.44 | 236.36 | 54.16