## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Ground water based KALYANPUR (KHODAR BAZAR) PART-II piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 2 | SM/15776 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1 &2 of Kalayanpur ( Khodar Bazar) Part-II water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Baruipur] | Assistant Engineer | Junior Engineer | ORD/000059/2023-2024 | 1053/SMD | 18/04/2023 | 17/07/2023 | M/S. S.S. ENTERPRISE | 21.77 | 0 | 0 | 0
2 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based KALYANPUR (KHODAR BAZAR) PART-II piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 2 | SM/15776 | Augmentation | Construction of Pump House cum Chlorine Room, Boundary Wall along with Laying Distribution System, Rising Main and providing FHTC for Augmentation of Piped W/S Scheme of KALYANPUR (KHODAR BAZAR) (PART-II) of BARUIPUR Block of Surface Water based W/S Scheme in the Arsenic affected areas of South 24-Parganas District under South 24-Pgns. W/S Division-I, PHE Dte. [No. of FHTC = 1180] [TSM/018149] | AE BSD |  | ORD/000174/2023-2024 | 971/SWD-I | 08/06/2023 | 06/09/2023 | APORUPA CONSTRUCTION | 151.88 | 0 | 0 | 0
3 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based KALYANPUR (KHODAR BAZAR) PART-II piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 2 | SM/15776 | Augmentation | Preparation and submission of Detailed Project Report of KALYANPUR (KHODAR BAZAR) , PART-II Ground Water Based Piped Water Supply Scheme in BARUIPUR PASCHIM Assembly Constituency of BARUIPUR Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. |  |  | ORD/000505/2021-2022 | 1904/SWD-I | 27/01/2022 | 26/02/2022 | RADIANT | 2.62 | 2.47 | 94.34 | 100
4 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Ground water based KALYANPUR (KHODAR BAZAR) PART-II piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 2 | SM/15776 | Augmentation | Supply & installation of LED board at PH No.-1 of Kalyanpur (Part-II) & Piyali Kolaghata w/s scheme under South 24-Pgs Mechanical Division PHE Dte. |  |  | ORD/000891/2023-2024 | 1070/SMSD | 17/08/2023 | 27/08/2023 | SHRI KRISHNA ENTERPRISE | 0.78 | 0.78 | 100 | 100
5 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based KALYANPUR (KHODAR BAZAR) PART-II piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 2 | SM/15776 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000171/2023-2024 | 295/SWD-I | 25/04/2023 | 25/04/2023 | Resource Division | 31.37 | 0 | 0 | 0
6 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based KALYANPUR (KHODAR BAZAR) PART-II piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 2 | SM/15776 | Augmentation | Sinking of 02 (Two) nos. Rig bored 250mm x 150mm dia & 300 mtr. deep Tubewell having 66 mtr. housing by Rotary method for KALYANPUR KHODARBAZAR (Part-II) Piped Water Supply Scheme to accommodate FHTC in Baruipur block under South 24-Pgns. W/S Division-I, PHE Dte. for Augnemtation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. Dist. [SM/15776] (2nd call) |  |  | ORD/000719/2024-2025 | 4577/SWD-I | 11/11/2024 | 11/12/2024 | RAJKUMAR MONDAL | 31.8 | 0 | 0 | 0
7 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Ground water based KALYANPUR (KHODAR BAZAR) PART-II piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 2 | SM/15776 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1, of Kalyanpur water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Baruipur] | Assistant Engineer | Junior Engineer | ORD/000529/2022-2023 | 442/SMD | 17/02/2023 | 18/05/2023 | RSA ENTERPRISE | 13.01 | 12.47 | 95.82 | 65
8 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Ground water based KALYANPUR (KHODAR BAZAR) PART-II piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 2 | SM/15776 | Augmentation | Supply & Fixing main switch & Bus bar at Pump House no-1 of Kalyanpur W/S Scheme under SMD, P.H.E. Dte.(Block-Baruipur) | Assistant Engineer | Junior Engineer | ORD/002688/2023-2024 | 1106/SMSD | 22/08/2023 | 01/01/2024 | RSA ENTERPRISE | 0.29 | 0 | 0 | 100
9 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Ground water based KALYANPUR (KHODAR BAZAR) PART-II piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 2 | SM/15776 | Augmentation | Improvement of outdoor Illumination arrangement with allied works at Pump House no-1 of Kalyanpur W/S Scheme under SMD, P.H.E. Dte. (Block-Baruipur) | Assistant Engineer | Junior Engineer | ORD/002689/2023-2024 | 1105/SMSD | 22/08/2023 | 01/01/2024 | RSA ENTERPRISE | 0.9 | 0 | 0 | 100
Total | [13 empty] | 254.41 | 15.72 | 6.18