## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based MALLIKPUR PART-II piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas dist | SM/15777 | Augmentation | Preparation and submission of Detailed Project Report of MALLIKPUR , PART-II Ground Water Based Piped Water Supply Scheme in BARUIPUR PASCHIM Assembly Constituency of BARUIPUR Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. |  |  | ORD/000506/2021-2022 | 1905/SWD-I | 27/01/2022 | 26/02/2022 | RADIANT | 2.62 | 2.56 | 97.68 | 100
2 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based MALLIKPUR PART-II piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas dist | SM/15777 | Augmentation | Sinking of 04 (Four) nos. Rig bored 250mm x 150mm dia. & 300 mtr. deepTubewell by Rotary method for MALLIKPUR (PART-II) PWSS of BARUIPUR block under South 24-Parganas W/S Division-I, P.H.E. Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district. [TSM/017349] | AE BSD |  | ORD/000685/2022-2023 | 3484/SWD-I | 15/03/2023 | 14/04/2023 | HUMAYUN KABIR | 63.52 | 0 | 0 | 0
3 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based MALLIKPUR PART-II piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas dist | SM/15777 | Augmentation | Construction of Boundary Wall, Chlorine Room along with Laying of Distribution System, Rising Main, Providing Functional Household Tap Connection (FHTC) for Augmentation of MALLIKPUR (PART-II) MOUZA Piped Water Supply Scheme of BARUIPUR Block for implementation of JJM under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. [No. of FHTC = 2368] [TSM/017349] | AE BSD |  | ORD/000131/2023-2024 | 665/SWD-I | 24/05/2023 | 22/08/2023 | M/S B.N. ENTERPRISE | 284.55 | 0 | 0 | 0
4 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based MALLIKPUR PART-II piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas dist | SM/15777 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000182/2023-2024 | 296/SWD-I | 25/04/2023 | 25/04/2023 | Resource Division | 73.07 | 0 | 0 | 0
5 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Ground water based MALLIKPUR PART-II piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas dist | SM/15777 | Augmentation | Quotation for new connection at mallickpur GP within Zone-VI, Padmapur Boosting station. Application No- 1008738498 |  |  | BILL/01969/2025-2026 |  | 02/09/2025 | 02/09/2025 | WBSEDCL | 9.47 | 0 | 0 | 0
Total | [13 empty] | 433.22 | 2.56 | 0.59