## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Proposed Ground Water Based TILPI(Zone-I) Piped Water Supply Scheme to Accommodate FHTC inJAYNAGAR-I Block Under South 24 Parganas W/S Division-I, South 24 Parganas District For Augmentation of Surface Water Based Water Supply Scheme In Arsenic Affected A | SM/15781 | Augmentation | Preparation and submission of Detailed Project Report of "TILPI Zone-I Ground Water Based Piped Water Supply Scheme" in JOYNAGAR-I block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. [2nd call] | AE BSD |  | ORD/000756/2022-2023 | 707/SWD-I | 23/06/2022 | 08/07/2022 | ECO CARE | 2.56 | 2.56 | 100 | 100
2 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Proposed Ground Water Based TILPI(Zone-I) Piped Water Supply Scheme to Accommodate FHTC inJAYNAGAR-I Block Under South 24 Parganas W/S Division-I, South 24 Parganas District For Augmentation of Surface Water Based Water Supply Scheme In Arsenic Affected A | SM/15781 | Augmentation | Sinking of Rig bored 250mm x 150 mm dia. & 300 mtr. deep Tubewell by Rotary method for TILPI Zone-I PWSS to accommodate FHTC in Joynagar-I Block Under South 24 Parganas W/S Division-I, P.H.E Dte. for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Areas of South 24 Parganas District. (TSM/018024) | AE BSD | JE RWS | ORD/000704/2022-2023 | 3513/SWD-I | 17/03/2023 | 16/04/2023 | MALLICK CONSTRUCTION | 15.82 | 14.7 | 92.92 | 100
3 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Proposed Ground Water Based TILPI(Zone-I) Piped Water Supply Scheme to Accommodate FHTC inJAYNAGAR-I Block Under South 24 Parganas W/S Division-I, South 24 Parganas District For Augmentation of Surface Water Based Water Supply Scheme In Arsenic Affected A | SM/15781 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1 & 2 Zone-I for Augmentation of Tilpi water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Jaynagar-I] | Assistant Engineer | Junior Engineer | ORD/000282/2023-2024 | 1142/SMD | 24/04/2023 | 23/07/2023 | JAL PRAVAHIKA PVT. LTD. | 21.77 | 0 | 0 | 0
4 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Proposed Ground Water Based TILPI(Zone-I) Piped Water Supply Scheme to Accommodate FHTC inJAYNAGAR-I Block Under South 24 Parganas W/S Division-I, South 24 Parganas District For Augmentation of Surface Water Based Water Supply Scheme In Arsenic Affected A | SM/15781 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1 & 2 Zone-I for Augmentation of Tilpi water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Jaynagar-I] | Assistant Engineer | Junior Engineer | ORD/000602/2023-2024 | 2369/SMD | 30/06/2023 | 28/09/2023 | JAL PRAVAHIKA PVT. LTD. | 21.77 | 0 | 0 | 45
5 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Proposed Ground Water Based TILPI(Zone-I) Piped Water Supply Scheme to Accommodate FHTC inJAYNAGAR-I Block Under South 24 Parganas W/S Division-I, South 24 Parganas District For Augmentation of Surface Water Based Water Supply Scheme In Arsenic Affected A | SM/15781 | Augmentation | Construction of 2 Nos. OHR of different capacities including design and drawing of pile cap after soil investigation, Pump House cum Chlorine Room (7 nos.), Boundary Wall along with Laying of Distribution System, Rising Main, Providing Functional Household Tap Connection (FHTC) for Augmentation of TILPI (ZONE-I), TILPI (ZONE-II), KHAKURDAHA & DHOSA Mouza PWSS of JOYNAGAR-I Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. | AE BSD | JE RWS | ORD/000563/2023-2024 | 2610/SWD-I | 17/10/2023 | 30/07/2025 | GARAI INFRA PROJECT | 1193.4 | 208.2 | 17.45 | 96
6 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Proposed Ground Water Based TILPI(Zone-I) Piped Water Supply Scheme to Accommodate FHTC inJAYNAGAR-I Block Under South 24 Parganas W/S Division-I, South 24 Parganas District For Augmentation of Surface Water Based Water Supply Scheme In Arsenic Affected A | SM/15781 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000153/2023-2024 | 295/SWD-I | 25/04/2023 | 25/04/2023 | Resource Division | 31.28 | 0 | 0 | 0
7 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Proposed Ground Water Based TILPI(Zone-I) Piped Water Supply Scheme to Accommodate FHTC inJAYNAGAR-I Block Under South 24 Parganas W/S Division-I, South 24 Parganas District For Augmentation of Surface Water Based Water Supply Scheme In Arsenic Affected A | SM/15781 | Augmentation | Sinking of Rig bored 250mm x 150mm dia & 360 mtr. deep Tubewell having 66 mtr. housing by Rotary method at 2nd Tubewell site for TILPI (Zone-I) Piped Water Supply Scheme to accommodate FHTC in Jaynagar-I block under South 24-Pgns. W/S Division-I, South 24-Pgns. District for Augnemtation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. Dist. [SM/15781] |  |  | ORD/000807/2023-2024 | 1286/SWD-I | 15/03/2024 | 14/04/2024 | M/S BASAK CONSTRUCTION | 18.9 | 0 | 0 | 0
8 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Proposed Ground Water Based TILPI(Zone-I) Piped Water Supply Scheme to Accommodate FHTC inJAYNAGAR-I Block Under South 24 Parganas W/S Division-I, South 24 Parganas District For Augmentation of Surface Water Based Water Supply Scheme In Arsenic Affected A | SM/15781 | Augmentation | Construction of platfrom for FHTC, restoration of road after laying of Pipeline, Land development and other allied works for "Ground Water Based Tilpi ZONE-I Piped Water Supply Scheme to Accommodate FHTC in Jaynagar-I Block Under South 24 Parganas W/S Division-I, South 24 Parganas District For Augmentation of Surface Water Based Water Supply Scheme In Arsenic Affected Areas of South 24 Parganas District." (SM/15781) | AE BSD | JE RWS | ORD/000354/2024-2025 | 3454/SWD-I | 02/08/2024 | 11/09/2025 | GARAI INFRA PROJECT | 83.17 | 0 | 0 | 85
9 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Proposed Ground Water Based TILPI(Zone-I) Piped Water Supply Scheme to Accommodate FHTC inJAYNAGAR-I Block Under South 24 Parganas W/S Division-I, South 24 Parganas District For Augmentation of Surface Water Based Water Supply Scheme In Arsenic Affected A | SM/15781 | Augmentation | Improvement of outdoor Illumination arrangement with allied works at Pump House no-2 of Tilpi Zone-I W/S Scheme under SMD, P.H.E. Dte. (Block-Jaynagar-I) (SM/15781) | Assistant Engineer | Junior Engineer | ORD/002349/2024-2025 | 1463/SMSD | 30/10/2024 | 14/11/2024 | JAL PRAVAHIKA PVT. LTD. | 0.95 | 0 | 0 | 0
10 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Proposed Ground Water Based TILPI(Zone-I) Piped Water Supply Scheme to Accommodate FHTC inJAYNAGAR-I Block Under South 24 Parganas W/S Division-I, South 24 Parganas District For Augmentation of Surface Water Based Water Supply Scheme In Arsenic Affected A | SM/15781 | Augmentation | Quotation for new service (power) connection at ph no-2 of Tilpi (zone-I) w/s scheme . Application no-1007784239 . |  |  | BILL/00443/2024-2025 | BP-2024-25-112 | 14/06/2024 | 14/06/2024 | WBSEDCL | 4.66 | 0 | 0 | 0
11 | SOUTH 24 PARGANAS |  | Alipore Division | Proposed Ground Water Based TILPI(Zone-I) Piped Water Supply Scheme to Accommodate FHTC inJAYNAGAR-I Block Under South 24 Parganas W/S Division-I, South 24 Parganas District For Augmentation of Surface Water Based Water Supply Scheme In Arsenic Affected A | SM/15781 | Augmentation | Road restoration of WB02526, L022- Dhosa to Dhosa Chandaneswar irrigation road |  |  | BILL/01780/2024-2025 | BP-2024-25-805 | 25/10/2024 | 25/10/2024 | W.B.S.R.D.A., SOUTH TWENTY FOUR PARGANAS DIVISION | 8.36 | 0 | 0 | 0
12 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Proposed Ground Water Based TILPI(Zone-I) Piped Water Supply Scheme to Accommodate FHTC inJAYNAGAR-I Block Under South 24 Parganas W/S Division-I, South 24 Parganas District For Augmentation of Surface Water Based Water Supply Scheme In Arsenic Affected A | SM/15781 | Augmentation | Quotation for new power connection at P. H. NO.1 of Tilpi zone-1 w/s scheme . Jaynagar-I Block . Application no.1008337082 . |  |  | BILL/02795/2024-2025 | BP-2024-25-571 | 20/03/2025 | 20/03/2025 | WBSEDCL | 3.14 | 0 | 0 | 0
Total | [13 empty] | 1405.76 | 225.46 | 16.04