## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Proposed Ground water based BERALIA piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Area | SM/15783 | Augmentation | Preparation and submission of Detailed Project Report of Ground Water Based Beralia Piped Water Supply Scheme to accommodate FHTC in Baruipur Block under South 24-Pgs W/S Division-I, PHE Dte for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. |  |  | ORD/000945/2022-2023 | 1266/SWD-I | 12/09/2022 | 12/10/2022 | GEO SOLUTION | 2.54 | 0 | 0 | 100
2 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Proposed Ground water based BERALIA piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Area | SM/15783 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000119/2023-2024 | 295/SWD-I | 25/04/2023 | 25/04/2023 | Resource Division | 23.83 | 0 | 0 | 0
3 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Proposed Ground water based BERALIA piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Area | SM/15783 | Augmentation | Sinking of 02 (Two) nos Rig bored 250mm x 150 mm dia. & 300 mtr. deep Tubewell by Rotary method for BERALIA PWSS to accommodate FHTC in Baruipur Block Under South 24 Parganas W/S Division-I, P.H.E Dte. for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Areas of South 24 Parganas District. (TSM/018427) | AE BSD | JE-1 | ORD/000706/2022-2023 | 3519/SWD-I | 17/03/2023 | 16/04/2023 | M/S A.M. CONSTRUCTION | 31.76 | 0 | 0 | 50
4 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Proposed Ground water based BERALIA piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Area | SM/15783 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1 &2 of Beralia water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Baruipur] | Assistant Engineer | Junior Engineer | ORD/001128/2023-2024 | 4270/SMD | 07/11/2023 | 05/02/2024 | T.S. CONSTRUCTION | 22.2 | 0 | 0 | 40
5 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Proposed Ground water based BERALIA piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Area | SM/15783 | Augmentation | Supply & Fixing main switch & Bus bar at Pump House no-1 & 2 of Beralia W/S Scheme under SMD, P.H.E. Dte.(Block-Baruipur)(SM/15783) | Assistant Engineer | Junior Engineer | ORD/000299/2024-2025 | 928-SMSD | 28/06/2024 | 13/07/2024 | T.S. CONSTRUCTION | 0.58 | 0 | 0 | 0
6 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Proposed Ground water based BERALIA piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Area | SM/15783 | Augmentation | Payment of electricity bill for new service connection under SMD, PHE Dte. |  |  | BILL/00122/2024-2025 | BP-2024-25-38 | 24/04/2024 | 24/04/2024 | WBSEDCL | 3.88 | 0 | 0 | 0
7 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Proposed Ground water based BERALIA piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Area | SM/15783 | Augmentation | Construction of Pump house cum Chlorine Room, Boundary Wall along with Laying of Distribution System, Rising Main, Providing Functional Household Tap Connection (FHTC) for BERALIA Piped Water Supply Scheme of BARUIPUR Block for implementation of JJM under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. [No. of FHTC = 990] [TSM/018427] | AE BSD | JE-1 | ORD/000069/2023-2024 | 370/SWD-I | 27/04/2023 | 25/06/2025 | SOMA ENTERPRISE | 207.4 | 0 | 0 | 93
Total | [13 empty] | 292.19 | 0 | 0