## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Proposed Ground water based DHOPA GACHHI piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected | SM/15786 | Augmentation | Sinking of 02 (Two) nos. Rig bored 250mm x 150mm dia. & 300 mtr. deep Tube-well having 66 mtr. housing pipe by Rotary method for DHOPAGACHI PWSS of BARUIPUR Block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division-I, P.H.E. Dte. [TSM/018424] | AE BSD |  | ORD/000643/2022-2023 | 3316/SWD-I | 06/03/2023 | 05/04/2023 | M/S M.S. ENTERPRISE | 31.77 | 0 | 0 | 0
2 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Proposed Ground water based DHOPA GACHHI piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected | SM/15786 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1 &2 of Dhopa Gachi water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Baruipur] | Assistant Engineer | Junior Engineer | ORD/000085/2023-2024 | 1065/SMD | 18/04/2023 | 17/07/2023 | B.T.PROJECTS PVT.LTD. | 21.46 | 0 | 0 | 0
3 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Proposed Ground water based DHOPA GACHHI piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected | SM/15786 | Augmentation | Preparation and submission of Detailed Project Report of Ground Water Based Dhopa Gachhi Piped Water Supply Scheme to accommodate FHTC in Baruipur Block under South 24-Pgs W/S Division-I, PHE Dte for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. |  |  | ORD/000941/2022-2023 | 1258/SWD-I | 09/09/2022 | 09/10/2022 | GEO SOLUTION | 2.48 | 0 | 0 | 100
4 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Proposed Ground water based DHOPA GACHHI piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected | SM/15786 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000122/2023-2024 | 295/SWD-I | 25/04/2023 | 25/04/2023 | Resource Division | 29.34 | 0 | 0 | 0
5 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Proposed Ground water based DHOPA GACHHI piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected | SM/15786 | Augmentation | Sinking of Rig bored 250mm x 150mm dia. & 300 mtr. deep Tubewell having 66 mtr. housing pipe by Rotary method at 2nd Tubewell site for DHOPAGACHI Piped Water Supply Scheme to accommodate FHTC in BARUIPUR Block under South 24-Parganas W/S Division-I, South 24 Parganas District for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs District. [SM/15786] |  |  | ORD/000878/2024-2025 | 4976/SWD-I | 05/12/2024 | 04/01/2025 | M/S. SHYAM CONSTRUCTION | 15.53 | 0 | 0 | 0
6 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Proposed Ground water based DHOPA GACHHI piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected | SM/15786 | Augmentation | Sinking of Rig bored 250mm x 150mm dia. & 300 mtr. deep Tube-well having 66 mtr. housing pipe by Rotary method at Head work site for DHOPAGACHI PWSS of BARUIPUR Block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division-I, P.H.E. Dte. [SM/15786] |  |  | ORD/000385/2024-2025 | 3588/SWD-I | 13/08/2024 | 28/08/2024 | PADMA ENGINEERING CO. | 15.88 | 0 | 0 | 0
7 | SOUTH 24 PARGANAS |  | Alipore Division | Proposed Ground water based DHOPA GACHHI piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected | SM/15786 | Augmentation | Jagita Sarda House to Khalpar Bypass Via Roybahadur Via Projit Mondal To Nikfiil Ranjan Roy House Via Khardhya Math Via Bapi Naskar House |  |  | BILL/01703/2024-2025 | BP-2024-25-788 | 25/10/2024 | 25/10/2024 | W.B.S.R.D.A., SOUTH TWENTY FOUR PARGANAS DIVISION | 1.16 | 0 | 0 | 0
8 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Proposed Ground water based DHOPA GACHHI piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected | SM/15786 | Augmentation | Payment of electricity bill for new service connection under SMD, PHE Dte. |  |  | BILL/04652/2023-2024 | BP-2023-24-489 | 12/02/2024 | 12/02/2024 | WBSEDCL | 2.31 | 0 | 0 | 0
9 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Proposed Ground water based DHOPA GACHHI piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected | SM/15786 | Augmentation | Construction of Pump house cum Chlorine Room, Boundary Wall along with Laying of Distribution System, Rising Main, Providing Functional Household Tap Connection (FHTC) for DHOPA GACHI Piped Water Supply Scheme of BARUIPUR Block for implementation of JJM under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. [No. of FHTC = 917] [TSM/018424] | AE BSD | JE RWS,JE-2 | ORD/000084/2023-2024 | 418/SWD-I | 02/05/2023 | 15/03/2026 | MONDAL CONSTRUCTION | 168.94 | 0 | 0 | 95
10 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Proposed Ground water based DHOPA GACHHI piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected | SM/15786 | Augmentation | Construction of OHR/ 2nd TW site, platform for providing FHTC, restoration of road and other allied works for Augmentation of Ground Water based DHOPAGACHHI piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte. (SM/15786) | AE BSD | JE RWS | ORD/000373/2024-2025 | 3551/SWD-I | 09/08/2024 | 22/03/2025 | MONDAL CONSTRUCTION (BARUIPUR) | 46.21 | 0 | 0 | 30
Total | [13 empty] | 335.08 | 0 | 0