## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | DAKSHIN RAJAPUR piped water supply scheme to accommodate FHTC in BHANGAR-I block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Under JJM | SM/15861 | Augmentation | Construction of 300 cum capacity OHR (20 mtr. Staging Height), Pump House cum Chlorine Room (2 Nos.) along with Laying Distribution System, Rising Main, Functional Household Tap Connection (FHTC) including design drawing of Pile Foundation & pile cap after soil investigation for DAKSHIN RAJAPUR Piped Water Supply Scheme to accommodate FHTC in Bhangar-I Block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission. (No of FHTC = 2106) (TSM/017116) | AE HQ-I | JE-4 | ORD/000022/2023-2024 | 99/SWD-I | 10/04/2023 | 04/02/2024 | MILAN GHOSH | 488.23 | 122.9 | 25.17 | 15
2 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | DAKSHIN RAJAPUR piped water supply scheme to accommodate FHTC in BHANGAR-I block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Under JJM | SM/15861 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1 & 2 of Dakshin Rajapur water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Bhangar-I] | Assistant Engineer | Junior Engineer | ORD/001519/2022-2023 | 908/SMD | 28/03/2023 | 26/06/2023 | GOENKA ENTERPRISE | 22.69 | 0 | 0 | 0
3 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | DAKSHIN RAJAPUR piped water supply scheme to accommodate FHTC in BHANGAR-I block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Under JJM | SM/15861 | Augmentation | Sinking of 02 (Two) nos. Rig bored 250mm x 150mm dia. & 300 mtr. deepTubewell having 66 mtr. housing pipe by Rotary method for DAKSHIN RAJAPUR PWSS of BHANGAR-I block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division-I, P.H.E. Dte. [TSM/017116] | AE HQ-I |  | ORD/000637/2022-2023 | 3283/SWD-I | 03/03/2023 | 02/04/2023 | SAMSUDDIN MANDAL | 31.76 | 29.75 | 93.65 | 100
4 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | DAKSHIN RAJAPUR piped water supply scheme to accommodate FHTC in BHANGAR-I block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Under JJM | SM/15861 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000037/2023-2024 | 287/SWD-I | 24/04/2023 | 24/04/2023 | Resource Division | 27.61 | 0 | 0 | 0
5 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | DAKSHIN RAJAPUR piped water supply scheme to accommodate FHTC in BHANGAR-I block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Under JJM | SM/15861 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000214/2023-2024 | 1007/SWD- I | 09/06/2023 | 09/06/2023 | Resource Division | 12.97 | 0 | 0 | 0
6 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | DAKSHIN RAJAPUR piped water supply scheme to accommodate FHTC in BHANGAR-I block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Under JJM | SM/15861 | Augmentation | Construction of Boundary Wall and others allied works at 2nd Tubewell site of DAKSHIN RAJAPUR Piped Water Supply Scheme to accommodate FHTC in Bhangar-I Block under South 24-Parganas W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission. (SM/15861) |  |  | ORD/000877/2024-2025 | 4975/SWD-I | 05/12/2024 | 19/01/2025 | Grafton Tarmac Engineering And Civil | 11.2 | 0 | 0 | 0
7 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | DAKSHIN RAJAPUR piped water supply scheme to accommodate FHTC in BHANGAR-I block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Under JJM | SM/15861 | Augmentation | Construction of Boundary Wall and others allied works at HW site of DAKSHIN RAJAPUR Piped Water Supply Scheme to accommodate FHTC in Bhangar-I Block under South 24-Parganas, W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission. (SM/15861) |  |  | ORD/000559/2024-2025 | 4232/SWD-I | 30/09/2024 | 29/11/2024 | MOLLICK ENTERPRISE | 48.21 | 0 | 0 | 0
8 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | DAKSHIN RAJAPUR piped water supply scheme to accommodate FHTC in BHANGAR-I block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Under JJM | SM/15861 | Augmentation | Quotation for new service (power) connection at Dakshin Rajapur PH-I Water supply scheme under Bhangar-I Block Reference ID- 106967865, Application No- 1008422044 |  |  | BILL/00252/2025-2026 | 42152 | 01/08/2025 | 01/08/2025 | WBSEDCL | 5.79 | 0 | 0 | 0
9 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | DAKSHIN RAJAPUR piped water supply scheme to accommodate FHTC in BHANGAR-I block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Under JJM | SM/15861 | Augmentation | Quotation for new service (power) connection at Dakshin Rajapur PH-II Water supply scheme under Bhangar-I Block Reference ID- 106967864, Application No- 1008422060. |  |  | BILL/00261/2025-2026 | 42152 | 01/08/2025 | 01/08/2025 | WBSEDCL | 4.92 | 0 | 0 | 0
Total | [13 empty] | 653.39 | 152.65 | 23.36