## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | GOBINDAPUR piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Under JJM | SM/15862 | Augmentation | Sinking of 02 (Two) nos. Rig bored 250mm X 150mm dia & 300 mtr. deep Tubewell having 66 mtr. housing pipe by Rotary method for GOBINDAPUR PWSS of Sonarpur Blockfor Augmentation of Surface Water Based Water Supply Scheme in the Arsenic Affected Areas of South 24 Parganas district under South 24 Parganas Water Supply Division-I, PHE Dte. [SM/15862] | AE HQ-I |  | ORD/000679/2022-2023 | 3465/SWD-I | 15/03/2023 | 14/04/2023 | TAPAS KUMAR GIRI | 31.8 | 0 | 0 | 0
2 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | GOBINDAPUR piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Under JJM | SM/15862 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1 & 2 for Augmentation of Gobindapur water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Sonarpur] | Assistant Engineer | Junior Engineer | ORD/000118/2023-2024 | 1035/SMD | 13/04/2023 | 12/07/2023 | A.K. INDUSTRIES | 25.4 | 0 | 0 | 0
3 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | GOBINDAPUR piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Under JJM | SM/15862 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000002/2023-2024 | 286/SWD-I | 24/04/2023 | 24/04/2023 | Resource Division | 30.53 | 0 | 0 | 0
4 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | GOBINDAPUR piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Under JJM | SM/15862 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000225/2023-2024 | 1006/SWD-I | 09/06/2023 | 09/06/2023 | Resource Division | 9.5 | 0 | 0 | 0
5 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | GOBINDAPUR piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Under JJM | SM/15862 | Augmentation | Distressed / Affected stretches of different road under P&RD Deptt. in West Bengal due to pipeline laying work by PHED [Sl. No.22] |  |  | BILL/00481/2024-2025 | BP-2024-25-293 | 11/09/2024 | 11/09/2024 | WBSRDA SOUTH 24 PGS ALIPORE | 1.07 | 0 | 0 | 0
6 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | GOBINDAPUR piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Under JJM | SM/15862 | Augmentation | Distressed / Affected stretches of different road under P&RD Deptt. in West Bengal due to pipeline laying work by PHED [Sl. No.16] |  |  | BILL/00475/2024-2025 | BP-2024-25-293 | 11/09/2024 | 11/09/2024 | WBSRDA SOUTH 24 PGS ALIPORE | 17.53 | 0 | 0 | 0
7 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | GOBINDAPUR piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Under JJM | SM/15862 | Augmentation | Construction of 200 cum OHR with soil investigation, pump house cum chlorine room, Laying rising and distrbution main pipe line with FHTC for GOBINDAPUR Piped Water Supply Scheme to accommodate FHTC in Sonarpur Block under South 24-Partganas, W/S Division-I for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission. (No of FHTC = 1543) (TSM/017732) | AE HQ-I,Assistant engineer (contractual) | JE RWS, Sonarpur Block | ORD/000080/2023-2024 | 392/SWD-I | 28/04/2023 | 01/10/2025 | NIRMAN ENTERPRISE | 370.71 | 41.22 | 11.12 | 25
8 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | GOBINDAPUR piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Under JJM | SM/15862 | Augmentation | Construction of Boundary Wall and others allied works at 2nd Tubewell site of GOBINDAPUR Piped Water Supply Scheme to accommodate FHTC in Sonarpur Block under South 24-Parganas, W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission. (SM/15862) |  |  | ORD/000754/2024-2025 | 4706/SWD-I | 18/11/2024 | 02/01/2025 | N. ENTERPRISE | 10 | 0 | 0 | 0
9 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | GOBINDAPUR piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Under JJM | SM/15862 | Augmentation | Construction of Boundary Wall, Pathway, Drain, Development of Land & others allied works of ¿GOBINDAPUR Piped Water Supply Scheme to accommodate FHTC in Sonarpur Block under South 24-Parganas, W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission" (SM/15862). | Assistant engineer (contractual) | JE-3 | ORD/000239/2024-2025 | 2659/SWD-I | 07/06/2024 | 22/07/2024 | NIRMAN ENTERPRISE | 59.77 | 0 | 0 | 0
10 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | GOBINDAPUR piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Under JJM | SM/15862 | Augmentation | Sinking of Rig bored 250mm X 150mm dia & 300 mtr. deep Tubewell having 66 mtr. housing pipe by Rotary method at Headwork site for GOBINDAPUR PWSS of Sonarpur Blockfor Augmentation of Surface Water Based Water Supply Scheme in the Arsenic Affected Areas of South 24 Parganas district under South 24 Paraganas Water Supply Division-I, PHE Dte. [TSM/015394] | Assistant engineer (contractual) | JE-3 | ORD/001108/2024-2025 | 111/SWD-I | 09/01/2025 | 30/03/2025 | SIMPLEX DRILLING COMPANY | 15.8 | 0 | 0 | 100
11 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | GOBINDAPUR piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Under JJM | SM/15862 | Augmentation | Sinking of 01 (one) no. Rig bored 250mm x 150mm dia. & 300 mtr. deep Tubewell having 66 mtr. housing pipe by Rotary method at 2nd Tubewell site for GOBINDAPUR Piped Water Supply Scheme to accommodate FHTC in SONARPUR Block under South 24-Parganas W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs District. [SM/15862] | Assistant engineer (contractual) | JE-3 | ORD/001188/2024-2025 | 773/SWD-I | 18/03/2025 | 16/05/2025 | KALPANA BUILDERS (SALTLAKE) | 15.56 | 0 | 0 | 100
Total | [13 empty] | 587.66 | 41.22 | 7.01