## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Ground water based BELADANGA piped water supply scheme to accommodate FHTC in JAYNAGAR-I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Areas of | SM/15864 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1 & 2 for Augmentation of Beladanga water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Jaynagar-I] | Assistant Engineer | Junior Engineer | ORD/000280/2023-2024 | 1140/SMD | 24/04/2023 | 23/07/2023 | M/S. DAS ENTERPRISE | 26.01 | 0 | 0 | 0
2 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based BELADANGA piped water supply scheme to accommodate FHTC in JAYNAGAR-I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Areas of | SM/15864 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000168/2023-2024 | 295/SWD-I | 25/04/2023 | 25/04/2023 | Resource Division | 23.95 | 0 | 0 | 0
3 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based BELADANGA piped water supply scheme to accommodate FHTC in JAYNAGAR-I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Areas of | SM/15864 | Augmentation | Sinking of 02 (Two) nos Rig bored 250mm x 150 mm dia. & 300 mtr. deep Tubewell by Rotary method for BELADANGA PWSS to accommodate FHTC in Joynagar-I Block Under South 24 Parganas W/S Division-I, P.H.E Dte. for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Areas of South 24 Parganas District. (TSM/020328) | AE BSD | JE-1 | ORD/000703/2022-2023 | 3512/SWD-I | 17/03/2023 | 05/01/2025 | ASIT PRAMANIK | 31.76 | 0 | 0 | 75
4 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based BELADANGA piped water supply scheme to accommodate FHTC in JAYNAGAR-I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Areas of | SM/15864 | Augmentation | Preparation and submission of Detailed Project Report of Ground Water Based Beladanga Piped Water Supply Scheme to accommodate FHTC in Jaynagar-I Block under South 24-Pgs W/S Division-I, PHE Dte for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district.. |  |  | ORD/000989/2022-2023 | 1493/SWD-I | 27/09/2022 | 27/10/2022 | MEASURE LAND | 2.47 | 2.47 | 99.66 | 100
5 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Ground water based BELADANGA piped water supply scheme to accommodate FHTC in JAYNAGAR-I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Areas of | SM/15864 | Augmentation | Payment of electricity bill for new service connection under SMD, PHE Dte. |  |  | BILL/05027/2023-2024 | BP-2023-24-562 | 11/03/2024 | 11/03/2024 | WBSEDCL | 6.54 | 0 | 0 | 0
6 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based BELADANGA piped water supply scheme to accommodate FHTC in JAYNAGAR-I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Areas of | SM/15864 | Augmentation | Construction of 250 Cum. capacity RCC Overhead Reservoir of 20 Mtr. Staging Height as per departmental design, drawing & specification with RCC Bored Pile & Pile Cap including Soil Investigation and foundation design, Boundary Wall, Pump House cum Chlorine Room and Laying Distribution System, Rising Main and providing FHTC for Augmentation of BELADANGA Piped W/S Scheme of Joynagar-I Block for Augmentation of Surface Water based W/S Scheme in the Arsenic affected areas of South 24-Parganas District under South 24-Pgns. W/S Division-I, PHE Dte. [No. of FHTC = 1424] [TSM/020328]. | AE BSD | JE-1,JE-2 | ORD/000075/2023-2024 | 389/SWD-I | 28/04/2023 | 22/02/2024 | M/S T.R. CONSTRUCTION | 312.36 | 53.38 | 17.09 | 5
7 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based BELADANGA piped water supply scheme to accommodate FHTC in JAYNAGAR-I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Areas of | SM/15864 | Augmentation | Sinking of 01 (one) no. Rig bored 250mm x 150mm dia. & 300 mtr. deep Tubewell having 66 mtr. housing pipe by Rotary method at 2nd Tubewell site for BELADANGA Piped Water Supply Scheme to accommodate FHTC in JAYNAGAR-I Block under South 24-Parganas W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs District. [SM/15864] |  |  | ORD/000008/2025-2026 | 911/SWD-I | 02/04/2025 | 02/05/2025 | ARUP ENTERPRISE | 15.58 | 0 | 0 | 0
Total | [13 empty] | 418.68 | 55.84 | 13.34