## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground Water Based TILPI(Zone-II) Piped Water Supply Scheme to Accommodate FHTC inJAYNAGAR-I Block Under South 24 Parganas W/S Division-I, South 24 Parganas District For Augmentation of Surface Water Based Water Supply Scheme In Arsenic Affected Areas of | SM/15865 | Augmentation | Preparation and submission of Detailed Project Report of "TILPI Zone-II Ground Water Based Piped Water Supply Scheme" in JOYNAGAR-I block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. [2nd call] | AE BSD |  | ORD/000757/2022-2023 | 708/SWD-I | 23/06/2022 | 08/07/2022 | ECO CARE | 2.56 | 2.56 | 100 | 100
2 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Ground Water Based TILPI(Zone-II) Piped Water Supply Scheme to Accommodate FHTC inJAYNAGAR-I Block Under South 24 Parganas W/S Division-I, South 24 Parganas District For Augmentation of Surface Water Based Water Supply Scheme In Arsenic Affected Areas of | SM/15865 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1 & 2 Zone-II for Augmentation of Tilpi water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Jaynagar-I] | Assistant Engineer | Junior Engineer | ORD/000283/2023-2024 | 1143/SMD | 24/04/2023 | 01/07/2025 | JAL PRAVAHIKA PVT. LTD. | 21.77 | 0 | 0 | 45
3 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground Water Based TILPI(Zone-II) Piped Water Supply Scheme to Accommodate FHTC inJAYNAGAR-I Block Under South 24 Parganas W/S Division-I, South 24 Parganas District For Augmentation of Surface Water Based Water Supply Scheme In Arsenic Affected Areas of | SM/15865 | Augmentation | Construction of 2 Nos. OHR of different capacities including design and drawing of pile cap after soil investigation, Pump House cum Chlorine Room (7 nos.), Boundary Wall along with Laying of Distribution System, Rising Main, Providing Functional Household Tap Connection (FHTC) for Augmentation of TILPI (ZONE-I), TILPI (ZONE-II), KHAKURDAHA & DHOSA Mouza PWSS of JOYNAGAR-I Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. | AE BSD | JE RWS | ORD/000563/2023-2024 | 2610/SWD-I | 17/10/2023 | 30/07/2025 | GARAI INFRA PROJECT | 1193.4 | 369.23 | 30.94 | 96
4 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground Water Based TILPI(Zone-II) Piped Water Supply Scheme to Accommodate FHTC inJAYNAGAR-I Block Under South 24 Parganas W/S Division-I, South 24 Parganas District For Augmentation of Surface Water Based Water Supply Scheme In Arsenic Affected Areas of | SM/15865 | Augmentation | Sinking of 02 (Two) nos Rig bored 250mm x 150 mm dia. & 300 mtr. deep Tubewell by Rotary method for TILPI Zone-II PWSS to accommodate FHTC in Joynagar-I Block Under South 24 Parganas W/S Division-I, P.H.E Dte. for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Areas of South 24 Parganas District. (TSM/018041) | AE BSD |  | ORD/000709/2022-2023 | 3523/SWD-I | 17/03/2023 | 16/04/2023 | M/S SUNDARI CONSTRUCTION | 31.76 | 30.99 | 97.58 | 100
5 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground Water Based TILPI(Zone-II) Piped Water Supply Scheme to Accommodate FHTC inJAYNAGAR-I Block Under South 24 Parganas W/S Division-I, South 24 Parganas District For Augmentation of Surface Water Based Water Supply Scheme In Arsenic Affected Areas of | SM/15865 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000155/2023-2024 | 295/SWD-I | 25/04/2023 | 25/04/2023 | Resource Division | 40.5 | 0 | 0 | 0
6 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Ground Water Based TILPI(Zone-II) Piped Water Supply Scheme to Accommodate FHTC inJAYNAGAR-I Block Under South 24 Parganas W/S Division-I, South 24 Parganas District For Augmentation of Surface Water Based Water Supply Scheme In Arsenic Affected Areas of | SM/15865 | Augmentation | Payment of electricity bill for new service connection under SMD, PHE Dte. |  |  | BILL/01751/2023-2024 | BP-2023-24-207 | 11/08/2023 | 11/08/2023 | WBSEDCL | 7.92 | 0 | 0 | 0
7 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground Water Based TILPI(Zone-II) Piped Water Supply Scheme to Accommodate FHTC inJAYNAGAR-I Block Under South 24 Parganas W/S Division-I, South 24 Parganas District For Augmentation of Surface Water Based Water Supply Scheme In Arsenic Affected Areas of | SM/15865 | Augmentation | Construction of Platform for providing FHTC for Ground Water Based TILPI (ZONE-II) piped water supply scheme to accommodate FHTC in JOYNAGAR-I block under South 24 Parganas W/S Division-I, PHE Dte. for AUGMENTATION of surface water based water supply scheme in the Arsenic Affected Areas of South 24 Parganas District. (SM/15865) [2nd call] |  |  | ORD/000575/2024-2025 | 4274/SWD-I | 01/10/2024 | 30/11/2024 | GARAI INFRA PROJECT | 29.92 | 0 | 0 | 0
8 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground Water Based TILPI(Zone-II) Piped Water Supply Scheme to Accommodate FHTC inJAYNAGAR-I Block Under South 24 Parganas W/S Division-I, South 24 Parganas District For Augmentation of Surface Water Based Water Supply Scheme In Arsenic Affected Areas of | SM/15865 | Augmentation | Development of land, Construction of approach road and other allied works for Ground Water Based TILPI (Zone-II) Piped Water Supply Scheme to Accommodate FHTC in JAYNAGAR-I Block under South 24 Parganas W/S Division-I, South 24 Parganas District For Augmentation of Surface Water Based Water Supply Scheme In Arsenic Affected Areas of South 24 Parganas District. (SM/15865) | AE BSD | JE RWS | ORD/000404/2024-2025 | 3684/SWD-I | 22/08/2024 | 30/04/2025 | GARAI INFRA PROJECT | 43.89 | 43.57 | 99.28 | 65
9 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Ground Water Based TILPI(Zone-II) Piped Water Supply Scheme to Accommodate FHTC inJAYNAGAR-I Block Under South 24 Parganas W/S Division-I, South 24 Parganas District For Augmentation of Surface Water Based Water Supply Scheme In Arsenic Affected Areas of | SM/15865 | Augmentation | Improvement of outdoor Illumination arrangement with allied works at Pump House no-1 of Tilpi Zone-II W/S Scheme under SMD, P.H.E. Dte. (Block-Jaynagar-I) | Assistant Engineer | Junior Engineer | ORD/002350/2024-2025 | 11/SMSD | 03/01/2025 | 18/01/2025 | JAL PRAVAHIKA PVT. LTD. | 0.95 | 0 | 0 | 100
Total | [13 empty] | 1372.67 | 446.35 | 32.52