## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based BALBALIA piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Areas of Sou | SM/15866 | Augmentation | Sinking of 02 (Two) nos. Rig bored 250mm x 150mm dia. & 300 mtr. deep Tubewell having 66 mtr. housing pipe by Rotary method for BALBALIA PWSS of BARUIPUR Block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division-I, P.H.E. Dte. [TSM/017761] | AE BSD |  | ORD/000651/2022-2023 | 3323/SWD-I | 06/03/2023 | 05/04/2023 | MAHI CONSTRUCTION | 31.77 | 15.26 | 48.02 | 0
2 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based BALBALIA piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Areas of Sou | SM/15866 | Augmentation | Preparation and submission of Detailed Project Report of Ground Water Based Balbalia Piped Water Supply Scheme to accommodate FHTC in Baruipur Block under South 24-Pgs W/S Division-I, PHE Dte for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. |  |  | ORD/000946/2022-2023 | 1278/SWD-I | 13/09/2022 | 13/10/2022 | GEO SOLUTION | 2.76 | 2.7 | 97.89 | 100
3 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based BALBALIA piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Areas of Sou | SM/15866 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000118/2023-2024 | 295/SWD-I | 25/04/2023 | 25/04/2023 | Resource Division | 45.75 | 0 | 0 | 0
4 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Ground water based BALBALIA piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Areas of Sou | SM/15866 | Augmentation | Payment of electricity bill for new service connection under SMD, PHE Dte. |  |  | BILL/02285/2023-2024 | BP-2023-24-252 | 11/09/2023 | 11/09/2023 | WBSEDCL | 3.92 | 0 | 0 | 0
5 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Ground water based BALBALIA piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Areas of Sou | SM/15866 | Augmentation | Supply & Fixing main switch & Bus bar at Pump House no-1 & 2 of Balbalia W/S Scheme under SMD, P.H.E. Dte.(Block-Baruipur) | Assistant Engineer | Junior Engineer | ORD/000298/2024-2025 | 940/SMSD | 28/06/2024 | 13/07/2024 | T.S. CONSTRUCTION | 0.58 | 0 | 0 | 0
6 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Ground water based BALBALIA piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Areas of Sou | SM/15866 | Augmentation | Improvement of outdoor Illumination arrangement with allied works at Pump House no-2 of Balbalia water supply scheme under SMD, P.H.E. Dte.(Block-Baruipur) (SM/15866) | Assistant Engineer | Junior Engineer | ORD/000139/2024-2025 | 961/SMSD | 09/07/2024 | 24/07/2024 | T.S. CONSTRUCTION | 0.89 | 0 | 0 | 0
7 | SOUTH 24 PARGANAS |  | Alipore Division | Ground water based BALBALIA piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Areas of Sou | SM/15866 | Augmentation | Road restoration for 1) WB02328, L043-Sankarpur II GP Office Ie Rajgara School via Gocharan Road 2) Debipur More to Sonagachi More |  |  | BILL/01733/2024-2025 | BP-2024-25-797 | 25/10/2024 | 25/10/2024 | W.B.S.R.D.A., SOUTH TWENTY FOUR PARGANAS DIVISION | 3.96 | 0 | 0 | 0
8 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based BALBALIA piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Areas of Sou | SM/15866 | Augmentation | Construction of 350 Cum. capacity OHR (20 mtr. staging height), Boundary Wall, Pump house cum Chlorine Room along with Laying of Distribution System, Rising Main, Providing Functional Household Tap Connection (FHTC) including design and drawing of pile foundation and pile cap after soil investigation for Augmentation of BALBALIA MOUZA Piped Water Supply Scheme of BARUIPUR Block for implementation of JJM under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. [No. of FHTC = 2078] [TSM/017761] | AE BSD | JE-2 | ORD/000157/2023-2024 | 840/SWD-I | 05/06/2023 | 27/07/2025 | ASHOKA ENTERPRISE | 480.17 | 83.91 | 17.47 | 60
9 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Ground water based BALBALIA piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Areas of Sou | SM/15866 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1 &2 of Balbalia water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Baruipur] | Assistant Engineer | Junior Engineer | ORD/001126/2023-2024 | 4261/SMD | 06/11/2023 | 04/02/2024 | T.S. CONSTRUCTION | 22.2 | 0 | 0 | 40
10 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based BALBALIA piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Areas of Sou | SM/15866 | Augmentation | Construction of platform for providing FHTC, protection work for laying pipeline and other allied works for Ground water based BALBALIA piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas district. (SM/15866) | AE BSD | JE-2 | ORD/001118/2024-2025 | 154/SWD-I | 15/01/2025 | 10/01/2026 | PINKI CONSTRUCTION | 86.35 | 0 | 0 | 40
11 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Ground water based BALBALIA piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Areas of Sou | SM/15866 | Augmentation | Improvement of outdoor Illumination arrangement with allied works at Pump House no-1 of Balbalia water supply scheme under SMD, P.H.E. Dte.(Block-Baruipur) (SM/15866) | Assistant Engineer | Junior Engineer | ORD/000138/2024-2025 | 960/SMSD | 09/07/2024 | 15/12/2024 | T.S. CONSTRUCTION | 0.89 | 0 | 0 | 100
Total | [13 empty] | 679.24 | 101.86 | 15