## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based CHAK ROSANMAMUD piped water supply scheme to accommodate FHTC in BISHNUPUR-I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Ar | SM/15867 | Augmentation | Layiing Distribution System with providing Functional Household Tap Connection (FHTC) and construction of (4.80 mtr. X 3.66mtr.) Pump House with water supply and Sanitary arrangement (as per dept. drawing) of CHAK ROSANMAMUD Piped Water Supply Scheme in Bishnupur-I Block for augmentation of Surface Water based W/S Scheme in the Arsenic affected areas of South 24-Parganas District. [TSM/018431] | AE SWSD-II | JE1 | ORD/000128/2023-2024 | 588/SWD-I | 16/05/2023 | 14/08/2023 | M/S B.S. CONSTRUCTION | 118.62 | 0 | 0 | 0
2 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based CHAK ROSANMAMUD piped water supply scheme to accommodate FHTC in BISHNUPUR-I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Ar | SM/15867 | Augmentation | Preparation and submission of Detailed Project Report of Ground Water Based Chak Rasanmamud Piped Water Supply Scheme to accommodate FHTC in Bishnupur-I Block under South 24-Pgns W/S Division-I, PHE Dte for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. |  |  | ORD/000964/2022-2023 | 1164/SWD-I | 29/08/2022 | 28/09/2022 | GEO SOLUTION | 2.46 | 2.43 | 98.89 | 100
3 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based CHAK ROSANMAMUD piped water supply scheme to accommodate FHTC in BISHNUPUR-I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Ar | SM/15867 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000120/2022-2023 | 323/SWD-I | 25/04/2023 | 25/04/2023 | Resource Division | 27.73 | 0 | 0 | 0
4 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based CHAK ROSANMAMUD piped water supply scheme to accommodate FHTC in BISHNUPUR-I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Ar | SM/15867 | Augmentation | Construction of Boundary Wall & other allied works at 12 (twelve) nos. Head Work Sites of different PWSS within Bishnupur-I Block, Dist.-South 24-Parganas for Augmentation of Surface Water based Water Supply Scheme in the Arsenic Affected areas of South 24-Parganas District. | AE SWSD-II | JE1,JE2,JE4 | ORD/000209/2023-2024 | 1377/SWD-I | 12/07/2023 | 19/03/2026 | CONCORD PROJECTS PVT. LTD. | 105.47 | 0 | 0 | 60
5 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Ground water based CHAK ROSANMAMUD piped water supply scheme to accommodate FHTC in BISHNUPUR-I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Ar | SM/15867 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1 & 2 for Augmentation of Chak Rosanmamud water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Bishnupur-I] | Assistant Engineer -II | Junior Engineer | ORD/000266/2023-2024 | 1126/SMD | 24/04/2023 | 01/01/2026 | PADMA ENGINEERING CO. | 25.42 | 0 | 0 | 25
6 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based CHAK ROSANMAMUD piped water supply scheme to accommodate FHTC in BISHNUPUR-I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Ar | SM/15867 | Augmentation | Layiing Distribution System with providing Functional Household Tap Connection (FHTC) and construction of (4.80 mtr. X 3.66mtr.) Pump House with water supply and Sanitary arrangement (as per dept. drawing) of CHAK ROSANMAMUD Piped Water Supply Scheme in Bishnupur-I Block for augmentation of Surface Water based W/S Scheme in the Arsenic affected areas of South 24-Parganas District. [TSM/018431] | AE SWSD-II | JE1 | ORD/000292/2024-2025 | 3107/SWD-I | 09/07/2024 | 07/09/2024 | TIYASHA ENTERPRISE | 118.7 | 0 | 0 | 55
7 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based CHAK ROSANMAMUD piped water supply scheme to accommodate FHTC in BISHNUPUR-I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Ar | SM/15867 | Augmentation | Construction of boundary wall, approach road, pump house, land development, road restoration, additional laying of pipeline, rising main and protection work of pipeline for CHAK ROSANMAMUD PWSS to accommodate FHTC in Bishnupur-I Block under South 24-Pgns for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic Affected areas of South 24-Pgns, W/S Divn-I, PHE Dte. [SM/15867] | AE SWSD-II | JE1 | ORD/000287/2024-2025 | 3051/SWD-I | 03/07/2024 | 15/07/2025 | P ENTERPRISE | 68.52 | 0 | 0 | 55
8 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based CHAK ROSANMAMUD piped water supply scheme to accommodate FHTC in BISHNUPUR-I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Ar | SM/15867 | Augmentation | Sinking of 01 (one) no. Rig bored 250mm x 150mm dia. & 300 mtr. deep Tubewell having 66 mtr. housing pipe by Rotary method at 2nd Tubewell site for CHAK ROSANMAMUD Piped Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. District in BISHNUPUR-I Block under South 24 Pgns W/S Sub-Division-II, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs District. [SM/15867] |  |  | ORD/001192/2024-2025 | 772/SWD-I | 18/03/2025 | 17/04/2025 | SATHI ENTERPRISE | 15.88 | 0 | 0 | 0
9 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based CHAK ROSANMAMUD piped water supply scheme to accommodate FHTC in BISHNUPUR-I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Ar | SM/15867 | Augmentation | Sinking of Rig bored 250mm x 150mm dia. & 300 mtr. deep Tubewell having 66 mtr. housing pipe by Rotary method for CHAK ROSANMAMUD PWSS of BISHNUPUR-I block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs. district under South 24-Parganas W/S Division-I, P.H.E. Dte. [TSM/018431] | AE SWSD-II | JE1 | ORD/000691/2022-2023 | 3480/SWD-I | 15/03/2023 | 21/01/2025 | BARI ENTERPRISE | 15.88 | 0 | 0 | 98
10 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based CHAK ROSANMAMUD piped water supply scheme to accommodate FHTC in BISHNUPUR-I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Ar | SM/15867 | Augmentation | Supplying, Fitting & Fixing of 20 (Twenty) nos Information Boards at different locations of Bishnupur-I Block under Ground water based CHAK ROSANMAMUD piped water supply scheme to accommodate FHTC in BISHNUPUR-I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Areas of South 24 Parganas District. (SM/15867) | AE SWSD-II | JE1 | ORD/000715/2024-2025 | 4545/SWD-I | 06/11/2024 | 06/12/2024 | SRIJON ENTERPRISE | 4.72 | 0 | 0 | 98
11 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Ground water based CHAK ROSANMAMUD piped water supply scheme to accommodate FHTC in BISHNUPUR-I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Ar | SM/15867 | Augmentation | Payment of quotation for new service connection at Chak Rasanmamud PWSS, PH No-1 under Bishnupur-I Block. Application No- 1008267772 Reference Id- 106861403 Quotation Date-12/12/2024 Memo No- 1008267772/Quot/03 |  |  | BILL/02484/2024-2025 | BP-2024-25-534 | 24/01/2025 | 24/01/2025 | WBSEDCL | 3.58 | 0 | 0 | 0
Total | [13 empty] | 506.97 | 2.43 | 0.48