## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Proposed Ground water based KANTHAL BERIA piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affecte | SM/15870 | Augmentation | Preparation and submission of Detailed Project Report of Ground Water Based Kanthal Beria Piped Water Supply Scheme to accommodate FHTC in Baruipur Block under South 24-Pgs W/S Division-I, PHE Dte for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. |  |  | ORD/000939/2022-2023 | 1256/SWD-I | 09/09/2022 | 09/10/2022 | GEO SOLUTION | 2.46 | 2.45 | 99.57 | 100
2 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Proposed Ground water based KANTHAL BERIA piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affecte | SM/15870 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000124/2023-2024 | 295/SWD-I | 25/04/2023 | 25/04/2023 | Resource Division | 11.83 | 0 | 0 | 0
3 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Proposed Ground water based KANTHAL BERIA piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affecte | SM/15870 | Augmentation | Construction of platform for providing FHTC, protection for pipeline and other allied works for Ground water based KANTHAL BERIA piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District. (SM/15870) |  |  | ORD/000435/2024-2025 | 3879/SWD-I | 03/09/2024 | 02/11/2024 | SUJAN KUMAR MISTRY | 47.19 | 0 | 0 | 0
4 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Proposed Ground water based KANTHAL BERIA piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affecte | SM/15870 | Augmentation | Sinking of 02 (Two) nos. Rig bored 250mm x 150mm dia. & 300 mtr. deep Tubewell having 66 mtr. housing pipe by Rotary method for KANTHAL BERIA PWSS of BARUIPUR Block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division-I, P.H.E. Dte. [TSM/018250] | AE BSD | JE-2 | ORD/000641/2022-2023 | 3290/SWD-I | 03/03/2023 | 02/04/2023 | TAPAS KUMAR GIRI | 31.8 | 29.87 | 93.95 | 100
5 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Proposed Ground water based KANTHAL BERIA piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affecte | SM/15870 | Augmentation | Improvement of outdoor Illumination arrangement with allied works at Pump House no-2 of Kathal Beria W/S scheme under SMD, P.H.E. Dte.(Block-Baruipur) (SM/15870) | Assistant Engineer | Junior Engineer | ORD/000144/2024-2025 | 1006/SMSD | 11/07/2024 | 26/07/2024 | B.T.PROJECTS PVT.LTD. | 0.89 | 0.88 | 99.21 | 100
6 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Proposed Ground water based KANTHAL BERIA piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affecte | SM/15870 | Augmentation | Improvement of outdoor Illumination arrangement with allied works at Pump House no-1 of Kathal Beria W/S scheme under SMD, P.H.E. Dte.(Block-Baruipur) (SM/15870) | Assistant Engineer | Junior Engineer | ORD/000145/2024-2025 | 1005/SMSD | 11/07/2024 | 26/07/2024 | B.T.PROJECTS PVT.LTD. | 0.89 | 0.88 | 99.21 | 100
7 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Proposed Ground water based KANTHAL BERIA piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affecte | SM/15870 | Augmentation | Payment of electricity bill for new service connection under SMD, PHE Dte. |  |  | BILL/00124/2024-2025 | BP-2024-25-36 | 24/04/2024 | 24/04/2024 | WBSEDCL | 7.18 | 0 | 0 | 0
8 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Proposed Ground water based KANTHAL BERIA piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affecte | SM/15870 | Augmentation | Construction of Pump house cum Chlorine Room, Boundary Wall along with Laying of Distribution System, Rising Main, Providing Functional Household Tap Connection (FHTC) for KANTHALBERIA Piped Water Supply Scheme of BARUIPUR Block for implementation of JJM under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. [No. of FHTC = 634] [TSM/018250] | AE BSD | JE RWS,JE-2 | ORD/000082/2023-2024 | 416/SWD-I | 02/05/2023 | 15/08/2025 | SUJAN KUMAR MISTRY | 149.57 | 84.83 | 56.72 | 85
9 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Proposed Ground water based KANTHAL BERIA piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affecte | SM/15870 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1 & 2 of Kanthal Beria water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Baruipur] | Assistant Engineer | Junior Engineer | ORD/000087/2023-2024 | 1067/SMD | 18/04/2023 | 31/12/2024 | B.T.PROJECTS PVT.LTD. | 22.37 | 20.76 | 92.83 | 100
10 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Proposed Ground water based KANTHAL BERIA piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affecte | SM/15870 | Augmentation | Supply & installation of LED board at P.H. No-1 & 2 of KANTHALBERIA water supply scheme, under South 24-Pgs Mechanical Division PHE Dte.[Block-Baruipur][SM/15870] | Assistant Engineer | Junior Engineer | ORD/000317/2024-2025 | 1185/SMSD | 21/08/2024 | 05/09/2024 | KARTICK BAL | 0.78 | 0 | 0 | 100
11 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Proposed Ground water based KANTHAL BERIA piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affecte | SM/15870 | Augmentation | Supply & Fixing main switch & Bus bar at Pump House no-1 & 2 of Kathal beria W/S Scheme under SMD, P.H.E. Dte.(Block-Baruipur)(SM/15870) | Assistant Engineer | Junior Engineer | ORD/000214/2024-2025 | 893/SMSD | 19/06/2024 | 04/07/2024 | B.T.PROJECTS PVT.LTD. | 0.58 | 0 | 0 | 100
Total | [13 empty] | 275.51 | 139.67 | 50.7