## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Proposed Ground water based KHARUPATALIA piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected | SM/15871 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1 & 2 of Kharupatalia water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Baruipur] |  |  | ORD/001125/2023-2024 | 4260/SMD | 06/11/2023 | 04/02/2024 | JAGANNATH ENTERPRISE | 21.33 | 0 | 0 | 0
2 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Proposed Ground water based KHARUPATALIA piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected | SM/15871 | Augmentation | Preparation and submission of Detailed Project Report of Ground Water Based Kharupatalia Piped Water Supply Scheme to accommodate FHTC in Baruipur Block under South 24-Pgs W/S Division-I, PHE Dte for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. |  |  | ORD/000938/2022-2023 | 1251/SWD-I | 08/09/2022 | 08/10/2022 | GEO SOLUTION | 2.54 | 2.54 | 99.87 | 100
3 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Proposed Ground water based KHARUPATALIA piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected | SM/15871 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000125/2023-2024 | 295/SWD-I | 25/04/2023 | 25/04/2023 | Resource Division | 24.11 | 0 | 0 | 0
4 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Proposed Ground water based KHARUPATALIA piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected | SM/15871 | Augmentation | Construction of Boundary Wall, Pump house cum Chlorine Room along with Laying of Distribution System, Rising Main, Providing Functional Household Tap Connection (FHTC) for KHARUPATALIA MOUZA Piped Water Supply Scheme of BARUIPUR Block for implementation of JJM under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. [No. of FHTC = 839] [TSM/018473] | AE BSD | JE RWS Baruipur Block | ORD/000163/2023-2024 | 935/SWD-I | 06/06/2023 | 30/06/2024 | PARAMESWAR CHOWDHURY | 199.89 | 17.67 | 8.84 | 50
5 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Proposed Ground water based KHARUPATALIA piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected | SM/15871 | Augmentation | Supply & Fixing main switch & Bus bar at Pump House no-1 & 2 of Kharupatalia W/S Scheme under SMD, P.H.E. Dte.(Block-Baruipur)(SM/15871) | Assistant Engineer | Junior Engineer | ORD/000185/2025-2026 | 698/SMSD | 15/05/2025 | 30/05/2025 | JAGANNATH ENTERPRISE | 0.58 | 0 | 0 | 0
6 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Proposed Ground water based KHARUPATALIA piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected | SM/15871 | Augmentation | Improvement of outdoor Illumination arrangement with allied works at Pump House no-2 of Kharupatalia W/S Scheme under SMD, P.H.E. Dte.(Block-Baruipur)(SM/15871) | Assistant Engineer | Junior Engineer | ORD/000182/2025-2026 | 706/SMSD | 15/05/2025 | 30/05/2025 | JAGANNATH ENTERPRISE | 0.88 | 0 | 0 | 0
7 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Proposed Ground water based KHARUPATALIA piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected | SM/15871 | Augmentation | Improvement of outdoor Illumination arrangement with allied works at Pump House no-1 of Kharupatalia W/S Scheme under SMD, P.H.E. Dte.(Block-Baruipur)(SM/15871) | Assistant Engineer | Junior Engineer | ORD/000186/2025-2026 | 699/SMSD | 15/05/2025 | 30/05/2025 | JAGANNATH ENTERPRISE | 0.88 | 0 | 0 | 0
Total | [13 empty] | 250.21 | 20.2 | 8.07