## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Proposed Ground water based DHOSA piped water supply scheme to accommodate FHTC in JAYNAGAR-I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Area | SM/16117 | Augmentation | Preparation and submission of Detailed Project Report of "DHOSA Ground Water Based Piped Water Supply Scheme" in JOYNAGAR-I block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. [2nd call] |  |  | ORD/000917/2022-2023 | 706/SWD-I | 23/06/2022 | 08/07/2022 | ECO CARE | 2.56 | 0 | 0 | 100
2 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Proposed Ground water based DHOSA piped water supply scheme to accommodate FHTC in JAYNAGAR-I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Area | SM/16117 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000151/2023-2024 | 295/SWD-I | 25/04/2023 | 25/04/2023 | Resource Division | 21.79 | 0 | 0 | 0
3 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Proposed Ground water based DHOSA piped water supply scheme to accommodate FHTC in JAYNAGAR-I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Area | SM/16117 | Augmentation | Payment of electricity bill for new service connection under SMD, PHE Dte. |  |  | BILL/05025/2023-2024 | BP-2023-24-561 | 11/03/2024 | 11/03/2024 | WBSEDCL | 12.62 | 0 | 0 | 0
4 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Proposed Ground water based DHOSA piped water supply scheme to accommodate FHTC in JAYNAGAR-I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Area | SM/16117 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1 & 2, for Augmentation of Dhosa supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Jaynagar-I] | Assistant Engineer | Junior Engineer | ORD/000285/2023-2024 | 1145/SMD | 24/04/2023 | 31/12/2025 | M/S. A.K. BANERJEE | 19.1 | 0 | 0 | 50
5 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Proposed Ground water based DHOSA piped water supply scheme to accommodate FHTC in JAYNAGAR-I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Area | SM/16117 | Augmentation | Construction of 2 Nos. OHR of different capacities including design and drawing of pile cap after soil investigation, Pump House cum Chlorine Room (7 nos.), Boundary Wall along with Laying of Distribution System, Rising Main, Providing Functional Household Tap Connection (FHTC) for Augmentation of TILPI (ZONE-I), TILPI (ZONE-II), KHAKURDAHA & DHOSA Mouza PWSS of JOYNAGAR-I Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. | AE BSD | JE RWS | ORD/000563/2023-2024 | 2610/SWD-I | 17/10/2023 | 30/07/2025 | GARAI INFRA PROJECT | 1193.4 | 0 | 0 | 96
6 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Proposed Ground water based DHOSA piped water supply scheme to accommodate FHTC in JAYNAGAR-I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Area | SM/16117 | Augmentation | Sinking of 02 (Two) nos. Rig bored 250mm x 150mm dia & 360 mtr. deep Tubewell having 66 mtr. housing by Rotary method for DHOSA Piped Water Supply Scheme to accommodate FHTC in Jaynagar-I block under South 24-Pgns. W/S Division-I, South 24-Pgns. District for Augnemtation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. Dist. [SM/16117] | AE BSD | JE RWS | ORD/000809/2023-2024 | 1287/SWD-I | 15/03/2024 | 05/12/2025 | ASHIM SHIL | 38.02 | 0 | 0 | 100
7 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Proposed Ground water based DHOSA piped water supply scheme to accommodate FHTC in JAYNAGAR-I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Area | SM/16117 | Augmentation | Improvement of outdoor Illumination arrangement with allied works at Pump House no-2 of Dhosa W/S Scheme under SMD, P.H.E. Dte. (Block-Jaynagar-I) | Assistant Engineer | Junior Engineer | ORD/002996/2023-2024 | 240/SMSD | 16/02/2024 | 01/05/2025 | M/S. A.K. BANERJEE | 0.54 | 0 | 0 | 100
Total | [13 empty] | 1288.03 | 0 | 0