## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Proposed Ground water based MAHISMARI piped water supply scheme to accommodate FHTC in JAYNAGAR-I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected | SM/16125 | Augmentation | Preparation and submission of Detailed Project Report of Ground Water Based Mahishmari Piped Water Supply Scheme to accommodate FHTC in Joynagar-I Block under South 24-Pgs W/S Division-I, PHE Dte for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. |  |  | ORD/000958/2022-2023 | 1183/SWD-I | 01/09/2022 | 01/10/2022 | GEO SOLUTION | 2.76 | 0 | 0 | 100
2 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Proposed Ground water based MAHISMARI piped water supply scheme to accommodate FHTC in JAYNAGAR-I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected | SM/16125 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000115/2023-2024 | 295/SWD-I | 25/04/2023 | 25/04/2023 | Resource Division | 25.32 | 0 | 0 | 0
3 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Proposed Ground water based MAHISMARI piped water supply scheme to accommodate FHTC in JAYNAGAR-I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected | SM/16125 | Augmentation | Construction of Platform for providing FHTC, protection wall for laying pipeline, restoraton of damaged roads due to laying of pieline other allied worksand miscelleneous work for Ground water based MAHISMARI piped water supply scheme to accommodate FHTC in JOYNAGAR-I block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District. (SM/16125) (2nd call) |  |  | ORD/000772/2024-2025 | 4757/SWD-I | 21/11/2024 | 05/01/2025 | B.M. ENTERPRISE | 57.33 | 0 | 0 | 0
4 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Proposed Ground water based MAHISMARI piped water supply scheme to accommodate FHTC in JAYNAGAR-I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected | SM/16125 | Augmentation | Sinking of 02 (Two) nos Rig bored 250mm x 150 mm dia. & 300 mtr. deep Tubewell by Rotary method for MAHISMARI PWSS to Joynagar-I Block Under South 24 Parganas W/S Division-I, P.H.E Dte. for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Areas of South 24 Parganas District. (TSM/018296) | AE BSD | JE-1 | ORD/000707/2022-2023 | 3520/SWD-I | 17/03/2023 | 16/04/2023 | MALLICK CONSTRUCTION | 31.63 | 0 | 0 | 100
5 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Proposed Ground water based MAHISMARI piped water supply scheme to accommodate FHTC in JAYNAGAR-I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected | SM/16125 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1 & 2 for Augmentation of Mahismari water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Jaynagar-I] | Assistant Engineer | Junior Engineer | ORD/000286/2023-2024 | 1146/SMD | 24/04/2023 | 05/07/2026 | SARKAR ELECTRICAL | 21.77 | 0 | 0 | 45
6 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Proposed Ground water based MAHISMARI piped water supply scheme to accommodate FHTC in JAYNAGAR-I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected | SM/16125 | Augmentation | Construction of Boundary Wall, Pump house cum Chlorine Room along with Laying of Distribution System, Rising Main, Providing Functional Household Tap Connection (FHTC) for MAHISHMARI MOUZA Piped Water Supply Scheme of JAYNAGAR-I Block for implementation of JJM under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. [No. of FHTC = 1025] [TSM/018296] | AE BSD | JE-1 | ORD/000350/2023-2024 | 1736/SWD-I | 10/08/2023 | 01/05/2025 | M. MUKHERJEE | 350.46 | 0 | 0 | 40
7 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Proposed Ground water based MAHISMARI piped water supply scheme to accommodate FHTC in JAYNAGAR-I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected | SM/16125 | Augmentation | Improvement of outdoor Illumination arrangement with allied works at Pump House no-1 of Mahismari W/S Scheme under SMD, P.H.E. Dte. (Block-Jaynagar-I) (SM/16125) | Assistant Engineer | Junior Engineer | ORD/002312/2024-2025 | 382/SMSD | 18/03/2025 | 02/04/2025 | SARKAR ELECTRICAL | 0.95 | 0 | 0 | 0
Total | [13 empty] | 490.22 | 0 | 0