## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Proposed Ground water based NOR piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Areas of | SM/16126 | Augmentation | Sinking of 02 (Two) nos. Rig bored 250mm x 150mm dia. & 300 mtr. deep Tubewell having 66 mtr. housing pipe by Rotary method for NOR PWSS of BARUIPUR Block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division-I, P.H.E. Dte. [TSM/018252] | AE BSD |  | ORD/000640/2022-2023 | 3286/SWD-I | 03/03/2023 | 02/04/2023 | TAPAS KUMAR GIRI | 31.8 | 0 | 0 | 50
2 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Proposed Ground water based NOR piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Areas of | SM/16126 | Augmentation | Preparation and submission of Detailed Project Report of Ground Water Based Nor Piped Water Supply Scheme to accommodate FHTC in Baruipur Block under South 24-Pgs W/S Division-I, PHE Dte for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. |  |  | ORD/000937/2022-2023 | 1250/SWD-I | 08/09/2022 | 08/10/2022 | GEO SOLUTION | 2.45 | 0 | 0 | 100
3 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Proposed Ground water based NOR piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Areas of | SM/16126 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000126/2023-2024 | 295/SWD-I | 25/04/2023 | 25/04/2023 | Resource Division | 9.28 | 0 | 0 | 0
4 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Proposed Ground water based NOR piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Areas of | SM/16126 | Augmentation | Supply & Fixing main switch & Bus bar at Pump House no-1 & 2 of Nor W/S Scheme under SMD, P.H.E. Dte.(Block-Baruipur)(SM/16126) | Assistant Engineer | Junior Engineer | ORD/000300/2024-2025 | 927/SMSD | 28/06/2024 | 13/07/2024 | PS & ASSOCIATES | 0.58 | 0 | 0 | 0
5 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Proposed Ground water based NOR piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Areas of | SM/16126 | Augmentation | Construction of platfrom for Providing FHTC, Protection work for Pipeline, Development of Land, and other allied works for "Ground Water Based NOR Piped Water Supply Scheme to Accommodate FHTC in Baruipur Block Under South 24 Parganas W/S Division-I, PHE Dte. For Augmentation of Surface Water Based Water Supply Scheme In Arsenic Affected Areas of South 24 Parganas District." SM/16126 |  |  | ORD/000341/2024-2025 | 3315/SWD-I | 23/07/2024 | 06/09/2024 | MILAN GHOSH | 48.46 | 0 | 0 | 0
6 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Proposed Ground water based NOR piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Areas of | SM/16126 | Augmentation | Improvement of outdoor Illumination arrangement with allied works at Pump House no-2 of Nor water supply scheme under SMD, P.H.E. Dte.(Block-Baruipur) (SM/16126) | Assistant Engineer | Junior Engineer | ORD/000321/2024-2025 | 1015/SMSD | 11/07/2024 | 26/07/2024 | PS & ASSOCIATES | 0.92 | 0 | 0 | 0
7 | SOUTH 24 PARGANAS |  | Alipore Division | Proposed Ground water based NOR piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Areas of | SM/16126 | Augmentation | Road restoration of Debipur More to Sonagachi More. |  |  | BILL/01734/2024-2025 | BP-2024-25-798 | 25/10/2024 | 25/10/2024 | W.B.S.R.D.A., SOUTH TWENTY FOUR PARGANAS DIVISION | 2.46 | 0 | 0 | 0
8 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Proposed Ground water based NOR piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Areas of | SM/16126 | Augmentation | PAYMENT OF ELECTRICITY BILL FOR NEW SERVICE CONNECTION UNDER SMD PHE DTE. |  |  | BILL/04685/2023-2024 | BP-2023-24-501 | 12/02/2024 | 12/02/2024 | WBSEDCL | 15.85 | 0 | 0 | 0
9 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Proposed Ground water based NOR piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Areas of | SM/16126 | Augmentation | Construction of Pump house cum Chlorine Room, Boundary Wall along with Laying of Distribution System, Rising Main, Providing Functional Household Tap Connection (FHTC) for NOR MOUZA Piped Water Supply Scheme of BARUIPUR Block for implementation of JJM under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. [No. of FHTC = 668] [TSM/018252] | AE BSD | JE-1 | ORD/000168/2023-2024 | 965/SWD-I | 08/06/2023 | 26/03/2025 | M/S B.N. ENTERPRISE | 140.38 | 0 | 0 | 60
10 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Proposed Ground water based NOR piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Areas of | SM/16126 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with neither neither allied accessories at P.H. 1 & 2 of Nor water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Baruipur] | Assistant Engineer | Junior Engineer | ORD/001624/2023-2024 | 4214/SMD | 31/10/2023 | 01/04/2026 | PS & ASSOCIATES | 25.9 | 0 | 0 | 40
11 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Proposed Ground water based NOR piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Areas of | SM/16126 | Augmentation | Improvement of outdoor Illumination arrangement with allied works at Pump House no-1 of Nor water supply scheme under SMD, P.H.E. Dte.(Block-Baruipur) (SM/16126) | Assistant Engineer | Junior Engineer | ORD/000303/2024-2025 | 1008/SMSD | 11/07/2024 | 01/01/2026 | PS & ASSOCIATES | 0.92 | 0 | 0 | 100
Total | [13 empty] | 279 | 0 | 0