## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Proposed Ground water based RAJPUR KORABAG piped water supply scheme to accommodate FHTC in JAYNAGAR-I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affe | SM/16131 | Augmentation | Preparation and submission of Detailed Project Report of Ground Water Based Rajpur Korabag Piped Water Supply Scheme to accommodate FHTC in Joynagar-I Block under South 24-Pgs W/S Division-I, PHE Dte for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. |  |  | ORD/000957/2022-2023 | 1307/SWD-I | 14/09/2022 | 14/10/2022 | GEO SOLUTION | 2.64 | 2.62 | 99.17 | 100
2 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Proposed Ground water based RAJPUR KORABAG piped water supply scheme to accommodate FHTC in JAYNAGAR-I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affe | SM/16131 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1 & 2 for Augmentation of Rajpur Korabag water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Jaynagar-I] | Assistant Engineer | Junior Engineer | ORD/000284/2023-2024 | 1144/SMD | 24/04/2023 | 23/07/2025 | M/S.UTTAM KUMAR CHATTERJEE | 21.6 | 0 | 0 | 90
3 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Proposed Ground water based RAJPUR KORABAG piped water supply scheme to accommodate FHTC in JAYNAGAR-I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affe | SM/16131 | Augmentation | Construction of 250 Cum. capacity OHR (20 mtr. staging height), Boundary Wall, Pump house cum Chlorine Room along with Laying of Distribution System, Rising Main, Providing Functional Household Tap Connection (FHTC) including design and drawing of pile foundation and pile cap after soil investigation for Augmentation of RAJPUR KORABEG MOUZA Piped Water Supply Scheme of JOYNAGAR-I Block for implementation of JJM under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. [No. of FHTC = 1692] [TSM/018299] | AE BSD | JE-2 | ORD/000361/2023-2024 | 1766/SWD-I | 10/08/2023 | 26/01/2026 | EQUIPMENTS AND SPARES AGENCIES | 411.03 | 154.74 | 37.65 | 45
4 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Proposed Ground water based RAJPUR KORABAG piped water supply scheme to accommodate FHTC in JAYNAGAR-I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affe | SM/16131 | Augmentation | Sinking of 02 (Two) nos Rig bored 250mm x 150 mm dia. & 300 mtr. deep Tubewell by Rotary method for RAJPUR KORABEG PWSS to accommodate FHTC in Joynagar-I Block Under South 24 Parganas W/S Division-I, P.H.E Dte. for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Areas of South 24 Parganas District. (TSM/018299) | AE BSD | JE-2 | ORD/000705/2022-2023 | 3514/SWD-I | 17/03/2023 | 16/04/2023 | SOURAV GHOSH | 31.75 | 31.09 | 97.94 | 5
5 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Proposed Ground water based RAJPUR KORABAG piped water supply scheme to accommodate FHTC in JAYNAGAR-I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affe | SM/16131 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000116/2023-2024 | 295/SWD-I | 25/04/2023 | 25/04/2023 | Resource Division | 32.75 | 0 | 0 | 0
6 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Proposed Ground water based RAJPUR KORABAG piped water supply scheme to accommodate FHTC in JAYNAGAR-I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affe | SM/16131 | Augmentation | Construction of Platform and for providing FHTC , protection wall for laying pipeline and other allied works for Ground water based RAJPUR KORABAG piped water supply scheme to accommodate FHTC in JOYNAGAR-I block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District. (SM/16131) (2nd call) |  |  | ORD/000738/2024-2025 | 4636/SWD-I | 14/11/2024 | 29/12/2024 | EQUIPMENTS AND SPARES AGENCIES | 71.4 | 0 | 0 | 0
7 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Proposed Ground water based RAJPUR KORABAG piped water supply scheme to accommodate FHTC in JAYNAGAR-I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affe | SM/16131 | Augmentation | Payment of electricity bill for new service connection under SMD, PHE Dte. |  |  | BILL/05031/2023-2024 | BP-2023-24-560 | 11/03/2024 | 11/03/2024 | WBSEDCL | 6.04 | 0 | 0 | 0
8 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Proposed Ground water based RAJPUR KORABAG piped water supply scheme to accommodate FHTC in JAYNAGAR-I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affe | SM/16131 | Augmentation | Improvement of outdoor Illumination arrangement with allied works at Pump House no-2 of Rajpur Korabag W/S Scheme under SMD, P.H.E. Dte. (Block-Jaynagar-I) (SM/16131) | Assistant Engineer | Junior Engineer | ORD/001240/2025-2026 | 739-1/SMSD | 21/05/2025 | 05/06/2025 | M/S.UTTAM KUMAR CHATTERJEE | 0.82 | 0 | 0 | 0
9 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Proposed Ground water based RAJPUR KORABAG piped water supply scheme to accommodate FHTC in JAYNAGAR-I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affe | SM/16131 | Augmentation | Improvement of outdoor Illumination arrangement with allied works at Pump House no-1 of Rajpur Korabag W/S Scheme under SMD, P.H.E. Dte. (Block-Jaynagar-I) (SM/16131) | Assistant Engineer | Junior Engineer | ORD/001239/2025-2026 | 739/SMSD | 21/05/2025 | 05/06/2025 | M/S.UTTAM KUMAR CHATTERJEE | 0.82 | 0 | 0 | 0
Total | [13 empty] | 578.84 | 188.45 | 32.56