## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Proposed Ground water based RANA piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Areas o | SM/16132 | Augmentation | Preparation and submission of Detailed Project Report of Ground Water Based Rana Piped Water Supply Scheme to accommodate FHTC in Baruipur Block under South 24-Pgs W/S Division-I, PHE Dte for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. |  |  | ORD/000934/2022-2023 | 1226/SWD-I | 06/09/2022 | 06/10/2022 | GEO SOLUTION | 2.54 | 2.5 | 98.57 | 100
2 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Proposed Ground water based RANA piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Areas o | SM/16132 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000128/2023-2024 | 295/SWD-I | 25/04/2023 | 25/04/2023 | Resource Division | 11.59 | 0 | 0 | 0
3 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Proposed Ground water based RANA piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Areas o | SM/16132 | Augmentation | Payment of electricity bill for new service connection under SMD, PHE Dte. |  |  | BILL/01507/2023-2024 | BP-2023-24-172 | 02/08/2023 | 02/08/2023 | WBSEDCL | 2.56 | 0 | 0 | 0
4 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Proposed Ground water based RANA piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Areas o | SM/16132 | Augmentation | Payment of electricity bill for new service connection under SMD, PHE Dte. |  |  | BILL/03276/2023-2024 | BP-2023-24-366 | 04/11/2023 | 04/11/2023 | WBSEDCL | 10.38 | 0 | 0 | 0
5 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Proposed Ground water based RANA piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Areas o | SM/16132 | Augmentation | Sinking of 02 (Two) nos. Rig bored 250mm x 150mm dia. & 300 mtr. deep Tubewell having 66 mtr. housing pipe by Rotary method for RANA PWSS of BARUIPUR Block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division-I, P.H.E. Dte. [TSM/018248] | AE BSD | JE-2 | ORD/000644/2022-2023 | 3285/SWD-I | 03/03/2023 | 02/04/2023 | M/S SYCHROTECH INDUSTRY | 31.11 | 29.07 | 93.43 | 100
6 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Proposed Ground water based RANA piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Areas o | SM/16132 | Augmentation | Construction of Pump house cum Chlorine Room, Boundary Wall along with Laying of Distribution System, Rising Main, Providing Functional Household Tap Connection (FHTC) for RANA Piped Water Supply Scheme of BARUIPUR Block for implementation of JJM under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. [No. of FHTC = 998] [TSM/018248] | AE BSD | JE RWS | ORD/000440/2023-2024 | 2090/SWD-I | 29/08/2023 | 27/11/2023 | MS BUILDWELL | 181.82 | 69.68 | 38.33 | 80
7 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Proposed Ground water based RANA piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Areas o | SM/16132 | Augmentation | Construction of platfrom for FHTC, restoration of road after laying of Pipeline, Land devolopment and other allied works for "Ground Water Based RANA Piped Water Supply Scheme to Accommodate FHTC in BARUIPUR Block Under South 24 Parganas W/S Division-I, PHE Dte. For Augmentation of Surface Water Based Water Supply Scheme In Arsenic Affected Areas of South 24 Parganas District." (SM/16132) | AE BSD | JE RWS | ORD/000334/2024-2025 | 3272/SWD-I | 22/07/2024 | 05/09/2024 | BAIDYA ENTERPRISE | 91.55 | 10 | 10.93 | 25
8 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Proposed Ground water based RANA piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Areas o | SM/16132 | Augmentation | Supply & installation of LED board at P.H. No-1 & 2 of Sankharipur water supply scheme, under South 24-Pgs Mechanical Division PHE Dte.[Block-Baruipur] | Assistant Engineer | Junior Engineer | ORD/002105/2024-2025 | 389/SMSD | 19/03/2025 | 09/04/2025 | NEW RANBEE ENGINEERING | 0.79 | 0 | 0 | 0
9 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Proposed Ground water based RANA piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Areas o | SM/16132 | Augmentation | Supply & installation of LED board at P.H. No-1 & 2 of Rana water supply scheme, under South 24-Pgs Mechanical Division PHE Dte.[Block-Baruipur] | Assistant Engineer | Junior Engineer | ORD/002347/2024-2025 | 388/SMSD | 19/03/2025 | 09/04/2025 | KARTICK BAL | 0.79 | 0 | 0 | 0
10 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Proposed Ground water based RANA piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Areas o | SM/16132 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1 & 2 Zone-I of Rana water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Baruipur] | Assistant Engineer | Junior Engineer | ORD/000093/2023-2024 | 1091/SMD | 18/04/2023 | 01/05/2025 | SHIVAM ENTERPRISE | 21.76 | 1.92 | 8.83 | 100
11 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Proposed Ground water based RANA piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Areas o | SM/16132 | Augmentation | Improvement of outdoor Illumination arrangement with allied works at Pump House no-1 of Rana W/S Scheme under SMD, P.H.E. Dte.(Block-Baruipur)(SM/16132) | Assistant Engineer | Junior Engineer | ORD/001220/2024-2025 | 1656/SMSD | 13/12/2024 | 28/12/2024 | SHIVAM ENTERPRISE | 0.91 | 0 | 0 | 100
12 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Proposed Ground water based RANA piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Areas o | SM/16132 | Augmentation | Supply & Fixing main switch & Bus bar at Pump House no-1 & 2 of Rana W/S Scheme under SMD, P.H.E. Dte.(Block-Baruipur)(SM/16132) | Assistant Engineer | Junior Engineer | ORD/001225/2024-2025 | 1655/SMSD | 13/12/2024 | 28/12/2024 | SHIVAM ENTERPRISE | 0.87 | 0 | 0 | 67
13 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Proposed Ground water based RANA piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Areas o | SM/16132 | Augmentation | Supply & Fixing main switch & Bus bar at Pump House no-1 of Sankharipur W/S Scheme under SMD, P.H.E. Dte.(Block-Baruipur) | Assistant Engineer | Junior Engineer | ORD/001528/2024-2025 | 1712/SMSD | 27/12/2024 | 11/01/2025 | A.G.ENTERPRISE | 0.29 | 0 | 0 | 100
14 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Proposed Ground water based RANA piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Areas o | SM/16132 | Augmentation | Improvement of outdoor Illumination arrangement with allied works at Pump House no-2 of Rana W/S Scheme under SMD, P.H.E. Dte.(Block-Baruipur)(SM/16132) | Assistant Engineer | Junior Engineer | ORD/001218/2024-2025 | 1657/SMSD | 13/12/2024 | 28/12/2024 | SHIVAM ENTERPRISE | 0.91 | 0 | 0 | 100
15 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Proposed Ground water based RANA piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Areas o | SM/16132 | Augmentation | Improvement of outdoor Illumination arrangement with allied works at Pump House no-1 of Sankharipur W/S Scheme under SMD, P.H.E. Dte.(Block-Baruipur) | Assistant Engineer | Junior Engineer | ORD/001527/2024-2025 | 1713/SMSD | 27/12/2024 | 11/01/2025 | A.G.ENTERPRISE | 0.96 | 0 | 0 | 100
16 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Proposed Ground water based RANA piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Areas o | SM/16132 | Augmentation | Improvement of outdoor Illumination arrangement with allied works at Pump House no-2 of Sankharipur W/S Scheme under SMD, P.H.E. Dte.(Block-Baruipur) | Assistant Engineer | Junior Engineer | ORD/002146/2024-2025 | 1729/SMSD | 27/12/2024 | 11/01/2025 | SHRESTHA | 0.99 | 0 | 0 | 100
17 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Proposed Ground water based RANA piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Areas o | SM/16132 | Augmentation | Supply & Fixing main switch & Bus bar at Pump House no-2 of Sankharipur W/S Scheme under SMD, P.H.E. Dte.(Block-Baruipur) | Assistant Engineer | Junior Engineer | ORD/002147/2024-2025 | 1730/SMSD | 27/12/2024 | 11/01/2025 | SHRESTHA | 0.29 | 0 | 0 | 100
Total | [13 empty] | 360.12 | 113.18 | 31.43