## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Proposed Ground water based RATANPUR piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Are | SM/16133 | Augmentation | Preparation and submission of Detailed Project Report of Ground Water Based Rantanpur Piped Water Supply Scheme to accommodate FHTC in Baruipur Block under South 24-Pgs W/S Division-I, PHE Dte for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. |  |  | ORD/000933/2022-2023 | 1225/SWD-I | 06/09/2022 | 06/10/2022 | GEO SOLUTION | 2.54 | 2.5 | 98.32 | 100
2 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Proposed Ground water based RATANPUR piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Are | SM/16133 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000133/2023-2024 | 295/SWD-I | 25/04/2023 | 25/04/2023 | Resource Division | 25.6 | 0 | 0 | 0
3 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Proposed Ground water based RATANPUR piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Are | SM/16133 | Augmentation | Sinking of 02 (Two) nos. Rig bored 250mm x 150mm dia. & 300 mtr. deep Tubewell having 66 mtr. housing pipe by Rotary method for RATANPUR PWSS of BARUIPUR Block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24- Parganas W/S Division-I, P.H.E. Dte. [TSM/017962] | AE BSD | JE-1 | ORD/000647/2022-2023 | 3319/SWD-I | 06/03/2023 | 05/04/2023 | M/S SABITA ENTERPRISE | 31.72 | 14.83 | 46.76 | 50
4 | SOUTH 24 PARGANAS |  | Alipore Division | Proposed Ground water based RATANPUR piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Are | SM/16133 | Augmentation | Road restoration for 1) WB02435, L046-Mirpur on L045 to Ratanpur 2) WB02328, L043-Sankarpur II GP Office Ie Rajgara School via Gocharan Road |  |  | BILL/01669/2024-2025 | BP-2024-25-776 | 25/10/2024 | 25/10/2024 | W.B.S.R.D.A., SOUTH TWENTY FOUR PARGANAS DIVISION | 2.74 | 0 | 0 | 0
5 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Proposed Ground water based RATANPUR piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Are | SM/16133 | Augmentation | Construction of Boundary Wall, Pump house cum Chlorine Room along with Laying of Distribution System, Rising Main, Providing Functional Household Tap Connection (FHTC) for RATANPUR MOUZA Piped Water Supply Scheme of BARUIPUR Block for implementation of JJM under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. [No. of FHTC = 1004] [TSM/017962]. | AE BSD | JE-1 | ORD/000100/2023-2024 | 470/SWD-I | 04/05/2023 | 23/04/2025 | M. MUKHERJEE | 187.27 | 122.14 | 65.22 | 90
6 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Proposed Ground water based RATANPUR piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Are | SM/16133 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1 & 2 of Ratanpur water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Baruipur] | Assistant Engineer | Junior Engineer | ORD/000094/2023-2024 | 1092/SMD | 18/04/2023 | 02/07/2025 | SHIVAM ENTERPRISE | 21.75 | 0 | 0 | 40
7 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Proposed Ground water based RATANPUR piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Are | SM/16133 | Augmentation | Improvement of outdoor Illumination arrangement with allied works at Pump House no-2 of Ratanpur W/S Scheme under SMD, P.H.E. Dte.(Block-Baruipur)(SM/16133) | Assistant Engineer | Junior Engineer | ORD/001223/2024-2025 | 87/SMSD | 17/01/2025 | 01/02/2025 | SHIVAM ENTERPRISE | 0.91 | 0 | 0 | 0
8 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Proposed Ground water based RATANPUR piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Are | SM/16133 | Augmentation | Supply & Fixing main switch & Bus bar at Pump House no-1 & 2 of Ratanpur W/S Scheme under SMD, P.H.E. Dte.(Block-Baruipur)(SM/16133) | Assistant Engineer | Junior Engineer | ORD/001224/2024-2025 | 85/SMSD | 17/01/2025 | 01/02/2025 | SHIVAM ENTERPRISE | 0.58 | 0 | 0 | 0
9 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Proposed Ground water based RATANPUR piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Are | SM/16133 | Augmentation | Construction of boundary wall, protection work for pipeline, approach road, development of land and other allied works for Ground water based RATANPUR piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas district.(SM/16133) | AE BSD |  | ORD/000223/2024-2025 | 2641/SWD-I | 07/06/2024 | 13/01/2026 | SUPER CONSTRUCTION | 41.68 | 0 | 0 | 50
10 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Proposed Ground water based RATANPUR piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Are | SM/16133 | Augmentation | Improvement of outdoor Illumination arrangement with allied works at Pump House no-1 of Ratanpur W/S Scheme under SMD, P.H.E. Dte.(Block-Baruipur)(SM/16133) | Assistant Engineer | Junior Engineer | ORD/001221/2024-2025 | 86/SMSD | 17/01/2025 | 01/02/2025 | SHIVAM ENTERPRISE | 0.91 | 0 | 0 | 100
11 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Proposed Ground water based RATANPUR piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Are | SM/16133 | Augmentation | Charges for new service connection at pump house no-1 of Ratanpur water supply scheme(Baruipur Block) |  |  | BILL/02419/2024-2025 | BP-2024-25-514 | 10/01/2025 | 10/01/2025 | WBSEDCL | 6.98 | 0 | 0 | 0
Total | [13 empty] | 322.69 | 139.47 | 43.22