## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Proposed Ground water based SURJAPUR piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Are | SM/16135 | Augmentation | Construction of boundary wall (Two nos) for SURJAPUR PWSS of Baruipur block, under Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24 Paraganas district under South 24 Pgns. W/S Divn-I, PHE, Dte. (TSM/018700) [Length - 50.0 mtr.] (Tube Well site-1 & 2) | AE BSD |  | ORD/000089/2023-2024 | 442/SWD-I | 03/05/2023 | 02/07/2023 | B.M. TRADERS | 13.85 | 0 | 0 | 0
2 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Proposed Ground water based SURJAPUR piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Are | SM/16135 | Augmentation | Preparation and submission of Detailed Project Report of Ground Water Based Surjapur Piped Water Supply Scheme to accommodate FHTC in Baruipur Block under South 24-Pgs W/S Division-I, PHE Dte for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. |  |  | ORD/000928/2022-2023 | 1180/SWD-I | 01/09/2022 | 01/10/2022 | GEO SOLUTION | 2.36 | 2.36 | 99.82 | 100
3 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Proposed Ground water based SURJAPUR piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Are | SM/16135 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000261/2023-2024 | 2428/SWD-I | 30/09/2023 | 30/09/2023 | Resource Division | 22.03 | 0 | 0 | 0
4 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Proposed Ground water based SURJAPUR piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Are | SM/16135 | Augmentation | Payment of electricity bill for new service connection under SMD, PHE Dte. |  |  | BILL/00020/2023-2024 | BP-2023-24-30 | 18/05/2023 | 18/05/2023 | WBSEDCL | 2.57 | 0 | 0 | 0
5 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Proposed Ground water based SURJAPUR piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Are | SM/16135 | Augmentation | Payment of electricity bill for new service connection under SMD, PHE Dte. |  |  | BILL/02283/2023-2024 | BP-2023-24-251 | 11/09/2023 | 11/09/2023 | WBSEDCL | 7.94 | 0 | 0 | 0
6 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Proposed Ground water based SURJAPUR piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Are | SM/16135 | Augmentation | Sinking of 02 (Two) nos. Rig bored 250mm x 150mm dia. & 300 mtr. deep Tubewell having 66 mtr. housing pipe by Rotary method for SURJAPUR PWSS of BARUIPUR Block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division-I, P.H.E. Dte. [TSM/018700] | AE BSD | JE-2 | ORD/000653/2022-2023 | 3350/SWD-I | 09/03/2023 | 08/04/2023 | TAPAS KUMAR GIRI | 31.8 | 29.86 | 93.9 | 100
7 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Proposed Ground water based SURJAPUR piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Are | SM/16135 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000330/2023-2024 | 268/SWD-I | 10/01/2024 | 10/01/2024 | Resource Division | 2.14 | 0 | 0 | 0
8 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Proposed Ground water based SURJAPUR piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Are | SM/16135 | Augmentation | Laying distribution system, Rising main,including Funtional Household Tap connection(FHTC) for SURJAPUR piped water supply scheme of BARUIPUR Block, under augmentation of surface water based W/S scheme in the arsenic affected areas of South 24 Parganas district under South 24 Pgns. W/S Division-I, P.H.E Dte. (TSM/018700) | AE BSD | JE RWS Baruipur Block | ORD/000087/2023-2024 | 347/SWD-I | 26/04/2023 | 01/03/2025 | BAIDYA ENTERPRISE | 53.26 | 42.68 | 80.13 | 76
9 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Proposed Ground water based SURJAPUR piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Are | SM/16135 | Augmentation | Construction of Pump house cum chlorination room (Two nos) for SURJAPUR PWSS of Baruipur Block under Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district under South 24 Pgns W/S Division-I, PHE, Dte. (TSM/018700) | AE BSD | JE RWS Baruipur Block | ORD/000126/2023-2024 | 569/SWD-I | 15/05/2023 | 14/07/2023 | BINAPANI ENTERPRISE | 11.28 | 0 | 0 | 100
10 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Proposed Ground water based SURJAPUR piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Are | SM/16135 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1 & 2 of Surjapur water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Baruipur] | Assistant Engineer | Junior Engineer | ORD/000096/2023-2024 | 1094/SMD | 18/04/2023 | 30/07/2025 | JAI BHARAT COMMERCIAL CORPORATION | 21.77 | 7.51 | 34.51 | 100
11 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Proposed Ground water based SURJAPUR piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Are | SM/16135 | Augmentation | Improvement of outdoor Illumination arrangement with allied works at Pump House no-1 of Surjapur water supply scheme under SMD, P.H.E. Dte.(Block-Baruipur) (SM/16135) | Assistant Engineer | Junior Engineer | ORD/000116/2024-2025 | 488/SMSD | 23/04/2024 | 01/06/2025 | JAI BHARAT COMMERCIAL CORPORATION | 0.89 | 0 | 0 | 100
12 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Proposed Ground water based SURJAPUR piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Are | SM/16135 | Augmentation | Supply & Fixing main switch & Bus bar at Pump House no-1 & 2 of Surjapur W/S Scheme under SMD, P.H.E. Dte.(Block-Baruipur)(SM/16135) | Assistant Engineer | Junior Engineer | ORD/000118/2024-2025 | 487/SMSD | 23/04/2024 | 01/06/2025 | JAI BHARAT COMMERCIAL CORPORATION | 0.84 | 0 | 0 | 100
13 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Proposed Ground water based SURJAPUR piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Are | SM/16135 | Augmentation | Improvement of outdoor Illumination arrangement with allied works at Pump House no-2 of Surjapur water supply scheme under SMD, P.H.E. Dte.(Block-Baruipur) (SM/16135) | Assistant Engineer | Junior Engineer | ORD/000117/2024-2025 | 489/SMSM | 23/04/2024 | 01/06/2025 | JAI BHARAT COMMERCIAL CORPORATION | 0.89 | 0 | 0 | 100
14 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Proposed Ground water based SURJAPUR piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Are | SM/16135 | Augmentation | Supply & installation of LED board at P.H. No-1 & 2 of Surjapur water supply scheme, under South 24-Pgs Mechanical Division PHE Dte.[Block-Baruipur] | Assistant Engineer | Junior Engineer | ORD/000021/2025-2026 | 536/SMSD | 09/04/2025 | 30/04/2025 | MONOSEBA CONSTRUCTION | 0.79 | 0 | 0 | 100
15 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Proposed Ground water based SURJAPUR piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Are | SM/16135 | Augmentation | Charges for new service connection at pump house no-II of Surjapur water supply scheme (Baruipur Block) |  |  | BILL/02413/2024-2025 | BP-2024-25-513 | 10/01/2025 | 10/01/2025 | WBSEDCL | 7.44 | 0 | 0 | 0
Total | [13 empty] | 179.86 | 82.41 | 45.82