## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | Proposed Ground water based TEKA piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Areas o | SM/16137 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000129/2023-2024 | 295/SWD-I | 25/04/2023 |  | Resource Division | 26.12 | 0 | 0 | 0
2 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Proposed Ground water based TEKA piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Areas o | SM/16137 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1 & 2 of Teka water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Baruipur] | Assistant Engineer | Junior Engineer | ORD/000097/2023-2024 | 1095/SMD | 18/04/2023 | 17/07/2023 | JAI BHARAT COMMERCIAL CORPORATION | 21.77 | 0 | 0 | 0
3 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | Proposed Ground water based TEKA piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Areas o | SM/16137 | Augmentation | Preparation and submission of Detailed Project Report of Ground Water Based Teka Piped Water Supply Scheme to accommodate FHTC in Baruipur Block under South 24-Pgs W/S Division-I, PHE Dte for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. |  |  | ORD/000931/2022-2023 | 1222/SWD-I | 05/09/2022 | 05/10/2022 | GEO SOLUTION | 2.47 | 1.23 | 49.92 | 100
4 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | Proposed Ground water based TEKA piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Areas o | SM/16137 | Augmentation | Sinking of 02 (Two) nos. Rig bored 250mm x 150mm dia. & 300 mtr. deep Tubewell having 66 mtr. housing pipe by Rotary method for TEKA PWSS of BARUIPUR Block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division-I, P.H.E. Dte. [TSM/017759] | AE BSD | JE RWS | ORD/000646/2022-2023 | 3318/SWD-I | 06/03/2023 | 05/04/2023 | SUMAN ENTERPRISE | 31.72 | 7.74 | 24.39 | 50
5 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | Proposed Ground water based TEKA piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Areas o | SM/16137 | Augmentation | Construction of Pump house cum Chlorine Room, Boundary Wall along with Laying of Distribution System, Rising Main, Providing Functional Household Tap Connection (FHTC) for Augmentation of TEKA MOUZA Piped Water Supply Scheme of BARUIPUR Block for implementation of JJM under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. [No. of FHTC = 853] [TSM/017759] | AE BSD | JE RWS | ORD/000162/2023-2024 | 933/SWD-I | 06/06/2023 | 04/09/2023 | A.K. INDUSTRIES | 159.51 | 37.76 | 23.67 | 70
6 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Proposed Ground water based TEKA piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Areas o | SM/16137 | Augmentation | Payment of electricity bill for new service connection under SMD, PHE Dte. |  |  | BILL/05120/2023-2024 | BP-2023-24-576 | 12/03/2024 |  | WBSEDCL | 7.95 | 0 | 0 | 0
7 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Proposed Ground water based TEKA piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Areas o | SM/16137 | Augmentation | Payment of electricity bill for new service connection under SMD, PHE Dte. |  |  | BILL/05120/2023-2024 | BP-2023-24-576 | 12/03/2024 |  | WBSEDCL | 7.95 | 0 | 0 | 0
8 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Proposed Ground water based TEKA piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Areas o | SM/16137 | Augmentation | Improvement of outdoor Illumination arrangement with allied works at Pump House no-2 of Teka W/S scheme under SMD, P.H.E. Dte.(Block-Baruipur) (SM/16137) | Assistant Engineer | Junior Engineer | ORD/000274/2024-2025 | 1002/SMSD | 11/07/2024 | 26/07/2024 | JAI BHARAT COMMERCIAL CORPORATION | 0.89 | 0 | 0 | 0
9 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Proposed Ground water based TEKA piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Areas o | SM/16137 | Augmentation | Improvement of outdoor Illumination arrangement with allied works at Pump House no-1 of Teka W/S scheme under SMD, P.H.E. Dte.(Block-Baruipur) (SM/16137) | Assistant Engineer | Junior Engineer | ORD/000275/2024-2025 | 1001/SMSD | 11/07/2024 | 26/07/2024 | JAI BHARAT COMMERCIAL CORPORATION | 0.89 | 0 | 0 | 0
10 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Proposed Ground water based TEKA piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Areas o | SM/16137 | Augmentation | Supply & Fixing main switch & Bus bar at Pump House no-1 & 2 of Teka W/S Scheme under SMD, P.H.E. Dte.(Block-Baruipur)(SM/16137) | Assistant Engineer | Junior Engineer | ORD/000293/2024-2025 | 891/SMSD | 19/06/2024 | 04/07/2024 | JAI BHARAT COMMERCIAL CORPORATION | 0.84 | 0 | 0 | 0
Total | [13 empty] | 260.1 | 46.72 | 17.96