## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Augmentation of laying distribution system to extend the benefit of 100% Household in ZONE-VII at JOYNAGAR-II block within Mega surface water based water supply scheme of Falta-Mathurapur dist.- South 24 pgns. Under south 24 pgns water supply division-I, | SM/16183 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000209/2023-2024 | 382/SWD-I | 27/04/2023 | 27/04/2023 | Resource Division | 163.2 | 0 | 0 | 0
2 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Augmentation of laying distribution system to extend the benefit of 100% Household in ZONE-VII at JOYNAGAR-II block within Mega surface water based water supply scheme of Falta-Mathurapur dist.- South 24 pgns. Under south 24 pgns water supply division-I, | SM/16183 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000298/2023-2024 | 2435/SWD-I | 30/09/2023 | 30/09/2023 | Resource Division | 297.49 | 0 | 0 | 0
3 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Augmentation of laying distribution system to extend the benefit of 100% Household in ZONE-VII at JOYNAGAR-II block within Mega surface water based water supply scheme of Falta-Mathurapur dist.- South 24 pgns. Under south 24 pgns water supply division-I, | SM/16183 | Augmentation | Construction of 1250 Cum. capacity OHR (20 mtr. staging height) along with Laying of Distribution System, Rising Main, Providing Functional Household Tap Connection (FHTC) including design and drawing of pile foundation and pile cap after soil investigation for Augmentation of ZONE-VII NOLGORA MOUZA Piped Water Supply Scheme of JOYNAGAR-II Block for implementation of JJM under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. [No. of FHTC = 11912] [TSM/011554] and [TSM/015335] 124076810.5 | AE BSD | JE RWS | ORD/000260/2023-2024 | 1515/SWD-I | 21/07/2023 | 31/12/2025 | MRA NIRMAN UDYOG | 1590.17 | 0 | 0 | 65
4 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Augmentation of laying distribution system to extend the benefit of 100% Household in ZONE-VII at JOYNAGAR-II block within Mega surface water based water supply scheme of Falta-Mathurapur dist.- South 24 pgns. Under south 24 pgns water supply division-I, | SM/16183 | Augmentation | Additional work for Laying distribution system at Zone-VII (NOLGORA) of JOYNAGAR-II Block, for implementation of JJM under augmentation of surface water based W/S scheme in the arsenic affected areas of South 24 Parganas district under Baruipur sub Division of South 24 Pgns. W/S Division-I, P.H.E Dte.(SM/ 11770 , SM/16183) | AE BSD | JE RWS | ORD/000364/2024-2025 | 3511/SWD-I | 07/08/2024 | 30/06/2025 | MRA NIRMAN UDYOG | 434.23 | 0 | 0 | 40
5 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Augmentation of laying distribution system to extend the benefit of 100% Household in ZONE-VII at JOYNAGAR-II block within Mega surface water based water supply scheme of Falta-Mathurapur dist.- South 24 pgns. Under south 24 pgns water supply division-I, | SM/16183 | Augmentation | Construction of Boundary wall for proposed OHR Site at Nolgora Mouza , JL No.145, Khatian No. 1361, Plot No. 3932; within Joynagar-II block, under Mega Surface Water Based Water Supply Secheme for Falta-Mathurapur , Dist. South 24 Paraganas. [Length - 140.0 mtr.] | AE BSD | JE RWS,JE-2 | ORD/000595/2021-2022 | 1580/SWD-I | 27/12/2021 | 07/09/2025 | M/S. KALPANA CONSTRUCTION | 25.11 | 0 | 0 | 100
6 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Augmentation of laying distribution system to extend the benefit of 100% Household in ZONE-VII at JOYNAGAR-II block within Mega surface water based water supply scheme of Falta-Mathurapur dist.- South 24 pgns. Under south 24 pgns water supply division-I, | SM/16183 | Augmentation | Additional laying & allied works from Ghatarnia to Nolgora of Secondary Grid pipeline for Nolgora of Joynagar-II Block within Mega surface water based water supply scheme of Falta Mathurapur under "Augmentation of laying distribution system to extend the benefit of 100% Households in ZONE-VII at JOYNAGAR-II block within Mega surface water based water supply scheme for Falta-Mathurapur dist.- South 24 pgns. Under South 24 Pgns W/S Division-I, PHE Dte." (SM/16183) | AE BSD | JE-2 | ORD/000074/2025-2026 | 1577/SWD-I | 11/06/2025 | 26/07/2025 | ARASTA ENGINEERING & CO | 48.34 | 0 | 0 | 70
Total | [13 empty] | 2558.53 | 0 | 0