## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Augmentation of laying distribution system to extend the benefit of 100% Household in ZONE-III at BANESWARPUR under MOGRAHAT-I block within Mega surface water based water supply scheme of Falta-Mathurapur dist.- South 24 pgns. Under south 24 pgns water su | SM/16184 | Augmentation | Construction of balance FHTC platform, Chlorination Room (5.50m X 4.50m) and protection of pipelines for ZONE-III at BANESWARPUR under Augmentation of laying distribution system to extend the benefit of 100% Household in ZONE-III at BANESWARPUR under MOGRAHAT-I block within Mega surface water based water supply scheme of Falta-Mathurapur dist- South 24 pgns. under South 24 pgns W/S Division-I, PHE, Dte. (SM/16184) | AE SWSD-II | JE2 | ORD/000437/2024-2025 | 3882/SWD-I | 03/09/2024 | 19/10/2025 | PROJECT AND MAINTENANCE | 36.45 | 0 | 0 | 35
2 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Augmentation of laying distribution system to extend the benefit of 100% Household in ZONE-III at BANESWARPUR under MOGRAHAT-I block within Mega surface water based water supply scheme of Falta-Mathurapur dist.- South 24 pgns. Under south 24 pgns water su | SM/16184 | Augmentation | Construction of 550 Cum. capacity RCC Overhead Reservoir of 20 Mtr. Staging Height as per departmental design, drawing & specification with RCC Bored Pile & Pile Cap including Soil Investigation and foundation design, Laying Distribution System and providing FHTC for Augmentation of Piped W/S Scheme of Zone-III at PRATAPBERIA (Baneswarpur) of Mograhat-I Block within Mega Surface Water based Water Supply Scheme of Falta-Mathurapur Dist.-South 24-Parganas under South 24-Pgns. W/S Division-I, PHE Dte. [No. of FHTC = 4102] [TSM/015075 & TSM/010756] | AE SWSD-II | JE2 | ORD/000073/2023-2024 | 387/SWD-I | 28/04/2023 | 02/04/2025 | PROJECT AND MAINTENANCE | 418.32 | 157.44 | 37.64 | 95
3 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Augmentation of laying distribution system to extend the benefit of 100% Household in ZONE-III at BANESWARPUR under MOGRAHAT-I block within Mega surface water based water supply scheme of Falta-Mathurapur dist.- South 24 pgns. Under south 24 pgns water su | SM/16184 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with the allied accessories at newly sunk tube well of P.H. 1 under Basulhat water supply scheme adjacent to Zone-III at Baneswarpur under Mograhat-I Block under South 24 Pgs. Mechanical Division, PHE Dte. | Assistant Engineer ,Assistant Engineer -II | Junior Engineer | ORD/001148/2024-2025 | 4951/SMD | 31/12/2024 | 16/05/2025 | M/S. S.R. ENTERPRISE | 11.99 | 0 | 0 | 100
Total | [13 empty] | 466.75 | 157.44 | 33.73