## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Augmentation of laying distribution system to extend the benefit of 100% Household in ZONE-III at JOYNAGAR-II block within Mega surface water based water supply scheme of Falta-Mathurapur dist.- South 24 pgns. Under south 24 pgns water supply division-I, | SM/16185 | Augmentation | Laying distribution system of piped water supply at Zone-IIIB (Beledurganagar) of Joynagar-II block, under Baruipur Sub-Division, for "Augmentation of laying distribution system to extend the benefit of 100% Households in Zone-III at Joynagar-II block within Mega surface water based W/S scheme of Falta-Mathurapur dist. South 24 pgns water supply division-I,PHE Dte.". Erstwhile "Laying distribution system of piped water supply at Zone-IIIB (Beledurganagar) of Joynagar-II Block, under BARUIPUR Sub-Division, for ¿Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas¿ under South 24 Parganas W/S Division - I, P.H.E. Dte." | AE BSD | JE-1 | ORD/000339/2021-2022 | 2338/SWD-I | 22/02/2022 | 22/06/2022 | AJIT PRAMANICK | 416.96 | 120.71 | 28.95 | 85
2 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Augmentation of laying distribution system to extend the benefit of 100% Household in ZONE-III at JOYNAGAR-II block within Mega surface water based water supply scheme of Falta-Mathurapur dist.- South 24 pgns. Under south 24 pgns water supply division-I, | SM/16185 | Augmentation | Laying distribution system of piped water supply at Zone-III-A (Beladurganagar) of Joynagar-II Block, of BARUIPUR Sub-Division, for ¿Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas¿ under South 24 Parganas W/S Division - I, P.H.E. Dte. | AE BSD | JE-2 | ORD/000409/2021-2022 | 2337/SWD-I | 22/02/2022 | 22/06/2022 | MS LOKENATH CONSTRUCTION PROP SILPI DAS | 322.66 | 121.33 | 37.6 | 0
3 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Augmentation of laying distribution system to extend the benefit of 100% Household in ZONE-III at JOYNAGAR-II block within Mega surface water based water supply scheme of Falta-Mathurapur dist.- South 24 pgns. Under south 24 pgns water supply division-I, | SM/16185 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000066/2022-2023 | 2981/SWD-I | 20/02/2023 | 20/02/2023 | Resource Division | 326.04 | 0 | 0 | 0
4 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Augmentation of laying distribution system to extend the benefit of 100% Household in ZONE-III at JOYNAGAR-II block within Mega surface water based water supply scheme of Falta-Mathurapur dist.- South 24 pgns. Under south 24 pgns water supply division-I, | SM/16185 | Augmentation | Construction of development of land, approach road, protection work for pipeline, and other allied works for "Augmentation of laying distribution system to extend the benifit of 100% House hold in Zone-III at JOYNAGAR-II Block within Mega surface water based water supply scheme for Falta Mathurapur District South 24 Pgns under South 24 Parganas W/S Division-I, of South 24-Pgns. W/S Circle, PHE Dte." (SM/16185) | AE BSD | JE-2 | ORD/000277/2024-2025 | 2648/SWD-I | 07/06/2024 | 02/06/2025 | R.S. CONSTRUCTION CO. | 55.65 | 0 | 0 | 40
5 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Augmentation of laying distribution system to extend the benefit of 100% Household in ZONE-III at JOYNAGAR-II block within Mega surface water based water supply scheme of Falta-Mathurapur dist.- South 24 pgns. Under south 24 pgns water supply division-I, | SM/16185 | Augmentation | joynagar Jalaberia Kultali Road from 7.47 Kmp to 8.00 Kmp restoration of Paver Block,from 8.00 Kmp to 9.5 Kmp & 16.0 Kmp to 18.50 Kmp restoration of Head Shoulder due to laying of pipes by PHED under Lakshmikantapur Highway Sub-Division of Diamond Harbour Highway Division, P.W(Roads) Directorate in the District of South 24 Parganas |  |  | BILL/00637/2024-2025 | BP-2024-25-364 | 02/10/2024 | 02/10/2024 | EXECUTIVE ENGINEER, DIAMOND HARBOUR HIGHWAY DIVISION PW(ROADS) DTE. | 10.48 | 0 | 0 | 0
6 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Augmentation of laying distribution system to extend the benefit of 100% Household in ZONE-III at JOYNAGAR-II block within Mega surface water based water supply scheme of Falta-Mathurapur dist.- South 24 pgns. Under south 24 pgns water supply division-I, | SM/16185 | Augmentation | Gap Negotiation for Secondary grid of JOYNAGAR-II Block under Augmentation of laying distribution system to extend the benefit of 100% Households in ZONE-III at JOYNAGAR-II block within Mega surface water based water supply scheme for Falta-Mathurapur, South 24-Pgns. District under South 24-Pgns W/S Division-I, PHE Dte. (SM/16185) | AE BSD | JE-2 | ORD/000015/2025-2026 | 967/SWD-I | 09/04/2025 | 09/05/2025 | BISWAS CONSTRUCTION | 8.68 | 0 | 0 | 80
7 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Augmentation of laying distribution system to extend the benefit of 100% Household in ZONE-III at JOYNAGAR-II block within Mega surface water based water supply scheme of Falta-Mathurapur dist.- South 24 pgns. Under south 24 pgns water supply division-I, | SM/16185 | Augmentation | Additional laying of pipeline of secondary grid from Sikirhat to Ghatarnia and allied works for Nolgora of Joynagar-II Block under Augmentation of laying distribution system to extend the benefit of 100% Households in ZONE-III at JOYNAGAR-II block within Mega surface water based water supply scheme for Falta-Mathurapur, South 24 pgns. District under South 24 pgns W/S Division-I, PHE Dte. (SM/16185) | AE BSD | JE-2 | ORD/000006/2025-2026 | 909/SWD-I | 02/04/2025 | 01/06/2025 | BISWAS CONSTRUCTION | 47.37 | 0 | 0 | 70
Total | [13 empty] | 1187.85 | 242.04 | 20.38