## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | Augmentation of laying distribution system to extend the benefit of 100% Household in ZONE-III at KULTALI block within Mega surface water based water supply scheme of Falta-Mathurapur dist.- South 24 pgns. Under south 24 pgns water supply division-I, PHE | SM/16186 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000070/2022-2023 | 2986/SWD-I | 20/02/2023 |  | Resource Division | 233.8 | 0 | 0 | 0
2 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | Augmentation of laying distribution system to extend the benefit of 100% Household in ZONE-III at KULTALI block within Mega surface water based water supply scheme of Falta-Mathurapur dist.- South 24 pgns. Under south 24 pgns water supply division-I, PHE | SM/16186 | Augmentation | Laying distribution system of piped water supply at Zone-IIIA (MONDALER LAT) of Kultali Block, under BARUIPUR Sub-Division, for ¿Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas¿ under South 24 Parganas W/S Division - I, P.H.E. Dte. | AE BSD |  | ORD/000360/2021-2022 | 2532/SWD-I | 08/03/2022 | 06/07/2022 | SUPRITI ENTERPRISE | 808.84 | 365.38 | 45.17 | 85
3 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | Augmentation of laying distribution system to extend the benefit of 100% Household in ZONE-III at KULTALI block within Mega surface water based water supply scheme of Falta-Mathurapur dist.- South 24 pgns. Under south 24 pgns water supply division-I, PHE | SM/16186 | Augmentation | Construction of 1250 m3 capacity 20 M. staging height R.C.C. Over Head Water Reservoir as per departmental design, drawing & specification with R.C.C. Bored Pile & Pile Cap for Augmentation of laying distribution system to extend the benefit of 100% House hold in Zone-III (MONDALER LAT) at KULTALI Block within Mega Surface water based Water Supply scheme of Falta-Mathurapur District South 24 Pgns. under South 24 Pgns Water Supply Division-1, PHE Dte. [TSM : 015332] |  |  | ORD/000557/2023-2024 | 2585/SWD-I | 13/10/2023 | 08/08/2024 | M/S LOKENATH CONSTRUCTION | 439.11 | 0 | 0 | 0
4 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | Augmentation of laying distribution system to extend the benefit of 100% Household in ZONE-III at KULTALI block within Mega surface water based water supply scheme of Falta-Mathurapur dist.- South 24 pgns. Under south 24 pgns water supply division-I, PHE | SM/16186 | Augmentation | Laying distribution system of piped water supply at Zone-III-B ( MONDALER LAT) of Kultali Block, under BARUIPUR Sub-Division, for ?Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas? under South 24 Parganas W/S Division - I, P.H.E. Dte. | AE BSD |  | ORD/000127/2021-2022 | 2561/SWD-I | 11/03/2022 | 09/07/2022 | MANASH GHOSH | 626.38 | 88.27 | 14.09 | 91
5 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | Augmentation of laying distribution system to extend the benefit of 100% Household in ZONE-III at KULTALI block within Mega surface water based water supply scheme of Falta-Mathurapur dist.- South 24 pgns. Under south 24 pgns water supply division-I, PHE | SM/16186 | Augmentation | Laying of 315 mm diameter (OD) HDPE pipe by Horizontal Directional Drilling (HDD) process for crossing Piyali River at Panchuakhali Bridge in between nodes 8 & 8a within Kultali Block for Secondry Grid of under Augmentation of laying distribution system to extend the benefit of 100% Household in ZONE-III at KULTALI block within Mega surface water based water supply scheme of Falta-Mathurapur dist.- South 24 pgns. Under south 24 pgns water supply division-I, PHE Dte. (SM/16186) |  |  | ORD/000252/2024-2025 | 2715/SWD-I | 10/06/2024 | 30/06/2024 | ATINDRA CONSTRUCTION PRIVATE LIMITED. | 67.9 | 0 | 0 | 0
6 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | Augmentation of laying distribution system to extend the benefit of 100% Household in ZONE-III at KULTALI block within Mega surface water based water supply scheme of Falta-Mathurapur dist.- South 24 pgns. Under south 24 pgns water supply division-I, PHE | SM/16186 | Augmentation | Construction of pipeline protection works restoration of road damaged due to laying of pipeline and other allied works for Augmentation of laying distribution system to extend the benefit of 100% House Hold in ZONE-III at KULTALI block within Mega Surface Water Based Water Supply Scheme for Falta-Mathurapur District South 24 Parganas under South 24 Pgns W/S Division-I, PHE Dte. (SM/16186) | AE BSD | JE RWS | ORD/000402/2024-2025 | 3682/SWD-I | 22/08/2024 | 06/10/2024 | M/S. S.S. ENTERPRISE (NODAKHALI) | 95.58 | 0 | 0 | 0
Total | [13 empty] | 2271.62 | 453.65 | 19.97