## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Augmentation of laying distribution system to extend the benefit of 100% Households in ZONE-IV at KULTALI block within Mega surface water based water supply scheme for Falta-Mathurapur dist.- South 24 pgns. Under south 24 pgns W/S division-I of South 24-p | SM/16189 | Augmentation | Construction of 1000 Cu.m. capacity 20 M. staging height R.C.C. Over Head Water Reservoir as per departmental design, drawing & specification including R.C.C. Bored Pile & Pile Cap of piped water supply within Zone-IV at Gopalganj Mouza of Kultali Block for the "Mega Surface Water Based Water Supply Scheme, Dist. South 24 Parganas" under Baruipur Sub-Division of South 24 Paraganas Water Supply Division-I Division of PHE Dte. | AE BSD |  | ORD/000015/2022-2023 | 867/SWD-I | 13/07/2022 | 09/05/2023 | M/S PATH MAKERS | 269.19 | 234.16 | 86.99 | 90
2 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Augmentation of laying distribution system to extend the benefit of 100% Households in ZONE-IV at KULTALI block within Mega surface water based water supply scheme for Falta-Mathurapur dist.- South 24 pgns. Under south 24 pgns W/S division-I of South 24-p | SM/16189 | Augmentation | Construction of Protection work for pipeline restoration of road, construction of approach Road, development of Land for "Augmentation of laying distribution system to extend the benifit of 100% House hold in Zone-IV at KULTALI Block within Mega surface water based water supply scheme for Falta Mathurapur District South 24 Pgns under South 24 Parganas W/S Division-I, PHE Dte." (SM/16189) | AE BSD | JE RWS | ORD/000357/2024-2025 | 3457/SWD-I | 02/08/2024 | 29/01/2025 | ARNAB ENTERPRISE | 89.77 | 70.15 | 78.15 | 100
3 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Augmentation of laying distribution system to extend the benefit of 100% Households in ZONE-IV at KULTALI block within Mega surface water based water supply scheme for Falta-Mathurapur dist.- South 24 pgns. Under south 24 pgns W/S division-I of South 24-p | SM/16189 | Augmentation | Construction of pipe carrying structure with laying of 323.9 mm dia M.S. Secondary Rising Main for crossing of Canal at Brindaban Kheya Bridge and Raju Vata Culvert under Augmentation of laying distribution system to extend the benefit of 100% Households in ZONE-IV at KULTALI Block within Mega surface water based water supply scheme for Falta-Mathurapur dist.- South 24 pgns. Under south 24 pgns W/S Division-I of South 24-pgns. W/S Circle, PHE Dte. [SM/16189] | AE BSD | JE-2 | ORD/000283/2024-2025 | 3039/SWD-I | 02/07/2024 | 01/08/2024 | SRIJON ENTERPRISE | 26.01 | 25.68 | 98.73 | 100
4 | SOUTH 24 PARGANAS |  | Alipore Division | Augmentation of laying distribution system to extend the benefit of 100% Households in ZONE-IV at KULTALI block within Mega surface water based water supply scheme for Falta-Mathurapur dist.- South 24 pgns. Under south 24 pgns W/S division-I of South 24-p | SM/16189 | Augmentation | Road restoration for L048-Jauhia lo Patpukur. |  |  | BILL/01732/2024-2025 | BP-2024-25-796 | 25/10/2024 | 25/10/2024 | W.B.S.R.D.A., SOUTH TWENTY FOUR PARGANAS DIVISION | 3.48 | 0 | 0 | 0
5 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Augmentation of laying distribution system to extend the benefit of 100% Households in ZONE-IV at KULTALI block within Mega surface water based water supply scheme for Falta-Mathurapur dist.- South 24 pgns. Under south 24 pgns W/S division-I of South 24-p | SM/16189 | Augmentation | Laying distribution system of piped water supply at Zone-IV (DASKHIN GARANKATHI MOUZA) of Kultali Block, under Raidighi Sub-Division, for ¿Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas¿ under South 24 Parganas W/S Division - I, P.H.E. Dte. | AE BSD | JE-2 | ORD/000366/2021-2022 | 2533/SWD-I | 08/03/2022 | 15/02/2026 | GHOSH BROTHERS | 855.67 | 510.54 | 59.67 | 85
6 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Augmentation of laying distribution system to extend the benefit of 100% Households in ZONE-IV at KULTALI block within Mega surface water based water supply scheme for Falta-Mathurapur dist.- South 24 pgns. Under south 24 pgns W/S division-I of South 24-p | SM/16189 | Augmentation | Gap Negotiation for Secondary grid of Mathurapur-II block within Mega surface water based water supply scheme of Falta Mathurapur under "Augmentation of laying distribution system to extend the benefit of 100% Households in ZONE-IV at KULTALI block within Mega surface water based water supply scheme for Falta-Mathurapur dist.- South 24 pgns. Under south 24 pgns W/S division-I of South 24-pgns. W/S Circle, PHE Dte." [SM/16189] | AE BSD | JE-1 | ORD/001083/2024-2025 | 5350/SWD-I | 30/12/2024 | 28/02/2025 | CHANDAN ROY | 96.58 | 0 | 0 | 75
7 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Augmentation of laying distribution system to extend the benefit of 100% Households in ZONE-IV at KULTALI block within Mega surface water based water supply scheme for Falta-Mathurapur dist.- South 24 pgns. Under south 24 pgns W/S division-I of South 24-p | SM/16189 | Augmentation | Construction of pipe carrying structure with laying of 219.10 mm dia M.S. pipe for Secondary Rising Main for crossing of Jamtala Canal for Augmentation of laying distribution system to extend the benefit of 100% Households in ZONE-IV at KULTALI block within Mega surface water based water supply scheme for Falta-Mathurapur dist.- South 24 pgns. Under south 24 pgns W/S division-I of South 24-pgns. W/S Circle, PHE Dte. ( SM/16189) | AE BSD | JE RWS,JE-2 | ORD/000286/2024-2025 | 3042/SWD-I | 02/07/2024 | 01/08/2024 | SRIJON ENTERPRISE | 29.92 | 0 | 0 | 97
Total | [13 empty] | 1370.61 | 840.53 | 61.33