## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Augmentation of laying distribution system to extend the benefit of 100% Households in ZONE-V at JOYNAGAR-II block within Mega surface water based water supply scheme for Falta-Mathurapur dist.- South 24 pgns. Under south 24 pgns W/S division-I of South 2 | SM/16190 | Augmentation | Laying distribution system of piped water supply at Zone-VA (Monirtala) of Joynagar-II Block, of BARUIPUR Sub-Division, for ¿Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas¿ under South 24 Parganas W/S Division - I, P.H.E. Dte. | AE BSD |  | ORD/000676/2022-2023 | 71/SWD-I | 13/04/2022 | 11/08/2022 | TARUN KUMAR BHATTACHARYA PROPRIETOR | 565.06 | 197.88 | 35.02 | 40
2 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Augmentation of laying distribution system to extend the benefit of 100% Households in ZONE-V at JOYNAGAR-II block within Mega surface water based water supply scheme for Falta-Mathurapur dist.- South 24 pgns. Under south 24 pgns W/S division-I of South 2 | SM/16190 | Augmentation | Laying distribution system of piped water supply at Zone-VB (Monirtala) of Kultali Block, under BARUIPUR Sub-Division, for ¿Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas¿ under South 24 Parganas W/S Division - I, P.H.E. Dte. | AE BSD |  | ORD/000369/2021-2022 | 2339/SWD-I | 22/02/2022 | 22/06/2022 | CALCON CONSTRUCTIONS | 267.4 | 98.46 | 36.82 | 40
3 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Augmentation of laying distribution system to extend the benefit of 100% Households in ZONE-V at JOYNAGAR-II block within Mega surface water based water supply scheme for Falta-Mathurapur dist.- South 24 pgns. Under south 24 pgns W/S division-I of South 2 | SM/16190 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000067/2022-2023 | 2983/SWD-I | 20/02/2023 | 20/02/2023 | Resource Division | 230.38 | 0 | 0 | 0
4 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Augmentation of laying distribution system to extend the benefit of 100% Households in ZONE-V at JOYNAGAR-II block within Mega surface water based water supply scheme for Falta-Mathurapur dist.- South 24 pgns. Under south 24 pgns W/S division-I of South 2 | SM/16190 | Augmentation | Construction of 1250 Cu.m. capacity 20 M. staging height R.C.C. Over Head Water Reservoir as per departmental design, drawing & specification including R.C.C. Bored Pile & Pile Cap of piped water supply within Zone-V at Monirtar Mouza of Joynagar-II Block for the "Mega Surface Water Based Water Supply Scheme, Dist. South 24 Parganas" under Baruipur Sub-Division of South 24 Paraganas Water Supply Division-I Division of PHE Dte. | AE BSD | JE-2 | ORD/000143/2022-2023 | 1337/SWD-I | 16/09/2022 | 13/07/2023 | AJIT PRAMANICK | 322.51 | 165.52 | 51.32 | 45
5 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Augmentation of laying distribution system to extend the benefit of 100% Households in ZONE-V at JOYNAGAR-II block within Mega surface water based water supply scheme for Falta-Mathurapur dist.- South 24 pgns. Under south 24 pgns W/S division-I of South 2 | SM/16190 | Augmentation | Construction of pipeline protection works, restoration of roads damaged due to laying of pipeline and other allied works for Augmentation of laying distribution system to extend the benefit of 100% House Hold in ZONE-V at JOYNAGAR-II block within Mega Surface Water Based Water Supply Scheme for Falta-Mathurapur District South 24 Parganas under South 24 Pgns W/S Division-I, PHE Dte. (SM/16190) (2nd call) | AE BSD | JE-1 | ORD/000773/2024-2025 | 4758/SWD-I | 21/11/2024 | 31/12/2025 | MAMONI ENTERPRISE | 89.72 | 0 | 0 | 30
Total | [13 empty] | 1475.07 | 461.86 | 31.31