## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Augmentation of laying distribution system to extend the benefit of 100% Households in ZONE-VI at JOYNAGAR-II block within Mega surface water based water supply scheme for Falta-Mathurapur dist.- South 24 pgns. Under south 24 pgns W/S division-I of South | SM/16191 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000068/2022-2023 | 2983/SWD-I | 20/02/2023 | 20/02/2023 | Resource Division | 30.76 | 0 | 0 | 0
2 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Augmentation of laying distribution system to extend the benefit of 100% Households in ZONE-VI at JOYNAGAR-II block within Mega surface water based water supply scheme for Falta-Mathurapur dist.- South 24 pgns. Under south 24 pgns W/S division-I of South | SM/16191 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000205/2023-2024 | 382/SWD-I | 27/04/2023 | 27/04/2023 | Resource Division | 24.9 | 0 | 0 | 0
3 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Augmentation of laying distribution system to extend the benefit of 100% Households in ZONE-VI at JOYNAGAR-II block within Mega surface water based water supply scheme for Falta-Mathurapur dist.- South 24 pgns. Under south 24 pgns W/S division-I of South | SM/16191 | Augmentation | Laying distribution system of piped water supply at Zone-VI (Radha Ballavpur) of Joynagar-II Block, of BARUIPUR Sub-Division, for ¿Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas¿ under South 24 Parganas W/S Division - I, P.H.E. Dte. | AE BSD | JE-2 | ORD/000359/2021-2022 | 2599/SWD-I | 15/03/2022 | 27/02/2025 | SUPRITI ENTERPRISE | 740.59 | 0 | 0 | 88
4 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Augmentation of laying distribution system to extend the benefit of 100% Households in ZONE-VI at JOYNAGAR-II block within Mega surface water based water supply scheme for Falta-Mathurapur dist.- South 24 pgns. Under south 24 pgns W/S division-I of South | SM/16191 | Augmentation | Pipeline at different areas & others ancillary works including Land development of 900 Cu.M. Capacity R.C.C. Over Head Reservoir site for "Augmentation of laying distribution system to extend the benefit of 100% Household in Zone-VI (Radhaballavpur mouza) at Joynagar-II block within the Mega Surface Water Based Water Supply scheme, District Southy 24 Parganas" under Baruipur Sub Division of South 24 Parganas Water Supply Division-I of PHE Dte. [SM/ 16191] | AE BSD | JE-2 | ORD/000620/2023-2024 | 2804/SWD-I | 09/11/2023 | 24/12/2023 | WALL FORT INDIA | 15.71 | 0 | 0 | 50
5 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Augmentation of laying distribution system to extend the benefit of 100% Households in ZONE-VI at JOYNAGAR-II block within Mega surface water based water supply scheme for Falta-Mathurapur dist.- South 24 pgns. Under south 24 pgns W/S division-I of South | SM/16191 | Augmentation | Construction of 900 m3 capacity 20 M. staging height R.C.C. Over Head Water Reservoir as per departmental design, drawing & specification including R.C.C. Bored Pile & Pile Cap for "Augmentation of laying distribution system to extend the benefit of 100% Household in Zone-VI (RADHABALLAVPUR) at Joynagar-II Block within Mega Surface Water Based Water Supply Scheme of Falta-Mathurapur District South 24 Parganas under South 24 parganas water Supply Division-I of PHEDte." [TSM : 014964] | AE BSD | JE-2 | ORD/000535/2023-2024 | 2364/SWD-I | 26/09/2023 | 14/03/2026 | ATCO ENTERPRISE | 364 | 0 | 0 | 30
6 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Augmentation of laying distribution system to extend the benefit of 100% Households in ZONE-VI at JOYNAGAR-II block within Mega surface water based water supply scheme for Falta-Mathurapur dist.- South 24 pgns. Under south 24 pgns W/S division-I of South | SM/16191 | Augmentation | Laying of additional pipeline for parallel connections from main pipeline to provide FHTC in Zone-VI RADHABALLAVPUR Mouza under Augmentation of laying distribution system to extend the benefit of 100% households in Zone-VI at Joynagar-II Block within Mega Surface Water Based Water Supply Scheme for Falta-Mathurapur Dist.- South 24-Pgns. under South 24-Pgns W/S Division-I, PHE Dte. (SM/16191) | AE BSD | JE-2 | ORD/001157/2024-2025 | 375/SWD-I | 04/02/2025 | 19/06/2025 | SUPRITI ENTERPRISE | 50.03 | 0 | 0 | 50
7 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Augmentation of laying distribution system to extend the benefit of 100% Households in ZONE-VI at JOYNAGAR-II block within Mega surface water based water supply scheme for Falta-Mathurapur dist.- South 24 pgns. Under south 24 pgns W/S division-I of South | SM/16191 | Augmentation | Construction of pipe carrying structure with laying of 508 mm dia M.S. Secondary Rising Main for crossing of Canal at Simana Bazar, 610 mm dia M.S. Secondary Rising Main for crossing of Canal at Path Pukur Bridge and 355.6 mm dia M.S. pipe for Secondary Rising Main for crossing of Canal at Jibon Mandaler Haat under Augmentation of laying distribution system to extend the benefit of 100% Households in ZONE-VI, Zone-IV and Zone-II respectively within JOYNAGAR-II block within Mega surface water based water supply scheme for Falta-Mathurapur dist.- South 24 pgns. Under south 24 pgns W/S division-I of South 24-pgns. W/S Circle, PHE Dte. [SM/16191, 18655 & 18222] | AE BSD | JE-1,JE-2 | ORD/000285/2024-2025 | 3041/SWD-I | 02/07/2024 | 16/08/2024 | SRIJON ENTERPRISE | 69.41 | 0 | 0 | 100
Total | [13 empty] | 1295.4 | 0 | 0