## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Augmentation of laying distribution system to extend the benefit of 100% Households in ZONE-VI at JOYNAGAR-II block within Mega surface water based water supply scheme for Falta-Mathurapur dist.- South 24 pgns. Under south 24 pgns W/S division-I of South | SM/16191 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000068/2022-2023 | 2983/SWD-I | 20/02/2023 | 20/02/2023 | Resource Division | 30.76 | 0 | 0 | 0
2 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Augmentation of laying distribution system to extend the benefit of 100% Households in ZONE-VI at JOYNAGAR-II block within Mega surface water based water supply scheme for Falta-Mathurapur dist.- South 24 pgns. Under south 24 pgns W/S division-I of South | SM/16191 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000205/2023-2024 | 382/SWD-I | 27/04/2023 | 27/04/2023 | Resource Division | 24.9 | 0 | 0 | 0
3 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Augmentation of laying distribution system to extend the benefit of 100% Households in ZONE-VI at JOYNAGAR-II block within Mega surface water based water supply scheme for Falta-Mathurapur dist.- South 24 pgns. Under south 24 pgns W/S division-I of South | SM/16191 | Augmentation | Laying distribution system of piped water supply at Zone-VI (Radha Ballavpur) of Joynagar-II Block, of BARUIPUR Sub-Division, for ¿Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas¿ under South 24 Parganas W/S Division - I, P.H.E. Dte. | AE BSD | JE-2 | ORD/000359/2021-2022 | 2599/SWD-I | 15/03/2022 | 27/02/2025 | SUPRITI ENTERPRISE | 740.59 | 663.01 | 89.52 | 88
4 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Augmentation of laying distribution system to extend the benefit of 100% Households in ZONE-VI at JOYNAGAR-II block within Mega surface water based water supply scheme for Falta-Mathurapur dist.- South 24 pgns. Under south 24 pgns W/S division-I of South | SM/16191 | Augmentation | Pipeline at different areas & others ancillary works including Land development of 900 Cu.M. Capacity R.C.C. Over Head Reservoir site for "Augmentation of laying distribution system to extend the benefit of 100% Household in Zone-VI (Radhaballavpur mouza) at Joynagar-II block within the Mega Surface Water Based Water Supply scheme, District Southy 24 Parganas" under Baruipur Sub Division of South 24 Parganas Water Supply Division-I of PHE Dte. [SM/ 16191] | AE BSD | JE-2 | ORD/000620/2023-2024 | 2804/SWD-I | 09/11/2023 | 24/12/2023 | WALL FORT INDIA | 15.71 | 14.41 | 91.72 | 50
5 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Augmentation of laying distribution system to extend the benefit of 100% Households in ZONE-VI at JOYNAGAR-II block within Mega surface water based water supply scheme for Falta-Mathurapur dist.- South 24 pgns. Under south 24 pgns W/S division-I of South | SM/16191 | Augmentation | Construction of 900 m3 capacity 20 M. staging height R.C.C. Over Head Water Reservoir as per departmental design, drawing & specification including R.C.C. Bored Pile & Pile Cap for "Augmentation of laying distribution system to extend the benefit of 100% Household in Zone-VI (RADHABALLAVPUR) at Joynagar-II Block within Mega Surface Water Based Water Supply Scheme of Falta-Mathurapur District South 24 Parganas under South 24 parganas water Supply Division-I of PHEDte." [TSM : 014964] | AE BSD | JE-2 | ORD/000535/2023-2024 | 2364/SWD-I | 26/09/2023 | 14/03/2026 | ATCO ENTERPRISE | 364 | 0 | 0 | 30
6 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Augmentation of laying distribution system to extend the benefit of 100% Households in ZONE-VI at JOYNAGAR-II block within Mega surface water based water supply scheme for Falta-Mathurapur dist.- South 24 pgns. Under south 24 pgns W/S division-I of South | SM/16191 | Augmentation | Laying of additional pipeline for parallel connections from main pipeline to provide FHTC in Zone-VI RADHABALLAVPUR Mouza under Augmentation of laying distribution system to extend the benefit of 100% households in Zone-VI at Joynagar-II Block within Mega Surface Water Based Water Supply Scheme for Falta-Mathurapur Dist.- South 24-Pgns. under South 24-Pgns W/S Division-I, PHE Dte. (SM/16191) | AE BSD | JE-2 | ORD/001157/2024-2025 | 375/SWD-I | 04/02/2025 | 19/06/2025 | SUPRITI ENTERPRISE | 50.03 | 0 | 0 | 50
Total | [13 empty] | 1225.99 | 677.43 | 55.26