## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based PASCHIM CHAKPANCHGHORA piped water supply scheme to accommodate FHTC in JOYNAGAR-I block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Pargan | SM/16930 | Augmentation | Preparation and submission of Detailed Project Report of PASCHIM CHAKPANCHGHORA Ground Water Based Piped Water Supply Scheme in JOYNAGAR-I Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE BSD |  | ORD/000388/2021-2022 | 1926/SWD-I NEW | 27/01/2022 | 26/02/2022 | ASTER CONSULTANCY | 2.76 | 2.61 | 94.49 | 0
2 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based PASCHIM CHAKPANCHGHORA piped water supply scheme to accommodate FHTC in JOYNAGAR-I block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Pargan | SM/16930 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000089/2023-2024 | 294/SWD-I | 25/04/2023 | 25/04/2023 | Resource Division | 32.55 | 0 | 0 | 0
3 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based PASCHIM CHAKPANCHGHORA piped water supply scheme to accommodate FHTC in JOYNAGAR-I block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Pargan | SM/16930 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000138/2022-2023 | 3421/SWD-I | 13/03/2023 | 13/03/2023 | Resource Division | 7.63 | 0 | 0 | 0
4 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based PASCHIM CHAKPANCHGHORA piped water supply scheme to accommodate FHTC in JOYNAGAR-I block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Pargan | SM/16930 | Augmentation | Sinking of 02 (Two) nos. Rig bored 250mm x 150mm dia. & 300 mtr. deep Tube-well by Rotary method for PASCHIM CHAKPANCHGHORA PWSS of JOYNAGAR-I block under South 24-Parganas W/S Division-I, P.H.E. Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district. [TSM/012513] | AE BSD | JE-2 | ORD/000749/2022-2023 | 3609/SWD-I | 24/03/2023 | 23/04/2023 | MONDAL ENTERPRISE | 31.77 | 29.96 | 94.31 | 100
5 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Ground water based PASCHIM CHAKPANCHGHORA piped water supply scheme to accommodate FHTC in JOYNAGAR-I block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Pargan | SM/16930 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, of Paschim Chakpanchghora supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Jaynagar-I] | Assistant Engineer | Junior Engineer | ORD/000576/2022-2023 | 601/SMD | 27/02/2023 | 01/04/2025 | CONCORD ENGINEERING | 19.28 | 2.3 | 11.94 | 45
6 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Ground water based PASCHIM CHAKPANCHGHORA piped water supply scheme to accommodate FHTC in JOYNAGAR-I block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Pargan | SM/16930 | Augmentation | Improvement of outdoor Illumination arrangement with allied works at Pump House no-1 of Paschim Chak Panchghara W/S Scheme under SMD, P.H.E. Dte. (Block-Jaynagar-I) (SM/16930) | Assistant Engineer | Junior Engineer | ORD/002298/2024-2025 | 1447/SMSD | 24/10/2024 | 08/11/2024 | CONCORD ENGINEERING | 0.59 | 0 | 0 | 0
7 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Ground water based PASCHIM CHAKPANCHGHORA piped water supply scheme to accommodate FHTC in JOYNAGAR-I block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Pargan | SM/16930 | Augmentation | Improvement of outdoor Illumination arrangement with allied works at Pump House no-2 of Paschim Chak Panchghara W/S Scheme under SMD, P.H.E. Dte. (Block-Jaynagar-I) (SM/16930) | Assistant Engineer | Junior Engineer | ORD/002299/2024-2025 | 1528/SMSD | 19/11/2024 | 04/12/2024 | CONCORD ENGINEERING | 0.59 | 0 | 0 | 0
8 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based PASCHIM CHAKPANCHGHORA piped water supply scheme to accommodate FHTC in JOYNAGAR-I block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Pargan | SM/16930 | Augmentation | Construction of 3 Nos. OHR of different capacities, Chlorine Room (six nos.) along with Laying of Distribution System, Rising Main, Providing Functional Household Tap Connection (FHTC) including design and drawing of pile cap after soil investigation for Augmentation of SRIKRISHNANAGAR, PASCHIM CHAK PANCHGHORA & PUNPO PWSS of JOYNAGAR-I Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. [No. of FHTC = 4272] [TSM/012514, TSM/012513, TSM/012506] | AE BSD | JE-2 | ORD/000038/2023-2024 | 152/SWD-I | 13/04/2023 | 01/07/2026 | BKB INFRA PROJECTS (P) LTD. | 1132.95 | 110.46 | 9.75 | 15
Total | [13 empty] | 1228.12 | 145.33 | 11.83