## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | Augmentation for providing balance FHTC in Buita Chingripota Nischintipur Rajibpur & Uttar Roypur GP under SWD - I, P.H.E. Dte District South 24 Parganas. | SM/16962 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000317/2023-2024 | 24/SWSD-I | 09/01/2024 |  | Resource Division | 15.76 | 0 | 0 | 0
2 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | Augmentation for providing balance FHTC in Buita Chingripota Nischintipur Rajibpur & Uttar Roypur GP under SWD - I, P.H.E. Dte District South 24 Parganas. | SM/16962 | Augmentation | Augmentation for Providing balance FHTC in BUITA, CHINGRIPOTA, NISCHINTIPUR, RAJIBPUR & UTTAR ROYPUR GP under South 24 Parganas W/S Division-I, PHE, Dte. Dist. South 24 Pgns. | AE SWSD-I | JE-1 | ORD/000564/2023-2024 | 2637/SWD-I | 20/10/2023 | 19/12/2023 | STAR ENGINEERS CO-OPERATIVE SOCEITY LTD. | 80.22 | 26.19 | 32.64 | 60
Total | [13 empty] | 95.98 | 26.19 | 27.28