## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Proposed Ground water based PETUA (PART-II) piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affec | SM/17299 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000178/2023-2024 | 295/SWD-I | 25/04/2023 | 25/04/2023 | Resource Division | 33.22 | 0 | 0 | 0
2 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Proposed Ground water based PETUA (PART-II) piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affec | SM/17299 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000112/2023-2024 | 294/SWD-I | 25/04/2023 | 25/04/2023 | Resource Division | 33.22 | 0 | 0 | 0
3 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Proposed Ground water based PETUA (PART-II) piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affec | SM/17299 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1 & 2 of Petua ( Part-II) water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Baruipur] | Assistant Engineer | Junior Engineer | ORD/000091/2023-2024 | 1084/SMD | 18/04/2023 | 17/07/2023 | ASHIM UDYOG | 22.78 | 0 | 0 | 43
4 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Proposed Ground water based PETUA (PART-II) piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affec | SM/17299 | Augmentation | Supply & Fixing main switch & Bus bar at Pump House no-1 & 2 of Petua (Part-II) W/S Scheme under SMD, P.H.E. Dte.(Block-Baruipur)(SM/17299) | Assistant Engineer | Junior Engineer | ORD/000779/2024-2025 | 888/SMSD | 19/06/2024 | 04/07/2024 | ASHIM UDYOG | 0.58 | 0 | 0 | 0
5 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Proposed Ground water based PETUA (PART-II) piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affec | SM/17299 | Augmentation | Improvement of outdoor Illumination arrangement with allied works at Pump House no-2 of Petua (Part-II) scheme under SMD, P.H.E. Dte.(Block-Baruipur) [SM/17299] | Assistant Engineer | Junior Engineer | ORD/000780/2024-2025 | 935/SMSD | 28/06/2024 | 13/07/2024 | ASHIM UDYOG | 0.89 | 0 | 0 | 0
6 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Proposed Ground water based PETUA (PART-II) piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affec | SM/17299 | Augmentation | Sinking of 02 (Two) nos. Rig bored 250mm x 150mm dia. & 300 mtr. deep Tube-well having 66 mtr. housing pipe by Rotary method for PETUA (PART-II) PWSS of BARUIPUR Block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division-I, P.H.E. Dte. [TSM/018705] | AE BSD | JE-1 | ORD/000748/2022-2023 | 3610/SWD-I | 24/03/2023 | 23/04/2023 | TAPAS KUMAR GIRI | 31.8 | 0 | 0 | 50
7 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Proposed Ground water based PETUA (PART-II) piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affec | SM/17299 | Augmentation | Preparation and submission of Detailed Project Report of Ground Water Based Petua (Part-II) Piped Water Supply Scheme to accommodate FHTC in Baruipur Block under South 24-Pgs W/S Division-I, PHE Dte for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. |  |  | ORD/000929/2022-2023 | 1198/SWD-I | 02/09/2022 | 02/10/2022 | GEO SOLUTION | 2.54 | 0 | 0 | 100
8 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Proposed Ground water based PETUA (PART-II) piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affec | SM/17299 | Augmentation | Payment of electricity bill for new service connection under SMD, PHE Dte. |  |  | BILL/04816/2023-2024 | BP-2023-24-527 | 22/02/2024 | 22/02/2024 | WBSEDCL | 6.24 | 0 | 0 | 0
9 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Proposed Ground water based PETUA (PART-II) piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affec | SM/17299 | Augmentation | Construction of Boundary Wall, Pump House cum Chlorine Room along with Laying of Distribution System, Rising Main, Providing Functional Household Tap Connection (FHTC) for PETUA (PART-II) MOUZA Piped Water Supply Scheme of BARUIPUR Block for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district under South 24-Pgns. W/S Division-I, PHE Dte. [No. of FHTC =1306] [TSM/018705] | AE BSD | JE-1 | ORD/000079/2023-2024 | 393/SWD-I | 28/04/2023 | 14/10/2025 | L.N. ENTERPRISE | 214.84 | 0 | 0 | 90
10 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Proposed Ground water based PETUA (PART-II) piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affec | SM/17299 | Augmentation | Development of land of OHR site / 2nd TW site including Construction of approch road and other allied works for Ground Water Based PETUA (Part-II) Piped Water Supply Scheme to Accommodate FHTC in BARUIPUR Block under South 24 Parganas W/S Division-I, South 24 Parganas District For Augmentation of Surface Water Based Water Supply Scheme In Arsenic Affected Areas of South 24 Parganas District. (SM/17299) | AE BSD |  | ORD/000848/2023-2024 | 1253/SWD-I | 13/03/2024 | 03/12/2025 | L.N. ENTERPRISE | 27.77 | 0 | 0 | 50
11 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Proposed Ground water based PETUA (PART-II) piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affec | SM/17299 | Augmentation | Sinking of Rig bored 250mm x 150mm dia. & 300 mtr. deep Tubewell having 66 mtr. housing pipe by Rotary method at 2nd Tubewell site for PETUA (PART-II) Piped Water Supply Scheme to accommodate FHTC in BARUIPUR Block under South 24-Parganas W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs District. [SM/17299] |  |  | ORD/001146/2024-2025 | 327/SWD-I | 29/01/2025 | 28/02/2025 | M/S MAA TARA ENTERPRISE | 15.57 | 0 | 0 | 0
12 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Proposed Ground water based PETUA (PART-II) piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affec | SM/17299 | Augmentation | Improvement of outdoor Illumination arrangement with allied works at Pump House no-1 of Patua (Part-II) W/S Scheme under SMD, P.H.E. Dte. (Block-Baruipur) | Assistant Engineer | Junior Engineer | ORD/002844/2023-2024 | 277/SMSD | 29/02/2024 | 15/03/2024 | ASHIM UDYOG | 0.89 | 0 | 0 | 100
Total | [13 empty] | 390.33 | 0 | 0