## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Augmentation of laying distribution system to extend the benefit of 100% Household in ZONE-I at KULTALI block within Mega surface water based water supply scheme of Falta-Mathurapur dist.- South 24 pgns. Under south 24 pgns water supply division-I, PHE Dt | SM/18219 | Augmentation | Construction of Boundary wall for proposed OHR Site at Purbatetulberia Mouza, JL No.10, Khatian No. 899/1, Plot No. 916 & 918; within Kultali block, under Mega Surface Water Based Water Supply Secheme for Falta-Mathurapur, Dist. South 24 Paraganas. [Length - 140.0 mtr.] | AE BSD |  | ORD/000418/2021-2022 | 1798/SWD_I | 14/01/2022 | 14/04/2022 | KHAN ENTERPRISE | 26.92 | 23.51 | 87.33 | 0
2 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Augmentation of laying distribution system to extend the benefit of 100% Household in ZONE-I at KULTALI block within Mega surface water based water supply scheme of Falta-Mathurapur dist.- South 24 pgns. Under south 24 pgns water supply division-I, PHE Dt | SM/18219 | Augmentation | Construction of 1500 Cum. capacity OHR (20 mtr. staging height) along with Laying of Distribution System, Rising Main, Providing Functional Household Tap Connection (FHTC) including design and drawing of pile foundation and pile cap after soil investigation for Augmentation of ZONE-I PURBO TETULBERIA MOUZA Piped Water Supply Scheme of KULTALI Block for implementation of JJM under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. [No. of FHTC = 14340] [TSM/011555 & TSM/016360] | AE BSD | JE RWS | ORD/000529/2023-2024 | 2344/SWD-I | 22/09/2023 | 02/04/2025 | MADAN MOHAN MONDAL | 1916.42 | 197.99 | 10.33 | 60
Total | [13 empty] | 1943.33 | 221.5 | 11.4