## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Augmentation of laying distribution system to extend the benefit of 100% Household in ZONE-VI at KULTALI block within Mega surface water based water supply scheme of Falta-Mathurapur dist.- South 24 pgns. Under south 24 pgns water supply division-I, PHE D | SM/18220 | Augmentation | Laying distribution system of piped water supply at Zone-VIA of Kultali Block, under BARUIPUR Sub-Division, for ¿Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas¿ under South 24 Parganas W/S Division - I, P.H.E. Dte.. | AE BSD |  | ORD/000403/2021-2022 | 2551/SWD-I | 10/03/2022 | 08/07/2022 | MS GOUTAM CHAKRABORTY | 640.41 | 290.58 | 45.37 | 0
2 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Augmentation of laying distribution system to extend the benefit of 100% Household in ZONE-VI at KULTALI block within Mega surface water based water supply scheme of Falta-Mathurapur dist.- South 24 pgns. Under south 24 pgns water supply division-I, PHE D | SM/18220 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000038/2022-2023 | 2955/SWD-I | 16/02/2023 | 16/02/2023 | Resource Division | 1655.16 | 0 | 0 | 0
3 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Augmentation of laying distribution system to extend the benefit of 100% Household in ZONE-VI at KULTALI block within Mega surface water based water supply scheme of Falta-Mathurapur dist.- South 24 pgns. Under south 24 pgns water supply division-I, PHE D | SM/18220 | Augmentation | Laying of HDPE pipe of 500 mm diameter by Horizontal Directional Drilling (HDD) process for crossing Matla-Tribtary between Kantamari and Madhya Gurguria on Maypith Road in between nodes 4 & 5 within Kultali Block for Secondry Grid of under Augmentation of laying distribution system to extend the benefit of 100% Household in ZONE-VI at KULTALI block within Mega surface water based water supply scheme of Falta-Mathurapur dist.- South 24 pgns. Under south 24 pgns water supply division-I, PHE Dte.". (SM/18220) |  |  | ORD/000737/2023-2024 | 495/SWD-I | 25/01/2024 | 24/02/2024 | ATINDRA CONSTRUCTION PRIVATE LIMITED. | 84.5 | 84.5 | 100 | 100
4 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Augmentation of laying distribution system to extend the benefit of 100% Household in ZONE-VI at KULTALI block within Mega surface water based water supply scheme of Falta-Mathurapur dist.- South 24 pgns. Under south 24 pgns water supply division-I, PHE D | SM/18220 | Augmentation | Construction of 900 Cum. capacity RCC Overhead Reservoir of 20 Mtr. Staging Height as per departmental design, drawing & specification with RCC Bored Pile & Pile Cap including Soil Investigation and foundation design with balance work for Augmentation of Laying Distribution System to extend benefit off 100% household in at MADHYA GURUIA (Zone-VI) Mouza in Kultali Block within Mega Surface Water based Water Supply Scheme of Falta-Mathurapur Dist.-South 24-Parganas under South 24-Pgns. W/S Division-I, PHE Dte. [TSM/016361] | AE BSD | JE-1 | ORD/000459/2023-2024 | 2136/SWD-I | 31/08/2023 | 26/06/2024 | M/S SARADA CONSTRUCTION | 669.13 | 75.22 | 11.24 | 30
5 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Augmentation of laying distribution system to extend the benefit of 100% Household in ZONE-VI at KULTALI block within Mega surface water based water supply scheme of Falta-Mathurapur dist.- South 24 pgns. Under south 24 pgns water supply division-I, PHE D | SM/18220 | Augmentation | Negotiation of gap of Secondary Grid pipeline under Augmentation of laying distribution system to extend the benefit of 100% household in Zone-VI at KULTALI block within Mega surface water based water supply scheme of Falta-Mathurapur Dist.-South 24 pgns. under South 24-Pgns Water Supply Division-I, PHE Dte. (SM/18220) | AE BSD | JE-2 | ORD/000092/2025-2026 | 1767/SWD-I | 02/07/2025 | 29/12/2025 | CHANDAN ROY | 88.79 | 0 | 0 | 80
Total | [13 empty] | 3137.99 | 450.29 | 14.35