## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Augmentation of laying distribution system to extend the benefit of 100% Household in ZONE-VI at KULTALI block within Mega surface water based water supply scheme of Falta-Mathurapur dist.- South 24 pgns. Under south 24 pgns water supply division-I, PHE D | SM/18220 | Augmentation | Laying distribution system of piped water supply at Zone-VIA of Kultali Block, under BARUIPUR Sub-Division, for ¿Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas¿ under South 24 Parganas W/S Division - I, P.H.E. Dte.. | AE BSD | JE-2 | ORD/000403/2021-2022 | 2551/SWD-I | 10/03/2022 | 08/07/2022 | MS GOUTAM CHAKRABORTY | 640.41 | 290.58 | 45.37 | 100
2 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Augmentation of laying distribution system to extend the benefit of 100% Household in ZONE-VI at KULTALI block within Mega surface water based water supply scheme of Falta-Mathurapur dist.- South 24 pgns. Under south 24 pgns water supply division-I, PHE D | SM/18220 | Augmentation | Construction of 900 Cum. capacity RCC Overhead Reservoir of 20 Mtr. Staging Height as per departmental design, drawing & specification with RCC Bored Pile & Pile Cap including Soil Investigation and foundation design with balance work for Augmentation of Laying Distribution System to extend benefit off 100% household in at MADHYA GURUIA (Zone-VI) Mouza in Kultali Block within Mega Surface Water based Water Supply Scheme of Falta-Mathurapur Dist.-South 24-Parganas under South 24-Pgns. W/S Division-I, PHE Dte. [TSM/016361] | AE BSD | JE-1 | ORD/000459/2023-2024 | 2136/SWD-I | 31/08/2023 | 26/06/2024 | M/S SARADA CONSTRUCTION | 669.13 | 75.22 | 11.24 | 30
3 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Augmentation of laying distribution system to extend the benefit of 100% Household in ZONE-VI at KULTALI block within Mega surface water based water supply scheme of Falta-Mathurapur dist.- South 24 pgns. Under south 24 pgns water supply division-I, PHE D | SM/18220 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000038/2022-2023 | 2955/SWD-I | 16/02/2023 | 16/02/2023 | Resource Division | 1655.16 | 0 | 0 | 0
4 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Augmentation of laying distribution system to extend the benefit of 100% Household in ZONE-VI at KULTALI block within Mega surface water based water supply scheme of Falta-Mathurapur dist.- South 24 pgns. Under south 24 pgns water supply division-I, PHE D | SM/18220 | Augmentation | Laying of HDPE pipe of 500 mm diameter by Horizontal Directional Drilling (HDD) process for crossing Matla-Tribtary between Kantamari and Madhya Gurguria on Maypith Road in between nodes 4 & 5 within Kultali Block for Secondry Grid of under Augmentation of laying distribution system to extend the benefit of 100% Household in ZONE-VI at KULTALI block within Mega surface water based water supply scheme of Falta-Mathurapur dist.- South 24 pgns. Under south 24 pgns water supply division-I, PHE Dte.". (SM/18220) |  |  | ORD/000737/2023-2024 | 495/SWD-I | 25/01/2024 | 24/02/2024 | ATINDRA CONSTRUCTION PRIVATE LIMITED. | 84.5 | 84.5 | 100 | 100
5 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Augmentation of laying distribution system to extend the benefit of 100% Household in ZONE-VI at KULTALI block within Mega surface water based water supply scheme of Falta-Mathurapur dist.- South 24 pgns. Under south 24 pgns water supply division-I, PHE D | SM/18220 | Augmentation | Laying of 475 mm dia (OD) M.S. pipe line for connecting gaps of Secondary grid at both sides of Pet Kulchart Bridge between Kantamari and Madhya Gurguria on Maypith Road in between nodes 4 & 5 within Kultali Block for Secondry Grid of under Augmentation of laying distribution system to extend the benefit of 100% Household in ZONE-VI at KULTALI block within Mega surface water based water supply scheme of Falta-Mathurapur dist.- South 24 pgns. Under south 24 pgns water supply division-I, PHE Dte.". (SM/18220) | AE BSD | JE RWS,JE-2 | ORD/000761/2024-2025 | 4682/SWD-I | 18/11/2024 | 02/01/2025 | SRIJON ENTERPRISE | 13.46 | 0 | 0 | 99
6 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Augmentation of laying distribution system to extend the benefit of 100% Household in ZONE-VI at KULTALI block within Mega surface water based water supply scheme of Falta-Mathurapur dist.- South 24 pgns. Under south 24 pgns water supply division-I, PHE D | SM/18220 | Augmentation | Negotiation of gap of Secondary Grid pipeline under Augmentation of laying distribution system to extend the benefit of 100% household in Zone-VI at KULTALI block within Mega surface water based water supply scheme of Falta-Mathurapur Dist.-South 24 pgns. under South 24-Pgns Water Supply Division-I, PHE Dte. (SM/18220) | AE BSD | JE-2 | ORD/000092/2025-2026 | 1767/SWD-I | 02/07/2025 | 29/12/2025 | CHANDAN ROY | 88.79 | 0 | 0 | 80
Total | [13 empty] | 3151.45 | 450.29 | 14.29