## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Augmentation of laying distribution system to extend the benefit of 100% Household in ZONE-VII at KULTALI block within Mega surface water based water supply scheme of Falta-Mathurapur dist.- South 24 pgns. Under south 24 pgns water supply division-I, PHE | SM/18221 | Augmentation | Laying distribution system of piped water supply at Zone-VIIB (BINODPUR) of Kultali Block, under BARUIPUR Sub-Division, for ¿Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas¿ under South 24 Parganas W/S Division - I, P.H.E. Dte. | AE BSD |  | ORD/000399/2021-2022 | 2534/SWD-I | 08/03/2022 | 06/07/2022 | M/S. S.S. ENTERPRISE | 739.71 | 0 | 0 | 0
2 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Augmentation of laying distribution system to extend the benefit of 100% Household in ZONE-VII at KULTALI block within Mega surface water based water supply scheme of Falta-Mathurapur dist.- South 24 pgns. Under south 24 pgns water supply division-I, PHE | SM/18221 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000042/2022-2023 | 2958/SWD-I | 16/02/2023 | 16/02/2023 | Resource Division | 1067.77 | 0 | 0 | 0
3 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Augmentation of laying distribution system to extend the benefit of 100% Household in ZONE-VII at KULTALI block within Mega surface water based water supply scheme of Falta-Mathurapur dist.- South 24 pgns. Under south 24 pgns water supply division-I, PHE | SM/18221 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000063/2022-2023 | 2978/SWD-I | 20/02/2023 | 20/02/2023 | Resource Division | 443.48 | 0 | 0 | 0
4 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Augmentation of laying distribution system to extend the benefit of 100% Household in ZONE-VII at KULTALI block within Mega surface water based water supply scheme of Falta-Mathurapur dist.- South 24 pgns. Under south 24 pgns water supply division-I, PHE | SM/18221 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000071/2022-2023 | 2987/SWD-I | 20/02/2023 | 20/02/2023 | Resource Division | 29.22 | 0 | 0 | 0
5 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Augmentation of laying distribution system to extend the benefit of 100% Household in ZONE-VII at KULTALI block within Mega surface water based water supply scheme of Falta-Mathurapur dist.- South 24 pgns. Under south 24 pgns water supply division-I, PHE | SM/18221 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000296/2023-2024 | 2434/SWD-I | 30/09/2023 | 30/09/2023 | Resource Division | 33.95 | 0 | 0 | 0
6 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Augmentation of laying distribution system to extend the benefit of 100% Household in ZONE-VII at KULTALI block within Mega surface water based water supply scheme of Falta-Mathurapur dist.- South 24 pgns. Under south 24 pgns water supply division-I, PHE | SM/18221 | Augmentation | Laying distribution system of piped water supply at Zone-VIIA (BINODPUR MOUZA) of Kultali Block, under BARUIPUR Sub-Division, for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas¿ under South 24 Parganas W/S Division - I, P.H.E. Dte. | AE BSD | JE-2 | ORD/000873/2022-2023 | 72/SWD-I | 13/04/2022 | 11/08/2022 | MRITYUNJOY MUKHERJEE AND CO | 518.85 | 0 | 0 | 60
7 | SOUTH 24 PARGANAS |  | Alipore Division | Augmentation of laying distribution system to extend the benefit of 100% Household in ZONE-VII at KULTALI block within Mega surface water based water supply scheme of Falta-Mathurapur dist.- South 24 pgns. Under south 24 pgns water supply division-I, PHE | SM/18221 | Augmentation | Road restoration of Nolgora to Sonartikari |  |  | BILL/01782/2024-2025 | BP-2024-25-807 | 25/10/2024 | 25/10/2024 | W.B.S.R.D.A., SOUTH TWENTY FOUR PARGANAS DIVISION | 14.42 | 0 | 0 | 0
8 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Augmentation of laying distribution system to extend the benefit of 100% Household in ZONE-VII at KULTALI block within Mega surface water based water supply scheme of Falta-Mathurapur dist.- South 24 pgns. Under south 24 pgns water supply division-I, PHE | SM/18221 | Augmentation | Construction of 1250 m3 capacity 20 M. staging height R.C.C. Over Head Water Reservoir as per departmental design, drawing & specification with R.C.C. Bored Pile & Pile Cap for Augmentation of laying distribution system to extend the benefit of 100% House hold in Zone-VII (Binodpur) at KULTALI Block within Mega Surface water based Water Supply scheme of Falta-Mathurapur District South 24 Pgns. under South 24 Pgns Water Supply Division-1, PHE Dte. [SM / 18221] |  |  | ORD/001182/2024-2025 | 629/SWD-I | 28/02/2025 | 25/12/2025 | PATH MAKERS | 436.4 | 0 | 0 | 0
Total | [13 empty] | 3283.8 | 0 | 0